## Sheet1
HULL 2017 "Look Up"
[5 empty] | 2016 | [7 empty] | 2017 | [12 empty] | 2018
[13 empty] | Made in Hull |  |  | Roots & Routes |  |  | Freedom |  |  | Tell the World
|  | H2017 | Partner |  | May | jun | jul | aug | sep | oct | nov | dec | jan | feb | mar | apr | May | jun | jul | aug | sep | oct | nov | dec | jan | feb
Season | Project | budget | budget | Total
Made in | Zephyr | 85000 | BIG | 85000 | May: feasibility; sep: design/make
Hull | Roadsworth (move to R&R)
| Michael Pinsky | 80000 |  | 80000 | May: design and permissions
| The Deep/Chris Dobrowolski | 20000 | 17500 | 37500 | May: visit; jul: research; aug: MOU
Roots & | Transmigration | 35000 |  | 35000 | May: visit; jul: research
Routes | Princes Quay | 60000 |  | 60000 | aug: MOU; sep: visit; oct: research
| The Deep/Artist 2 | 15000 | 15000 | 30000 | aug: visit; sep: research
| Roadsworth | 15000 |  | 15000 | sep: visit
Freedom | GF Smith |  | 200000 | 200000 | May: proposal /discussions/agreement; aug: MOU; sep: visits; oct: site agreements/permissions
| Hull School Art & Design | 20000 |  | 20000 | May: visit; jun: research; aug: MOU
| The Deep/Tania Kovats? | 20000 | 20000 | 40000 | jun: visit; jul: research
| KW | 40000 |  | 40000
| RIBA competition | 50000 | 50000 | 100000 | bar: Tell the World nov
Tell the | The Deep/Studio Roosegaard | 45000 | 40000 | 85000 | sep: visit
World | Trinity lighting Nayan | 60000 |  | 60000
| Princes Quay Christmas | 10000 |  | 10000 | aug: MOU
| Hull Christmas Lights | 15000 |  | 15000
| Management | 170500 |  | 170500
| Deep Management allowance |  | 7500 | 7500
| HC/AK expenses | 5000 |  | 5000
| Artist site visit budget | 5000 |  | 5000
| TOTAL | 750500 | 350000 | 1100500
Key
feasibility
proposal agreed
Design
Permission/consent
Make
Install
On site
Take down
Other event (with note)
Note on I6: hazel colquhoun: 9 Aug presentation of feas study - go ahead date
Note on J6: hazel colquhoun: blade will be being made while design and fabrication carried out of supports
Note on M6: hazel colquhoun: practice lifts in yard
Note on V17: hazel colquhoun: Apathy Band gig at Freedom festival
Note on I20: hazel colquhoun: brief & site agreed
Note on K20: hazel colquhoun: shortlist agreed
Note on J25: hazel colquhoun: Tender process
Note on N25: hazel colquhoun: appointment