## Sheet1
DATE | TIME | LOCATION | ACTIVITY | TEAM | PRODUCTION | NOTES
2016-10-31 |  |  | SITE PREP AND PLANNING | x 3
2016-11-01 |  | HULL | SITE PREP AND PLANNING | Rich, Will, Chloe
2016-11-02 |  |  | SITE PREP AND PLANNING | x 3
2016-11-03 |  |  | SITE PREP AND PLANNING | x 3
2016-11-04 |  |  | SITE PREP AND PLANNING | x 3
2016-11-07
2016-11-08 | 14:00 | Leeds | Review point - Niccy and Sean to studio | Rich and Catherine
2016-11-09
2016-11-10
2016-11-11
2016-11-14 |  | Contingency | Chloe remotely for prep
2016-11-15 |  | Hessle Road | FILMING WITH BENCH | x 4 |  | Over night accomodation?
2016-11-16 |  | Springbank | FILMING WITH BENCH | x 4
2016-11-17 |  | Contingency
2016-11-18 |  | Contingency |  |  |  | No Rich H
2016-11-21 |  | TBC | GO PRO FILMING/EDITING | x 3 |  | Sign off point one
2016-11-22 |  | TBC | GO PRO FILMING/EDITING | x 3
2016-11-23 |  | TBC | GO PRO FILMING/EDITING | x 3
2016-11-24 |  | TBC | GO PRO FILMING/EDITING | x 3
2016-11-25 |  | TBC | GO PRO FILMING/EDITING | x 3
2016-11-28 |  | Leeds | EDITING
2016-11-29 |  | Leeds | EDITING
2016-11-30 |  | Leeds | EDITING
2016-12-01 |  | Leeds | EDITING
2016-12-02 |  | Leeds | EDITING
2016-12-05 |  |  | TECH Building system and programming | Ben and Crofty
2016-12-06 |  |  | TECH Building system and programming | Ben and Crofty |  | Sign off point two
2016-12-07 |  |  | TECH Building system and programming | Ben and Crofty
2016-12-08 |  |  | TECH Building system and programming | Ben and Crofty
2016-12-09 |  |  | TECH Building system and programming | Ben and Crofty
2016-12-12 |  |  | CONTINGENCY |  |  | Sign off point three if needed
2016-12-13 |  |  | CONTINGENCY
2016-12-14 |  |  | CONTINGENCY
2016-12-15 |  |  | CONTINGENCY
2016-12-16 |  |  | CONTINGENCY
2016-12-19
2016-12-20
2016-12-21 |  |  | INSTALL TEST IN SHOPS | Vic, Ben, Rich, Catherine and Crofty
2016-12-22 |  |  | INSTALL TEST IN SHOPS
2016-12-23 |  |  | INSTALL TEST IN SHOPS
2016-12-26
2016-12-27
2016-12-28 |  |  | 105 GET IN TBC
2016-12-29 |  |  | WHITEFRIARGATE TEST TBC
2016-12-30
2016-12-31
2016-01-01 |  |  | OPENING
2016-01-02 |  |  | HAND OVER INSTALLATION RUNNING TO GC