## Sheet1
FLOOD-ALL AT SEA Draft Schedule
2016-09-01 | Research Meetings with executive Producer, TV Director and Line Producer advice.
Draft of Budget, Treatment etc to BAC by 12th September
Feedback and discuusions with BAC.
Confirm site with Hull 17 and agree Terms with Hull 17 for project.
2016-10-01 | Further researcha and treatment and Budget update rady for BBC
Decision from BBC
2016-11-01 | Confirm and contract TV Direcotr and key creative teams. Site agreements in place.
2016-12-01 | Scope and hiring of production personel.
2017-01-01
2017-02-01 | Draft of Script and designs
2017-03-01 | Casting
2017-04-01 | Tests to be carried out following Part 1 Flood
2017-05-01 | Further week testing in location
2017-05-29 | Build
2017-05-30 | Build
2017-05-31 | Build
2017-06-01 | Build
2017-06-02 | Build
2017-06-03 | Build
2017-06-04
2017-06-05 | Test
2017-06-06 | Test
2017-06-07 | Test
2017-06-08 | Test
2017-06-09 | Test
2017-06-10 | Test
2017-06-11
2017-06-12
2017-06-13 | Rehearsal
2017-06-14 | Rehearsal
2017-06-15 | Rehearsal
2017-06-16 | Rehearsal
2017-06-17 | Rehearsal
2017-06-18 | Community Cast rehearsal
2017-06-19
2017-06-20 | Rehearsal
2017-06-21 | Rehearsal
2017-06-22 | Rehearsal
2017-06-23 | Rehearsal
2017-06-24 | Rehearsal
2017-06-25 | Community Cast rehearsal
2017-06-26
2017-06-27 | Rehearsal
2017-06-28 | TV Arrive and Set Up
2017-06-29 | Run through
2017-06-30 | Rehearsal
2017-07-01 | Live Broadcast