- Project Blade – Project Structure Rev. 1

Delivery Team

Delivery Team

Transport Taskgroup

Transport Taskgroup

Structures Taskgroup

Structures Taskgroup

Operations & Installation Taskgroup

Operations & Installation Taskgroup

| DELIVERY TEAM |  |
| --- | --- |
| Role: - To implement the project within the agreed budget & timescale - To manage Planning - To own the Risk Register - To manage Health & Safety - To inform Communications |  |
| Membership |  |
| Chris Clay (Chair?) | Hull 2017 |
| Sam Hunt | Hull 2017 |
| Andrew Knight | Hull 2017 |
| Hazel Colquhoun | Hull 2017 |
| Garry Taylor | Hull City Council |
| Jason Speedy | Siemens |
| Chris Wetherall | Siemens |
| Nayan Kulkarni | Artist |
| Richard Bickers | Arup |
| Ben McKnight | Hull 2017 |
| Meetings / Reporting |  |
| - Fortnightly meetings (Thursdays at 9.00am) - Receive reports from Task groups |  |

| TRANSPORT TASKGROUP |  |
| --- | --- |
| Role: - To plan the transport of the blade from the yard to Queen Victoria Square (including craneage) - To plan the removal of the blade - To secure required transport & installation permits - To execute the transport operations - To provide craneage for the “trial installation” - To review and add to risk register |  |
| Membership |  |
| Richard Bickers (Chair) | Arup |
| Javed Hussain | Arup |
| Richard Townsend | Hull City Council (Highways) |
| Paul Robinson | Hull City Council (Transport Planning) |
| Anthony Granville | Siemens |
| Dave Smith (to be confirmed) | ALE |
| To be confirmed | North Midland |
| Members of Delivery Team – as needs basis |  |
| Meetings / Reporting |  |
| - Fortnightly meetings |  |

| STRUCTURES TASKGROUP |  |
| --- | --- |
| Role: - To design the supports for the blade - To undertake design checks (including check with Siemens) - To fabricate supports - To review and add to risk register |  |
| Membership |  |
| Richard Bickers (Chair) | Arup |
| Martin McGovern | Arup |
| Nayan Kulkarni | NK Projects Ltd |
| Anthony Granville | Siemens |
| ? | Pearl Green (to be confirmed) |
| Members of Delivery Team – as needs basis |  |
| Meetings / Reporting |  |
| - Fortnightly meetings |  |

| OPERATIONS & INSTALLATION TASKGROUP |  |
| --- | --- |
| Role: - To plan and coordinate maintenance & security activities whilst Blade is installed - To secure the Events Licence from HCC - To engage with Hull CC Street scene & Police etc. - To coordinate with other H2017 events etc. - To plan the installation day (and events leading up to this) - To coordinate physical installation activities with communications etc. - To organise volunteer support - To review and add to risk register |  |
| Membership |  |
| Chris Clay (Chair) | Hull 2017 |
| Andrew Knight/Hazel Colquhoun | Hull 2017 |
| Andy Burton | Hull City Council (Streetscene) |
| Milly Hennayke | Arup |
| Members of Delivery Team – as needs basis |  |
| Meetings / Reporting |  |
| - Monthly meetings, weekly nearer to Installation Day |  |