## 6 Panel Rolled Circle Free 3m h
Pezo von Ellrichshausen and Felice Varini
|  | Budget | Actual/Anticipated | Variance | Who has actually paid cost? | RIBA Notes
1 | Artwork
1.1 | Artwork application | 7000 | 8777.95 | -1777.95 |  | The artwork application taken out
|  | 7000 | 8777.95 | -1777.95
2 | Steel fabrication
2.1 | 192 no. 3mm bespoke perforated steel, punched | 18672 | 18672 | 0 | RIBA procurement (RMIG)
2.2 | 192 no. 3mm bespoke perforated steel, rolled and folded | 14976 | 14384 | 592 | RIBA procurement (Barnshaws)
2.3 | All other steel parts | 18138 | 18775.84 | -637.84 | RIBA procurement (Kloeckner)
|  | 51786 | 51831.84 | -45.84
setWorks cost
3.1 | Airmatic (previously item 2.15?) | 12300 | 17400 | -5100
3.2 | Rerolled sections (Barnshaws) | 0 | 750 | -750
3.3 | Transport from Barnshaws to Airmatic | 0 | 3815 | -3815 | 6 loads | Who authorised these costs?
3.4 | Transport from Airmatic to Wedge | 900 | 3180 | -2280 | 5 loads | Who authorised these costs?
3.5 | Transport from Airmatic to Barnshaws | 0 | 560 | -560 | 1 load | Who authorised these costs?
3.6 | Transport from Wedge to site | 900 | 5175 | -4275 | 1 Week standby, 7 loads to site, Manchester - Bury pick up and Bury - Wedge pick up | Who authorised these costs?
0
0
4.1 | Plywood (96 sheets) | 900 | 900 | 0
4.2 | Labour to CNC | 2800 | 2800 | 0
4.3 | Onsite build (4x 8 days) | 7500 | 12000 | -4500
4.4 | Hire equipment cost | 3000 | 3000 | 0
4.5 | H+S barriers etc | 600 | 600 | 0
0
5.1 | Additional Barrier hire week 2 | 0 | 600 | -600 |  | Is this for artwork?
5.2 | Additional Tower hire week 2 | 0 | 190 | -190 |  | Is this for artwork?
5.3 | Materials, protection etc for painters | 0 | 590 | -590 |  | Is Hull2017 claiming RIBA this through Setworks?
0
6.1 | 2 days H+S overseeing Felice RAMS etc | 0 | 600 | -600 | Hull 2017 - Part of £6,150 Hazel has on her budget schedule
6.2 | 5 days H+S overseeing general | 0 | 1500 | -1500 | Hull 2017 - Part of £6,150 Hazel has on her budget schedule
6.3 | 3 ½ nights site management | 0 | 1575 | -1575 | Hull 2017 - Part of £6,150 Hazel has on her budget schedule
6.4 | 5 days additional site management | 0 | 1500 | -1500 | Hull 2017 - Part of £6,150 Hazel has on her budget schedule
6.5 | Hotels associated with extra days | 0 | 375 | -375 | Hull 2017 - Part of £6,150 Hazel has on her budget schedule
6.6 | 1 day retrospective paperwork for PD | 0 | 300 | -300 | Hull 2017 - Part of £6,150 Hazel has on her budget schedule
6.7 | 1 day O+M collation and overview | 0 | 300 | -300 | Hull 2017 - Part of £6,150 Hazel has on her budget schedule
|  | 28900 | 57710 | -28810
7.1 | Deinstall Onsite build (4x 5 days) | 6000 | 7500 | -1500 |  | Why has this cost item increased? Who has authorised this?
7.2 | Hire equipment cost | 3000 | 3000 | 0
7.3 | H+S barriers etc | 600 | 600 | 0
7.3 |  | 900 | 0 | 900
|  | 10500 | 11100 | -600
8 | Travel cost | 3000 | 3352.26 | -352.26
|  | 3000 | 3352.26 | -352.26
Other costs
| Marketing | 1500 | 2000 | -500 | Hull 2017
| Security/invigilation | 12000 | 14025 | -2025 | Hull 2017
| Portable lights for RIBA install | 0 | 111.15 | -111.15 | Hull 2017
| RIBA @ Trinity Square - Cbling - 1 week hire as per quote 17-0830.01 | 0 | 60 | -60 | Hull 2017
| Scaffolding Tower for RIBA | 0 | 366.24 | -366.24 | Hull 2017
| 4 visits to Trinity Square by an electrician for the A Hall for Hull exhibition | 0 | 388.4 | -388.4 | Hull 2017
| Materials for Artwork installation HC | 0 | 313.48 | -313.48 | Hull 2017
| Materials for Artwork installation AK | 0 | 80.46 | -80.46 | Hull 2017
| Extra security due to lighting being switched off | 0 | 600 | -600 | Hull 2017
| URGENT ALL RISKS INSURANCE REQUIRED FROM 27.9.17 | 0 | 560 | -560 | Hull 2017
| Opening agreed spend | 1500 | 2000 | -500 | Hull 2017
| Opening apparent overspend | 0 | 931.7 | -931.7 | Hull 2017
| Hoardings moving | 0 | 1780.48 | -1780.48 | Hull 2017
| Extra spend on security - on site decisions | 0 | 900 | -900 | Hull 2017
| Petty cash | 0 | 5 | -5 | Hull 2017
| Wine for Hall for Hull launch | 0 | 968 | -968 | Hull 2017
|  | 15000 | 25089.91 | -10089.91
| Design Fees | 3850 | 3925.02 | -75.02 | RIBA
| Suppliers cost / Selection panel fee | 1200 | 1200 | 0 | RIBA
| Suppliers cost | 4700 | 4700 | 0 | RIBA
| Travel cost | 5500 | 5502.73 | -2.73 | RIBA
| Planning application | 400 | 482 | -82 | RIBA
| Travel / train | 100 | 101.1 | -1.1 | RIBA
|  | 15750 | 15910.85 | -160.85
| Total | 131936 | 173772.81 | -41836.81