CREATIVE COMMUNITIES PROGRAMME
END OF PROJECT REPORT

GENERAL INFORMATION

| PROJECT NAME: | Hull Fishing Heritage Art Exhibition |
| --- | --- |
| PROJECT LEAD: | Tony Cotson |
| REPORT DATE: | 31st August 2017 |

INTRODUCTION

Everyone who receives a grant from the Creative Communities Programme must complete this End of Project Report. Please read it straight away – you will need to collect the information throughout the lifetime of your project.

Please refer to your Agreement, and any changes you agreed with us, when you complete this Report.

This End of Project Report tells us:

- What has happened during your project as a whole;

- Your final income and expenditure figures;

- What you have learned from the project, how you have adapted to these learnings, and what you plan to do with this learning in future.

We will send you a separate online survey about your experience of the Creative Communities Programme as a grant recipient. We will process the information you give us to understand:

- The outcomes and impacts of our grant and support on your organisation;

- The effectiveness of our services and grants administration; and

- What key things the city needs to be aware of in future, when supporting community level arts and culture projects.

We also use this information to report to our funders.

Please email this activity report to: creativecommunities@hull2017.co.uk

- PROJECT REPORT

Please provide a brief update (3 or 4) sentences on each of the following areas to let us know how your project went, what you’ve learnt and how well we supported you.

The project exceeded all expectations with numbers attending the impact we had with our local schools and the way the exhibition brought local and wider community groups together.

We learnt first hand about the power of art to unite people and to tell human stories.

The training programme was very helpful, and the volunteers were a credit to the city.

EVENT PLANNING AND PROJECT MANAGEMENT

We learnt a great deal about effective marketing in the modern climate. We utilised social media to reach a wider audience and we honed our marketing through the production of advertising, video and print products.

The permission to use the Hull 2017 brand gave our project credibility and gave us the confidence to exceed our own expectations.

MARKETING AND COMMUNCIATIONS, PARTICIPATION AND LEARNING

RISK MANAGEMENT

The access training was very helpful and gave us the insight to ensure our assessments were sufficient to eliminate potential risks. Our building access was appreciated by many who attended using wheelchair and mobility scooters.

BUDGET

In this section we ask for a final summary of the income and expenditure of your activity to date.

Please complete the Budget Template provided. The template includes instructions on how to complete it.

Please use the space below for any comments and supporting information.

Specific Requirements - VAT

If you are registered for VAT, your expenditure figures should not include VAT that you can claim back. If you are not registered for VAT, your figures should include VAT. You may need to get advice from your own accountant or the relevant tax office. For information about VAT and other taxes, contact HM Revenue and Customs (HMRC) through their website at www.hmrc.gov.uk

B. MONITORING & EVALUATION REPORT

- Event Delivery

How did you do on reaching the targets laid out for project activity?

|  | ORIGINAL TARGET* | REVISED TARGET* | TOTAL* |
| --- | --- | --- | --- |
| PROJECT VENUE/LOCATION |  |  |  |
| HU1 – HU9 | 2500 | 2500 | 3000 |
| Not HU1 – HU9 | 500 | 500 | 650 |
| ACTIVITY |  |  |  |
| Number of performances |  |  |  |
| Number of exhibition days | 17 | 17 | 17 |
| Number of commissions* |  |  |  |
| Number of sessions for education, training or taking part* | 25 | 25 | 25 |
| Number of accessible activities |  |  |  |

*Original target: target(s) listed within your contract
*Revised target: new suggested targets now that your project planning and delivery is underway
*Total: final figures for the project as a whole
*Commissions: a commission is defined as the hiring or payment to an artist / artistic company to create an art work or performance. A commission can be wholly or partly funded by you / your organisation.
*Sessions for education, training or taking part: includes guided sessions, learning sessions, skills development workshops, formal training of volunteers, practical workshops, all other community/public facing workshops.

Hull Fishing Industry: The development work began with research at local libraries, Hull History Centre, Hull Maritime Museum and collaboration with Dr Alec Gill, Peter Naylor and the local Fishing Heritage Groups. We attended fishing heritage events such as the Lost Trawlermen’s Day and interviewed ex skippers and current fishermen as well as windows and family members.

The story was presented in a variety of formats including 2D and 3D artwork, factual information, interactive activities and video footage.

If your project incorporated heritage, please briefly say how you developed, presented and / or told people about heritage or historical content, e.g. using heritage buildings or sites, collecting oral history (stories and memories), displaying historical artworks or collections, working with museums or archives, sharing or presenting historical stories or events.

- Project Delivery Team

Who was involved in delivering your project? Please include yourself, employees and any freelancers that you contracted for this project.

|  | TOTAL NO. INDIVIDUALS | TOTAL NO. OF DAYS WORKED | TOTAL NO. OF HU1-HU9 RESIDENTS | TOTAL NO. OF DAYS WORKED BY HU1-HU9 RESIDENTS |
| --- | --- | --- | --- | --- |
| CATEGORY OR ROLE |  |  |  |  |
| Project Manager(s) | 4 | 200 | 4 | 200 |
| Artists | 30 | ? | 25 | ? |
| Production/exhibition staff | 8 | 38 | 8 | 38 |
| Other staff | 20 | 35 | 20 | 35 |
| Volunteers | 20 | 80 | 20 | 80 |

Using the equal opportunities form provided in the Toolkit, please complete the Total column within the tables below for all people involved in the Delivery Team for your project. We recommend that you ask all members of the project Delivery Team to complete this form at the start of the project, and include it as part of the contracting process for any new staff or freelancers going forward.

|  | TOTAL |  |  | TOTAL |
| --- | --- | --- | --- | --- |
| AGE GROUPS – DELIVERY TEAM |  |  | DISABILITY/LONG TERM ILLNESS – DELIVERY TEAM |  |
| 16-17 years | 8 |  | Yes | 0 |
| 18-19 years | 8 |  | No | 81 |
| 20-24 years |  |  | Prefer not to say | 0 |
| 25-29 years | 5 |  | CONDITIONS – DELIVERY TEAM |  |
| 30-34 years | 12 |  | Learning disability |  |
| 35-39 years | 7 |  | Long-term illness/condition |  |
| 40-44 years | 8 |  | Sensory impairment |  |
| 45-49 years |  |  | Mental Health condition |  |
| 50-54 years | 6 |  | Physical impairment |  |
| 55-59 years | 5 |  | Cognitive impairment |  |
| 60-64 years | 6 |  | Other |  |
| 65-69 years | 12 |  |  |  |
| 70-74 years | 4 |  |  |  |
| 75+ years |  |  |  |  |
| Prefer not to say |  |  |  |  |

|  | TOTAL |  |  | TOTAL |
| --- | --- | --- | --- | --- |
| GENDER - DELIVERY TEAM |  |  | ETHNICITY – DELIVERY TEAM |  |
| Male | 35 |  | Welsh/English/Scottish/Northern Irish/British | 78 |
| Female | 46 |  | Irish |  |
| Transgender |  |  | Gypsy or Irish Traveller |  |
| Other |  |  | Any other White background |  |
| Prefer not to say |  |  | White and Black Caribbean |  |
|  |  |  | White and Black African |  |
|  |  |  | White and Asian |  |
|  |  |  | Any other Mixed/multiple ethnic background |  |
|  |  |  | Indian |  |
|  |  |  | Pakistani |  |
|  |  |  | Bangladeshi |  |
|  |  |  | Chinese |  |
|  |  |  | Any other Asian background |  |
|  |  |  | African | 3 |
|  |  |  | Caribbean |  |
|  |  |  | Any other Black/African/Caribbean background |  |
|  |  |  | Arab |  |
|  |  |  | Any other ethnic group |  |
|  |  |  | Prefer not to say |  |

Thinking about your project as a whole, what would you say have been the main successes and challenges for you and your project delivery team (approximately 500 words):

Successes: Bringing together the community as we encouraged groups to join us as we shared the fishing heritage story. Young people, who did not know much about Hull’s fishing heritage now have a lasting experience from which to draw. Our local schools really embraced the opportunity to visit the exhibition and incorporate the content into their curriculum.

Our exhibition gave ex trawlermen a platform to share their personal stories with former shipmates as well as younger visitors to the exhibition.

The exhibition has ignited a passion for the story to be part of an annual legacy.

This can include formal and informal feedback given to you by staff and / or your own observations. You can use notes or minutes from project team meetings; informal conversations; emails; etc. to inform this.

The exhibition has raised the profile of art in the community at the same time as giving local artists an opportunity to display their work alongside art received from overseas. The profile of the church as a community hub and cultural venue is now established across the city.

A new generation of artists have now become inspired by Hull’s fishing heritage and in the process have learnt a great deal about their own identities and family histories.

The exhibition has reignited a sense of pride among the Hessle Road community and given hope that the story will not be forgotten. The exhibition also brought together opposing fishing heritage groups and through positive celebratory work it has encouraged all within the fishing community to support the venture and feel part of a wider and inclusive team with a shared ethos.

Links with Iceland were formed as we explored shared loss, culminating in a plaque dedicated to joint Hull and Icelandic fishermen lost to the sea. This was dedicated by the Right Reverend Alison White, Bishop of Hull at the packed Sea Sunday service that brought the exhibition to an end.

As we write a civic group of 36 Icelandic visitors to Hull are to visit the church as part of their Hull civic visit. Once again, recognition of the success of the exhibition and the role that the Fishermen’s Church plays in HUll’s fishing heritage.

Challenges: The workload was a challenge, especially the completing of forms but this we accept was necessary.

- Audiences & Participants

How many people, in total, attended or participated in the project as a whole?

| TYPE OF ENGAGEMENT | TOTAL | % FROM HU1-HU9 |
| --- | --- | --- |
| Number of audience members* | 3650 | 82 |
| Number of participants* | 50 | 98 |
| TOTAL BENEFICIARIES |  |  |

*The % can be taken from the results of your audience and participant surveys or box office reports
*‘Audience members’ includes people going to an exhibition or performance, and people getting access to work that is printed, recorded, broadcast or on the internet.
*‘Participants’ means those doing the activity.

Please complete the Total column within the tables below. You should collect this information using the Audience Survey (which will be designed with support from the Hull 2017 team) and / or via the Participant Equal Opportunities Form provided in the Toolkit.

|  | TOTAL |  |  | TOTAL |
| --- | --- | --- | --- | --- |
| AGE GROUPS – AUD. & PART. |  |  | DISABILITY/LONG TERM ILLNESS – AUD. & PART. |  |
| 0-2 years |  |  | Yes |  |
| 3-5 years |  |  | No |  |
| 6-10 years |  |  | Prefer not to say |  |
| 11-15 years |  |  | CONDITIONS – AUD. & PART. |  |
| 16-17 years |  |  | Learning disability |  |
| 18-19 years |  |  | Long-term illness/condition |  |
| 20-24 years |  |  | Sensory impairment |  |
| 25-29 years |  |  | Mental Health condition |  |
| 30-34 years |  |  | Physical impairment |  |
| 35-39 years |  |  | Cognitive impairment |  |
| 40-44 years |  |  | Other |  |
| 45-49 years |  |  |  |  |
| 50-54 years |  |  |  |  |
| 55-59 years |  |  |  |  |
| 60-64 years |  |  |  |  |
| 65-69 years |  |  |  |  |
| 70-74 years |  |  |  |  |
| 75+ years |  |  |  |  |
| Prefer not to say |  |  |  |  |

|  | TOTAL |  |  | TOTAL |
| --- | --- | --- | --- | --- |
| GENDER - AUDIENCES |  |  | ETHNICITY – AUDIENCES |  |
| Male |  |  | Welsh/English/Scottish/Northern Irish/British |  |
| Female |  |  | Irish |  |
| Transgender |  |  | Gypsy or Irish Traveller |  |
| Other |  |  | Any other White background |  |
| Prefer not to say |  |  | White and Black Caribbean |  |
|  |  |  | White and Black African |  |
|  |  |  | White and Asian |  |
|  |  |  | Any other Mixed/multiple ethnic background |  |
|  |  |  | Indian |  |
|  |  |  | Pakistani |  |
|  |  |  | Bangladeshi |  |
|  |  |  | Chinese |  |
|  |  |  | Any other Asian background |  |
|  |  |  | African |  |
|  |  |  | Caribbean |  |
|  |  |  | Any other Black/African/Caribbean background |  |
|  |  |  | Arab |  |
|  |  |  | Any other ethnic group |  |
|  |  |  | Prefer not to say |  |

Thinking about your project as a whole, what would you say have been the main successes and challenges for your audience members / participants:

See previous section

This can include formal and informal feedback given to you by staff and / or your own observations. You can use comments books; informal conversations; emails; etc. to inform this. It must also include any findings from your Audience/Participant Survey (A Question Bank is provided for the Audience/Participant Survey, from which you will build your own project questionnaire with support from Hull 2017 staff).

- Online Engagement

How did your project impact upon your online presence?

|  | TOTAL PAGE VIEWS | UNIQUE PAGE VEIWS |
| --- | --- | --- |
| Website views relating to project | 0 | 0 |

|  | LIKES/FOLLOWERS AT START | LIKES/FOLLOWERS AT END | IMPRESSIONS ON POSTS RELATING TO THE PROJECT | ENGAGEMENTS WITH POSTS RELATING TO THE PROJECT |
| --- | --- | --- | --- | --- |
| Facebook | 0 | 412/414 |  |  |
| Twitter | 0 | 97 |  |  |
| Instagram | 0 | 70 |  |  |
| Other | 0 |  |  |  |

DEFINITIONS

- Followers include: Facebook Page Likes / Profile Friends; Twitter Followers; YouTube Subscribers; etc.

- Impressions: impressions (“views”) of Facebook posts linked to CCP project; impressions (“views”) of Twitter tweets linked to CCP project; views of YouTube videos linked to CCP project; etc.

- Engagements: Facebook posts, likes, shares, comments; Twitter tweets, retweets, likes; YouTube shares, comments; etc.

Fascinating and moving, great conversation, thanks for all the hard work. Jane Emson.

Fabulous, stirred up a lot of memories of when my dad and uncle went to sea. K. Butcher-Hastie

Loved it, and everyone made you feel welcome. Stacy Smith Carter

This is a brilliant community, never forget those who sailed before us. Carl Bez Kahn

End of project feedback returns with City of Culture

In the boxes below, please share a selection of audience comments or quotes from social media made about your project. Please provide different examples to those in your Project Update Report:

- Partners

How many partners were involved with the project?

|  | TOTAL BASED IN HU1 – HU9 | TOTAL BASED OUTSIDE HU1 – HU9 |
| --- | --- | --- |
| PARTNER TYPE |  |  |
| Artistic partner (e.g. theatre, art gallery, music venue) |  |  |
| Heritage partner (e.g. museum, archive) | 3 | 1 |
| Funder (e.g. Arts Council England, business, private trust) | 2 |  |
| Public Sector partner (e.g. libraries, GPs) | 2 |  |
| Voluntary sector partner (e.g. community group, charity) | 3 |  |
| Education (e.g. school, college, university) | 1 |  |
| Other |  |  |
| PARTNERSHIP STAGE |  |  |
| Number of new partnerships established via this project | 10 | 1 |
| Number of existing partners involved in this project | 1 |  |

See previous successes and challenges.

Thinking about your project as a whole, what would you say have been the main successes and challenges for your partners:
This can include formal and informal feedback given to you by staff and / or your own observations. You can use notes or minutes from partner meetings; informal conversations; emails; etc. to inform this.