Bob & Roberta Smith at Hull College of Art & Design (HSAD)

Bob & Roberta Smith is developing a work based on the concept of creating a “Centre for Freedom of Expression” at HSAD, during the summer recess 2017.  This will fall appropriately in the Freedom season of Hull 2017 (July – September).

The work is envisaged to comprise a number of elements:

- a sign, designed by the artist, to be installed on the exterior of the building during July and August 2017 proclaiming the “Centre for Freedom of Expression”

- the exhibition of a new painting by the artist on the issue of Freedom of Expression (ownership to be retained by the artist)

- an exhibition of existing works by the artist which are linked to Freedom of Expression

- a “summer school” run by the artist over 1 or 2 days, on the theme of Freedom of Expression

- 2 gigs by the Apathy Band, acoustic set at HSAD and amplified at Kardomah

- a series of talks and events (e.g. discussion/workshops), to be developed with HSAD and partners such as WISE (Wilberforce Institute for the Study of Slavery and Emancipation)

- exhibition of works by students at HSAD which have been developed during the 2016/2017 academic year on the subject of Freedom of Expression and the arts

Programme

September 2016 - Bob & Roberta Smith talks to the student body as an introduction to his work.

November 2016 – maquette for sign completed and delivered to HSAD

February 2017 – Bob & Roberta Smith to talk to student body and show his film made for BBC4’s Modern Identity season “The Protestor” (broadcast 17 Nov 2016).

July 2017 – sign installed; exhibition installed

August 2017 – short series of talks/events  at HSAD; 1 or 2 day workshop/”summer school” at HSAD lead by Bob; Apathy Band gigs at HSAD and Kardomah. (Gig date provisional 31 Aug).

All of the August activities could take place in 1 week, linked to the Freedom season Symposium planned with the University.