## Slide 1: Project B75
Presentation to Project Board
9th August 2016

## Slide 2: Concept <<Andrew Knight>>
H2017 - Made in Hull Season
Siemens in Hull – future for Hull – Black energy to Green energy
Blade manufacture – handcrafted, shipbuilding skills etc. – employing people in Hull
Siemens collaboration – using in blade made by Hull people, made in Hull (tbc)
Timing – why January 1st for installation? Removed on 2nd April
Project B75

## Slide 3: The Installation <<Nayan Kulkarni>>
Photos of trip to Albourg – physicality of the blade
Name B75
Project B75

## Slide 4: The Installation <<Nayan Kulkarni>>
Ambition for Installation – being disruptive, highly visual statement
Where exhibited – Queen Vic Square
How exhibited - angle
Want it to be a surprise
Project B75

## Slide 9: Transport <<Richard Bickers or Mike Millage>>
High level review of routing options found “Route D” to be the most feasible to transport the blade from Alexandra Docks to Queen Victoria Square in Hull.
Project B75
Alexandra Docks
Queen Victoria Square

## Slide 10: Transport <<Richard Bickers or Mike Millage>>
Blade being delivered by ALE – Specialist abnormal load handlers.
Blade to be transported on SPMTs. Casing at “root” end and clamp towards “tip” end.
Project B75
Tip end of blade Clamp on SPMT Casing (root end) on Tractor/SPMT
Affected Street Apparatus and “pre-installation” activities.

## Slide 11: Installation <<Richard Bickers>>
Pre-fabricated steelwork structures at root & tip end incorporating standard fixings used by Siemens
Project B75
Root support Tip Support

## Slide 12: Installation <<Richard Bickers>>
Supports sit on Public Realm surface
Project B75
Mock Up in December 2012
Benches positioned below blade where 2.3m headroom clearance cannot be achieved

## Slide 13: Preferred Arrangement
Project B75

## Slide 14: Alternative Arrangement
Project B75

## Slide 15: Permissions <<Richard Bickers>>
Planning Consent – two scenarios
Event license (or similar)
Abnormal Loads license
Removal/reinstatement of street apparatus, regulatory signs and safety barriers
Police escort
Traffic Management/Temporary Traffic Regulation Orders
Oversail license
Project B75

## Slide 16: Ownership and Maintenance<<Richard Bickers>>
Ownership and Liabilities – Options for loan agreement
Insurance
Security Presence
Secure Design
Maintenance – cleaning, repairing and repainting
Project B75

## Slide 17: Programme <<Richard Bickers>>
Critical Path Activities | 2016 |  |  |  |  | 2017 | 
 | Aug | Sept | Oct | Nov | Dec | Jan | Feb
Presentation to Project Board |  |  |  |  |  |  | 
Go/No Go decision by Project Board |  |  |  |  |  |  | 
Design of Supports |  |  |  |  |  |  | 
Fabricator Procurement |  |  |  |  |  |  | 
Fabrication of Supports |  |  |  |  |  |  | 
Pre-installation – Mock Up |  |  |  |  |  |  | 
Pre-installation – Socketing of Street Furniture |  |  |  |  |  |  | 
Completion of Queen Victoria Square Public Realm Works |  |  |  |  |  |  | 
Installation |  |  |  |  |  |  | 
Removal |  |  |  |  |  |  | 
Project B75

## Slide 18: Programme <<Richard Bickers>>
Initial Detailed Programme for Installation
Project B75
Date / Time | Activity
Friday 30th December 2016 | 
11.00 | Meeting with key project members to review following: Completion of preparation works Detailed Installation programme Risk Register
13.00 | Team building meeting with all persons involved. Remind them of roles & responsibilities
Sunday 1st January 2017 | 
6.00 | Meet at Siemens Yard. Health and Safety Induction
6.30 | Load steel supports onto lorries – transport to site Cranes into position in Queen Victoria Square Gangs start to remove street-furniture
7.30 | Blade leaves Siemens Yard under police escort Steel supports lifted into position and bolted together
8.30 (approx.) | Blade leaves A63 (Highways England property) Gangs start to replace street furniture
10.00 | Blade arrives in Queen Victoria Square
11.00 | Blade lifted into position
12.00 | Blade securing in position Safety checks
13.00 | Cranes demobilised & removed from site Clean Up
14.00 | Hand-over

## Slide 19: Costs<<Richard Bickers>>
Approach to cost estimate – bottom up
Transportation
Installation
Maintenance
Removal
Management and Consultancy
Cost for Blade, ALE’s input, storage, mock-up, Police and craneage are excluded from the cost estimate.
Project B75
Description | Estimated Cost
Installation | £119,000
Maintenance (28 days) | £23,320
Management and Consultancy | £70,000
Contingency (5% of above) | £10,616
Total | £222,936
Description | Estimated Cost
Transportation | £178,900
Removal | £59,100
Total | £228,000
Additional 28 days (incl. 5% Contingency) | £19,236

## Slide 20: Risk <<Richard Bickers>>
Key Project Risks
Project B75
Delay to QVS | High winds during installation and removal
Public interference during installation/removal | Planning consent delayed
Damage to Public Realm | Legal enforcement action
Budget exceeded | Temporary planning consent
Political objectors | Surprise element
Planning consent is not granted | New Year’s Eve
Fire | Climbing
People collision with blade | Straps securing blade

## Slide 21: Concluding Remarks <<Andrew Knight / Chris Clay>>
Potential media coverage – national / global
Messages
Making a Surprise
CGI
Project B75