## Org Chart
Last Testament of Lillian Bilocca - Organogram - Roles & Responsibilities
WORK STREAMS | HULL 2017 | HULL TRUCK THEATRE | FREELANCE | GUILDHALL TBD | NOTES
LEGAL & CONTRACTING
Commission writer | Lead (L): H17 Exec Producer
Transfer creative contracts | Joint (J): Legal Counsel | (J): Executive Director
Co-production agreement | (J): Legal Counsel | (J): Executive Director
Legal advice | (J): Legal Counsel | (J): Producer
Designs delivered |  | (J): Producer & Head of Prod | (J): Production Manager
Event Licensing |  | (J): Producer & Head of Prod | (J): Production Manager
Show licensing |  | (J): Head of Prod | (J): Production Manager
Show Timing |  | (L): Producer
Venue Contract |  | (L): Producer
Legal PRS |  | (L): Head of Prod / Administrator
Legal PPL |  | (L): Head of Prod / Administrator
Rights clearance on other footage or imagery |  | (L): Head of Prod / Administrator
Contractual Liability | (J): Legal Counsel | (J): Producer
Ownership | (J): Legal Counsel | (J): Producer
Performance rights |  | (L): Producer
Crediting on Shows |  | (L): Producer
TV rights |  | (L): Producer
Writer's rights | (J): Legal Counsel | (J): Producer
Contracting of suppliers |  | (J): Head of Prod | (J): Production Manager
Contracting of creatives | (J): Legal Counsel | (J): Producer
Contracting of actors & SM |  | (L): Producer / Administrator
Child licencing |  | (L): Administrator
Community company paperwork |  | (L): Producer / Community Coordinator
Venue Negotiation | CEO & Director | (L): Producer
Employers liability (Insurance all artists and staff) |  | (L): Head of Finance
Insurance Physical Production |  | (L): Head of Finance
Public liability |  | (J): Head of Finance |  | (J): Facilities Manager
Venue Insurance |  |  |  | (L): Facilities Manager
VENUE MANAGEMENT / FOH
Approve production design |  | (J): Producer / Head of Prod | (J): Production Manager
Floor plan |  |  | (L): Production Manager
Production Venue Management |  | (J): Head of Prod | (J): Production Manager
FOH systems |  | (L): FOH Manager
Audience journey |  | (L): FOH Manager
Dressing rooms |  |  | (L): Production Manager
Production office |  |  | (L): Production Manager
Toilets |  | (J): FOH Manager |  | (J): Duty Manager
Accreditation |  | (L): Admin Assist
MARKETING, TICKETING, PR
Performance schedule |  | (L): Producer / Head of Prod
Box office projections |  | (L): Producer / Exec Director
Pricing Strategy |  | (L): Producer / Comms Director
Launch/Onsale | (L): Director M, C & L / Comms Director | Producer / Comms Director
Ticketing Set-Up |  | (L): Box Office Manager
Seating & staging |  | (J): Producer / Head of Prod | (J): Production Manager
Concept for marketing & PR assets | Marketing Coordinator / Comms Director | (L): Comms Director / Producer
Brochure | Marketing Coordinator | (L): Comms Director / Producer
Leaflets | Marketing Coordinator | (L): Comms Director / Producer
FOH assets |  | (L): Comms Director / Producer
Website | (J): Head of Digital | (J): Emma
Social media | (J): Head of Digital | (J): Vicki
Digital media | (J): Head of Digital | (J): Emma / Vicki
Audience experience |  | (L): FOH Manager
PR & messaging | (J): Comms Director | (J): Comms Director / Producer | (J): PR Consultant
Press night | (J): Head of Arts Admin & Events | (J): Comms Director / FOH Manager / Producer
BBC documentary |  | (J): Producer | (J): Writer
Stakeholder development |  | (L): Comms Director / Development Manager
Monitoring & Evaluation | (L): M&E Manager | Comms Director
Sponsorship | Head of Partnerships | (L): Development Manager
Partnerships | Head of Partnerships | (L): Development Manager
PROJECT MANAGEMENT
Risk register |  | (L): Producer
Roles & responsibilities |  | (L): Producer
Organogram |  | (L): Producer
Project team meetings |  | (L): Producer
Budget management & Reporting |  | (L): Producer
Billing/ Open book accounting |  | (L): Finance Manager / Producer
FIT UP/ REHEARSAL / SHOW MANAGEMENT
H&S |  | (J): Head of Production | (J): Production Manager
Production Schedule |  | (J): Head of Production | (J): Production Manager
Production Budget |  | (J): Head of Production | (J): Production Manager
ESAG |  | (J): Head of Production | (J): Production Manager
CDM |  | (J): Head of Production | (J): Production Manager
Fit up |  | Head of Prod | (L): Production Manager
Fit up staff |  | Head of Prod | (L): Production Manager
Incident, accident & near miss reporting in fit up |  | (J): Head of Production | (J): Production Manager
Method statement for fit up |  | (J): Head of Production | (J): Production Manager
Rehearsal room risk assessment |  |  | (L): CSM
Rehearsal risk assessment |  |  | (L): CSM
Rehearsal scheduling (incl Community) |  |  | (J): Director / CSM
Production risk assessment |  | (J): Head of Production | (J): Production Manager
Risk Assessment for fit up |  | (J): Head of Production | (J): Production Manager
Rehearsal & show reporting |  |  | (J): CSM / Production Manager
Incident, accident & near miss reporting in show |  |  | (L): CSM
Staff welfare |  | (J): Head of Prod | (J): CSM / Community Coordinator / Production Manager
Safeguarding |  | (J): Head of Prod | (J): CSM / Community Coordinator / Production Manager
First aid - performers, staff |  | (J): Head of Prod | (J):CSM / Production Manager
First aid - audience members |  |  | (J): FOH Manager / Duty Manager
Security |  | (J): Head of Prod / FOH Manager | (J):CSM/ Production Manager | (J): Guildhall TBC
Equipment maintenance |  |  | (L): Production Manager
Stage Management |  |  | (L): Production Manager / CSM
Production show staff |  |  | (L): CSM
Approvers
Legal | (J): Legal Counsel | (J): Exec Director / Producer
Budget | (J): Legal Counsel | (J): Exec Director / Producer / Finance Manager
Creative and Production |  | (L): Artistic Director / Producer / Head of Prod
Technical |  | (J): Head of Prod | (J): Production Manager
Digital |  | (L): Comms Director / Producer
Health & Safety |  | (J): Head of Production | (J): Production Manager
Marketing and Community |  | (L): Comms Director / Producer