Traffic and Waste Management Update
13/02/2017

Attending:

Chris Clay
Jonathon Black

Melissa McVeigh

Apologies: Helen Thackeray

| POINT | ACTION |
| --- | --- |
| 1. Traffic Management |  |
| CC to meet bus companies weekly from now on CC to speak to Mike Johnson (BBC) about bus station design Park & Ride sites yet to be confirmed 4 suggested sites for Park & Ride: Walton Street / Saltend or ABP / The Old Council Depot or Army barracks (near Beverley) Interchange to be used for shuttle buses | CC CC |
| 2. Security |  |
| CC confirmed Showsec as security and stewarding company of choice CC to share contact details and MM to complete Addendum RC to confirm Showsec have signed Framework Agreement and NDA | CC / RC |
| 3. Procurement |  |
| RFQ – 3 x Waste Management responses received Biffa, Ryan’s Cleaning, East Riding Council RFQ – 3 x Medical responses received St. John’s, North East Medical, Event Medical Services RFQ - H&S due back 15/02/2017 MM / HT / CC to go through RFQs w/c 13th February | MM/HT/CC |
| 4. BBC visit |  |
| BBC agenda for w/c 20/02/2017 RC to invite HT/JB/MM to following meetings: MONDAY 20TH – onsite at Burton Constable. 11:00; O2 Mobile mast site visit. 11:30; KCOM site visit. 12:30; Ticketmaster site visit. 13:30; Proposed Showsec site visit. 14:30; Proposed Bars & Concession supplier site visit. 15:30; Venue meeting (can we move this from 14:00?). TBC; Production / Site contractor visits. TUESDAY 21ST – Venue TBC. 09:30 – 10:30; Traffic management (TBC). 10:30 – 12:00; Security & Stewarding / DPS & Alcohol Management. 13:00 – 14:30; SAG. | RC |
| 5. Volunteer Requirement |  |
| Volunteers required at: - Transport hubs (tbc) - Outside fence to do wayfinding at on-site bus station and marshalling bus queues Jack May (BBC) to speak to MM about volunteer requirements inside the fence. CC to share JM contact details with MM MM to discuss volunteer requirements with HJ/SC | CC MM |
| 6. Resident Liaison |  |
| Resident liaison – next Skirlaugh residents meeting tbc HT to attend | HT |