Larkin Exhibition
Fri 28th July 2016

Present: SW, PP, SH, HD 
Notes: SMHS

NOTES											ACTIONS

Guest Curator:
Grayson Perry & Alan Bennett have declined. 
- Live invites currently with Nick Cave, John Cooper Clark
- update on David Williams Conversation. 						GC
- HD has sent the request to Lenny Henry, but has heard nothing back.  			HD
- Speak to Rosie Millard and Sue Roberts at the BBC for their contacts.			HD

Mainstream names are needed for the Guest Curator – not academics. Could we look at Lyricists?
- Information to share the artists list that was put together for the exhibition. 		SW
- Conversation to be started with Mark Gatiss/Reece Shearsmith 			SH
- check with Martin Green re Tracy Thorn						HD

A named curator will be needed before a funding application is submitted.

BBC
Christine Hamell is to meet SW to discuss proposed documentary			SW
- Pat Connor/Helen Boaden to be contacted about the Larkin Archive at the BBC. 	HD

Plan B
Version of Larkin Exhibition project to be created by PLS; no guest curator; minimal wrap around activities;

Research										SW & PP & GC
Following areas of research, in relation to the archive collection to be initiated by PLS and SW, to indentify new ways of looking and new content:
- Larkin the Librarian
- Larkin the Poet
- Larkin’s Family
- Larkin & Jazz

Request for ‘top ten’ key items from the collection which have not been seen before in public.

Wrap Around Programme
For Ref, collation of activities which have been staged in the past 			SW & PP

Budget
Review of budget and development of both Plan A and Plan B budgets			SW & HD

Next Meetings

w/c 1 August			SW & PLS members to meet to work on Research

3 Aug				SW & HD to meet to work on Budgets

10 Aug				Simon Wilson to meet with James Trowsdale

17 Aug				12.30 – 2.30 - Larkin Exhibition Group Meeting