Milestone 1 – On signature of the contract – September 2016 (£31,000)

- Agreed budget update

- Initial marketing copy and image brief delivered to designers.

- Project Plan delivered

- Timeline document created

- Headline venue held

- Agreed budget

- Contributing artist update

- Ticket pricing structure agreed for pre activations and December weekend.

- On sale date agreed

Milestone 2 – January 2017 (£31,000)

- Agreed budget update

- Progress update against project plan

- At least two Tier 1 artists contracted for December.

- Headline Venue contracted.

- Defined plan presented to the steering group.

- Marketing and comms plan developed with Hull 2017 marketing team.

- Image and copy for confirmed Tier 1 artists.

Milestone 3 – June 2017 (£31,000)

- Agreed budget update

- Progress update against project plan

- All artists contracted

- Artist accommodation and travel booked.

- Initial tech and staffing scoped.

- Volunteer requirements confirmed.

- December weekend tickets on sale.

- Plan put forward for activity happening around December weekend with external promoters.

Milestone 4 - January 2017 (£9000)

- Evaluation

- Reconciled Budget, copies of contracts and proof of payments to artists, suppliers and any other contracted parties received by Hull2017.

- Successful delivery.

## Thursday, 19 May 2016

| 00:00 - 00:00 | Timeline (Steering Group Meeting in Hull.) Delegates: 0 Capacity: 0 | *Timeline |
| --- | --- | --- |

## Friday, 27 May 2016

| 00:00 - 00:00 | Timeline (Receive a detailed project budget) Delegates: 0 Capacity: 0 | *Timeline |
| --- | --- | --- |

## Monday, 15 August 2016

| 00:00 - 00:00 | Timeline (Full contract with timeline and budget attached) Delegates: 0 Capacity: 0 | *Timeline |
| --- | --- | --- |

## Wednesday, 31 August 2016

| 00:00 - 00:00 | Timeline (Commission initial articles in reference to the north and confirm project outline.) Delegates: 0 Capacity: 0 | *Timeline |
| --- | --- | --- |

## Thursday, 1 September 2016

| 00:00 - 00:00 | Timeline (Begin build of Discover section of 2017 website for Substance) Delegates: 0 Capacity: 0 | *Timeline |
| --- | --- | --- |

| 00:00 - 00:00 | Timeline (First payment released to Substance. After contract signed and agreed.) Delegates: 0 Capacity: 0 | *Timeline |
| --- | --- | --- |

| 00:00 - 00:00 | Timeline (Luke start contract contributors of online editorial, print editorial and editorial for other publications) Delegates: 0 Capacity: 0 | *Timeline |
| --- | --- | --- |

## Monday, 5 September 2016

| 00:00 - 00:00 | Timeline (Revisit budget after contracting content and curating events pre-2017 December weekend) Delegates: 0 Capacity: 0 | *Timeline |
| --- | --- | --- |

## Saturday, 1 October 2016

| 00:00 - 00:00 | Timeline (Pencil peripheral venues for December weekend) Delegates: 0 Capacity: 0 | *Timeline |
| --- | --- | --- |

## Tuesday, 1 November 2016

| 00:00 - 00:00 | Timeline (Lead image and copy created) Delegates: 0 Capacity: 0 | *Timeline |
| --- | --- | --- |

## Monday, 14 November 2016

| 00:00 - 00:00 | Event (Pre Activation Event: Hull) Delegates: 0 Capacity: 0 | Hull City Centre (HCC) |
| --- | --- | --- |

## Saturday, 21 January 2017

| 00:00 - 00:00 | Event (Pre Activation Event: Liverpool) Delegates: 0 Capacity: 0 | *FYI |
| --- | --- | --- |

## Wednesday, 1 February 2017

| 00:00 - 00:00 | Timeline (Confirm Content Outline: with rough idea of content over weekend.) Delegates: 0 Capacity: 0 | *Timeline |
| --- | --- | --- |

## Saturday, 1 April 2017

| 00:00 - 00:00 | Timeline (Contract all performers for the December weekend.) Delegates: 0 Capacity: 0 | *Timeline |
| --- | --- | --- |

| 00:00 - 00:00 | Timeline (Have all marketing material ready for full programme announcement) Delegates: 0 Capacity: 0 | *Timeline |
| --- | --- | --- |

## Saturday, 22 April 2017

| 00:00 - 00:00 | Event (Pre Activation Event: Manchester) Delegates: 0 Capacity: 0 | *FYI |
| --- | --- | --- |

## Friday, 30 June 2017

| 00:00 - 00:00 | Timeline (Release booklet with articles by artists working in the north.) Delegates: 0 Capacity: 0 | *Timeline |
| --- | --- | --- |

## Saturday, 22 July 2017

| 00:00 - 00:00 | Event (Pre Activation Event: Leeds) Delegates: 0 Capacity: 0 | *FYI |
| --- | --- | --- |

## Saturday, 2 September 2017

| 00:00 - 00:00 | Event (Pre Activation Event: Newcastle) Delegates: 0 Capacity: 0 | *FYI |
| --- | --- | --- |

## Saturday, 9 December 2017

| 00:00 - 00:00 | Timeline (Substance Festival Weekend: Hull (See Substance Festival Weekend arrangement for event detail)) Delegates: 0 Capacity: 0 | *Timeline |
| --- | --- | --- |

## Sunday, 10 December 2017

| 00:00 - 00:00 | Timeline (Substance Festival Weekend: Hull (See Substance Festival Weekend arrangement for event detail)) Delegates: 0 Capacity: 0 | *Timeline |
| --- | --- | --- |