## Sheet1
A HALL FOR HULL
|  | ORIGINAL BUDGET AGREED BY CONTRACT RIBA/H2017 | VARIATIONS TO ORIGINAL BUDGET (QUERY IF AGREED BY RIBA) | ACTUAL / ANTICIPATED SPEND | VARIANCE BETWEEN ORIGINAL AGREED BUDGET AND ACTUAL/ANTICIPATED SPEND | WHO HAS ACTUALLY PAID ? | HULL 2017 OR RIBA SEPARATE COST | NOTES
1 | VARIOUS COSTS
| Expressions of Interest Honoraria | 3850 |  | 3925 | -75 | RIBA |  | Noted as Design Fees on MBM spreadsheet
| Selection Panel Fees | 1200 |  | 1200 | 0 | RIBA
| Feasibility Design (Setworks) | 4700 |  | 4700 | 0 | RIBA |  | Noted as Suppliers Cost on MBM spreadsheet
| Planning Fees | 400 |  | 482 | -82 | RIBA
| Architect/Artist Travel | 8500 |  | 8854 | -354 | RIBA ? |  | Split into 2 sums of £5500 and £3000 on MBM spreadsheet
|  | 18650 |  | 19161 | -511
2 | ARTWORK APPLICATION
| Artwork application | 7000 |  | 8777.95 | -1777.95 | RIBA |  | Breakdown has been provided by Marie
3 | HULL 2017 ONSITE COSTS RE THE ARTWORK
| Portable lights for RIBA install | 0 | 0 | 111.15 | -111.15 | H2017 |  | Hull 2017 onsite costs re the artwork
| RIBA @ Trinity Square - Cbling - 1 week hire as per quote 17-0830.01 | 0 | 0 | 60 | -60 | H2017
| Scaffolding Tower for RIBA | 0 | 0 | 366.24 | -366.24 | H2017
| 4 visits to Trinity Square by an electrician for the A Hall for Hull exhibition | 0 | 0 | 388.4 | -388.4 | H2017
| Materials for Artwork installation HC | 0 | 0 | 313.48 | -313.48 | H2017
| Materials for Artwork installation AK | 0 | 0 | 80.46 | -80.46 | H2017
| Extra security due to lighting being switched off | 0 | 0 | 600 | -600 | H2017
|  | 0 | 0 | 1919.73 | -1919.73
4 | ADDITIONAL ONSITE COSTS
| Additional Barrier hire week 2 | 0 | 0 | 600 | -600 |  |  | We believe these onsite costs re the artwork incurred by Setworks
| Additional Tower hire week 2 | 0 | 0 | 190 | -190
| Materials, protection etc for painters | 0 | 0 | 590 | -590
|  | 0 | 0 | 1380 | -1380
5 | STEEL FABRICATION
| 192 no. 3mm bespoke perforated steel, punched |  | 18672 | 18672 |  | RIBA |  | RMIG
| 192 no. 3mm bespoke perforated steel, rolled and folded |  | 14976 | 14384 |  | RIBA |  | Barnshaw
| All other steel parts |  | 18138 | 18775.84 |  | RIBA |  | Kloeckner
|  | 50562 | 51786 | 51831.84 | -1269.84
6 | SETWORKS COSTS
| Airmatic (previously item 2.15?) |  | 12300 | 17400
| Rerolled sections (Barnshaws) |  | 0 | 750
| Transport from Barnshaws to Airmatic |  | 0 | 3815
| Transport from Airmatic to Wedge |  | 900 | 3180
| Transport from Airmatic to Barnshaws |  | 0 | 560
| Transport from Wedge to site |  | 900 | 5175
|  | 12000 | 14100 | 30880 | -18880 |  |  | We believe the additional amount of £2,100 in column D was agreed by RIBA with Setworks prior to going onsite
7 | FURTHER COSTS
| Plywood (96 sheets) | 0 | 900 | 900 | -900 | RIBA? |  | We believe this section was agreed by RIBA with Setworks prior to going on site
| Labour to CNC | 0 | 2800 | 2800 | -2800 | RIBA?
| Onsite build (4x 8 days) | 0 | 7500 | 12000 | -12000 | RIBA?
| Hire equipment cost | 0 | 3000 | 3000 | -3000 | RIBA?
| H+S barriers etc | 0 | 600 | 600 | -600 | RIBA?
|  | 0 | 14800 | 19300 | -19300
8 | CDM COSTS
| 2 days H+S overseeing Felice RAMS etc | 0 | 0 | 600 | -600 |  | H2017 | CDM costs agreed of £6,150 to be paid by Hull 2017
| 5 days H+S overseeing general | 0 | 0 | 1500 | -1500 |  | H2017
| 3 ½ nights site management | 0 | 0 | 1575 | -1575 |  | H2017
| 5 days additional site management | 0 | 0 | 1500 | -1500 |  | H2017
| Hotels associated with extra days | 0 | 0 | 375 | -375 |  | H2017
| 1 day retrospective paperwork for PD | 0 | 0 | 300 | -300 |  | H2017
| 1 day O+M collation and overview | 0 | 0 | 300 | -300 |  | H2017
|  | 0 | 0 | 6150 | -6150
9 | DECOMMISSIONING
| Deinstall Onsite build (4x 5 days) |  |  | 7500 |  | RIBA | RIBA
| Hire equipment cost |  |  | 3000 |  | RIBA | RIBA
| H+S barriers etc |  |  | 600 |  | RIBA | RIBA
|  |  |  | 0 |  | RIBA | RIBA
|  | 10500 | 0 | 11100 | -600 | RIBA | RIBA
10 | SECURITY | 12000 | 0 | 14925 | -2925 | H2017 | H2017
11 | MARKETING
| RIBA | 1500 |  |  | 1500 |  |  | RIBA to allocate actual/anticipated spend
| H2017 | 1500 |  | 2000 | -500 | H2017 | H2017
|  | 3000 | 0 | 2000 | 1000
12 | MISC | 288 | 0 | 101.1 | 186.9 | RIBA
13 | ADDITIONAL COSTS
| INSURANCE REQUIRED FROM 27.9.17 | 0 |  | 560 | -560 | H2017 | H2017
| Opening | 0 |  | 2931.7 | -2931.7 | H2017 | H2017
| Hoardings moving | 0 |  | 1780.48 | -1780.48 | H2017 | H2017
| Petty cash | 0 |  | 5 | -5 | H2017 | H2017
| Wine for Hall for Hull launch | 0 |  | 968 | -968 | H2017 | H2017
| Streetscene services (cleaning) | 0 |  | 331 | -331 | H2017 | H2017
|  | 0 | 0 | 6576.18 | -6576.18
| Total | 114000 |  | 174102.8 | -60102.8
| Specific RIBA costs |  |  |  |  | 27938.95
| Specific Hull 2017 costs |  |  |  |  | 31570.91