## Sheet1
The Last Ballad of Lillian Bilocca - Project Team Meetings
Template
Agenda Item
Creative / Artistic
Production
Venue
Project Management
- Roles & responsibilities
- Project Timeline
- Project Risk Register
- Scheduling
- Project documentation
Budget
Admin / Contracts

## 14.4.17
The Last Ballad of Lillian Bilocca - Project Team Meetings
14.4.17
Agenda Item | Notes | Actions
Creative / Artistic
Script due w/c 24 Apr
HD & SF call with BBC re digital wrap-around activity.
Space - committed their funds for this year.
Radio - Sue Roberts relationship. Can be recorded before, during or after.
TV - non-traditional TV doc films. 30 min. Film maker to be identified to come on journey. SF to speak to Carol Morely.
| SF & Adrian to identify delivery deadlines. Rehearsal skype to be enabled. | PV to chase
Production | Production team to be identified. SM team to be split between Hull & Manc. | PV to review lists with Tech & Ops
| Job descriptions for SM, operators & costume to be gathered. | LA to share Told by an Idiot ones & request from Liverpool.
| EMP, ESAG, RA & CDM processes to be establised & paperwork collated. | PV to liaise with CC
Venue | Swan St rehearsals in Manc. Holy Apostles in Hull. Wifi required. | MA to confirm/arrange
| HD made ask to the Guildhall. | LA to chase next week re receipt of email and date for meeting
| Unison building | HD, LA & PV to visit. MA to arrange
| Garage & buildings behind the Guildhall? | PV to investigate
| Test event for 200 volunteers to move around the space. Include those with access requirements 1 June? | PV & MA to investigate
Project Management
- Roles & responsibilities | Wider project team meetings to be in the diary fortnightly - Thurs @ 11am. First team meeting with Project Team & MarCommsDigi Thurs 5 May @ 11am. | MA to arrange.
| Marketing, learning & digital leads to be identified asap. Digital needs to be David due to wrap around activity. | HD/PB
| Organogram to be drafted | PV to draft production team. LA to add wider team.
| Volunteering & community company | HD to speak to Harriet
- Project Timeline | HD created gant chart. | HD/LA/MA to populate over the next 3 weeks.
- Project Risk Register
- Scheduling | Performance schedule to be on agenda for full MarComms meeting | LA to draft agenda. PV to bring break info
- Project documentation | Minutes from the last meeting to be circulated following notes from HD & PV | LA to circulate
Budget | Buyout details to be sent to Paul | HD to highlight buyout lines. LA to send
Admin / Contracts | Design dropbox in process. Transfer to sharepoint. Everything in shared folder except budgets & contracts. | LA/MA to discuss with JC and set up

## 04.05.17
The Last Ballad of Lillian Bilocca - Project Team Meetings
14.4.17
Agenda Item | Notes | Actions
Creative / Artistic
| Script delivered. Circulate internally & to creatives | LA to check with SF & circulate.
| The Unthanks performing at CSL Sun 1 Oct in Jubilee Church. | LA to add to the production summary.
| HD & SF spoke to BBC. Creative documentary discussed with Jonty. BBC have budget. Can have it's own life/.. MP to be creative lead. | SF & MP will talk to Jonty seperately.
Radio could be pursued later on.
| SF & Adrian to identify delivery deadlines. Rehearsal skype to be enabled. | LA to speak to Sarah about this. Does she have any further info.
| Share script with WH for legal review. | LA to send.
HD responded to Virginia re international travel.
| Lil the Play. Conversation with Paul Dennis. | HD speak to PB & then approach.
Production | Production team to be identified. SM team to be split between Hull & Manc. | HD to speak to PV
| Job descriptions for SM, operators & costume to be gathered. | HD to speak to PV. LA to save & MA re Leeds ones.
| EMP, ESAG, RA & CDM processes to be establised & paperwork collated. | Awaiting new production manager.
| New Production Manager required. HD AV checked Ben Pugh. Other suggestions from Chris? | HD & LA to speak to Chris tomorrow.
| LA shared notes from design meeting with SF for approval. LA to chase SF & resend by end of the week. | LA to do this.
Venue | Swan St rehearsals in Manc. Holy Apostles in Hull. Wifi required. | LA shared email with space. HD to check HT rate.
| Unison building | HD, LA & PV to visit. MA to chase on his return.
| Garage & buildings behind the Guildhall? | Awaiting production manager
| Test event for 200 volunteers to move around the space. Include those with access requirements 1 June? | LA & MA to pick up next week
| Cancel Martin for Mon & invite MA | LA to speak to Tare
| Meeting at Guildhall 8.5.17. Table - run down of rooms, map & routes, rehearsal schedule. Confirmation of booking, costs. | LA & HD to review rehearsal schedule tomorrow.
Project Management
- Roles & responsibilities | Kick off meeting identified | HD to speak to Phil.
| Organogram to be drafted | Awaiting Production Manager/
| Volunteering & community company Use Periplum as example | HD to speak to Harriet
- Project Timeline | HD created gant chart. | HD/LA/MA to populate over the next 3 weeks.
- Project Risk Register
- Scheduling | Performance schedule to be on agenda for full MarComms meeting | LA to draft agenda. PV to bring break info
- Project documentation
Budget | HD had another pass at budget. Buyout lines identified by HD in yellow.
Admin / Contracts | Design dropbox in process. Transfer to sharepoint. Everything in shared folder except budgets & contracts. | LA to chase JC
| Actor offer required. Deal memo & contracts to be drafted. Buyout to be outlined. | LA to chase WH re contracts.
| Dialect coach required. | HD to email SF.
| Sunday performances. HD checking with AM. His contract was agreed with defined performance days. | HD to chase.
| Max's agreement been returned? | LA chased WH
MISC | HD to email RET re rehearsal space, support from Michelle, Costume & Props. Do they have a super they can offer | HD to email MD.
| Insurance | HD to check with CC
| Silver Cod Trophy. Is this still required? | LA to check at some point.