## Sheet1
CURIOUS DIRECTIVE: FROGMAN PRODUCTION SCHEDULE |  | Version 1
Date & Time | Activity | Who | Notes
TBC | Internet Installation | KCOM | ADSL Connection being fitted ( David Watson is paying)
Monday 30th October
10:00-11:30 | Arrival and Load-in | Curious Directive/HPSS/TBC(drapes)
11:30-13:00 | Pipe and Drape Install | TBC
11:30-14:00 | Rig LX and begin Sound/AV Cable Lay | Curious Directive/HPSS
14:00-15:00 | Break | All
15:00-17:00 | Control Position Set-up | Curious Directive
Continue Cable Lay
Tuesday 31st October
10:00-13:00 | AV Set-up | Curious Directive
Sound Check
Ethernet internet connection check
13:00-14:00 | Break | All
14:00-17:00 | Focus LX | Curious Directive/HPSS
VR Set-up
Wednesday 1st November
10:00-11:00 | Final Checks | Curious Directive
11:00-12:00 | Cast Checks Tech | Curious Directive
12:00 | Break | All
13:00 | Set up | Curious Directive
14:00 | Doors | Danielle Harris
14:30 | Show 1 | Curious Directive
15:45 | End
19:00 | Doors | Danielle Harris
19:30 | Show 2 | Curious Directive
20:45 | End
Thursday 2nd November
14:00 | Doors | Danielle Harris
14:30 | Show 1 | Curious Directive
15:45 | End
19:00 | Doors | Danielle Harris
19:30 | Show 2 | Curious Directive
20:45 | End
Friday 3rd November
14:00 | Doors | Danielle Harris
14:30 | Show 1 | Curious Directive
15:45 | End
19:00 | Doors | Danielle Harris
19:30 | Show 2 | Curious Directive
20:45 | End
Saturday 4th November
14:00 | Doors | Danielle Harris
14:30 | Show 1 | Curious Directive
15:45 | End
19:00 | Doors | Danielle Harris
19:30 | Show 2 | Curious Directive
20:45 | End
Sunday 5th November
14:00 | Doors | Danielle Harris
14:30 | Show 1 | Curious Directive
15:45 | End
19:00 | Doors | Danielle Harris
19:30 | Show 2 | Curious Directive
20:45 | End
Monday 6th November - No Shows
Tuesday 7th November
14:00 | Doors | Danielle Harris
14:30 | Show 1 | Curious Directive
15:45 | End
19:00 | Doors | Danielle Harris
19:30 | Show 2 | Curious Directive
20:45 | End
Wednesday 8th November
14:00 | Doors | Danielle Harris
14:30 | Show 1 | Curious Directive
15:45 | End
19:00 | Doors | Danielle Harris
19:30 | Show 2 | Curious Directive
20:45 | End
Thursday 9th November
14:00 | Doors | Danielle Harris
14:30 | Show 1 | Curious Directive
15:45 | End
19:00 | Doors | Danielle Harris
19:30 | Show 2 | Curious Directive | BSL Performance
20:45 | End
Friday 10th November
14:00 | Doors | Danielle Harris
14:30 | Show 1 | Curious Directive
15:45 | End
19:00 | Doors | Danielle Harris
19:30 | Show 2 | Curious Directive
20:45 | End
Saturday 11th November
14:00 | Doors | Danielle Harris
14:30 | Show 1 | Curious Directive
15:45 | End
19:00 | Doors | Danielle Harris
19:30 | Show 2 | Curious Directive
20:45 | End