Hull Independent Producer Initiative (HIPI)

Timeline:

- 29 April: Finish JD.

- W/c 3 May: Meet to discuss JD and role.

- W/C 9 May: Send out to partners and companies.

- W/C 23 May, finalise JD and prepare application announcement and recruitment.

- W/c 11 July: Announce.

- W/c 1 August: Deadline Monday 1 August at 10am.

- W/c 8 August: Interviews.

- W/c 5 September: Post commences.

Measure of Success:

- Creating a stronger creative network, who communicate with each other regularly and understand how they can best achieve success.

- Enhance capacity of companies to write funding bids. Securing funding for 2017 projects and NPO where possible.

- Export Hull’s culture further, increasing the amount of work toured.

- Networking the sector.

- Capacity growing initiative that allows more companies and artists to live and work in Hull.

- Developing artistic aspirations of Middle Child, Silent Uproar, Ensemble 52, Apus Productions, Roaring Girls, She Productions, Pub Corner Poets, Bellow Theatre and Broccolily.

- Increasing the resource that the above companies have in orer to deliver their productions.