## Detailed Critial Path
Event Name: Where Do We Go From Here
Client: Hull City of Culture
Event Date: 1 Dec - 7 Jan
KEY
Milestones
Completed
Needs Immediate Action
Key Meetings | Start Date | End Date | Notes | Name / Responsibility
Internal Project Team Meetings | 2017-08-01 | 2018-01-31 | every 2 weeks, moving to every week in october | Haith
Creative Project Team Meetings (face to face) | 2017-08-01 | 2018-02-01 | every 2 weeks | Niccy/Sam/Jason Bruges
Artist Agency Conference call (weekly) | 2017-08-01 | 2018-01-31 | On going | Niccy
Artists Stakeholder Meetings | 2016-08-08 |  |  | Kirstine
Internal Debrief |  | 2018-01-20 | TBC in line with Board timelines | Haith
External Debrief |  | 2018-01-25 | TBC in line with Board timelines | Niccy
Wash up report meeting |  | 2017-01-31 | TBC in line with Board timelines | All
Art Commisioning
Creative kick off meeting with key internals. | 2017-08-15 |  | Complete
Identify artists for intrest to tender
Create deck for briefing and brief
Artist tender deadline
Contract Chosen Artists
Individual brief writing |  |  |  | NH/RC
Meeting Phase 1 to answer queries with each artist chosen |  |  | urban productions will be on the 5th sept.
Phase 2 and engagement with senior team
Wash up report meeting
Creative
Creative Kick off Project meeting |  |  |  | Niccy / Sam
Core team meeting |  |  |  | Niccy / Sam
Continuous stakeholder client liaison |  |  |  | Niccy / Sam
Present creative themes and core concepts to Board and stakeholders |  |  |  | Niccy / Sam
Review of creative themes and core concepts with wider teams (fortnightly meeting) |  |  |  | Niccy / Sam
Approval of scope on creative themes and core concepts |  |  |  | Niccy / Sam
3D scope of works briefed and commenced. (design) |  |  |  | Niccy / Sam
Sound design scope developed. |  |  |  | Niccy / Sam
Present technical production for approval |  |  |  | Niccy / Sam
H&S approve technical production and operational plans |  |  |  | Niccy / Sam
Stakeholder meetings (inclusive of media partners) |  |  |  | Niccy / Sam
written word first draft (narartive) |  |  |  | Niccy / Sam
Development Phase 1 |  |  |  | Niccy / Sam
Decvelopment Phase 2 |  |  |  | Niccy / Sam
wriitten word narrative sign off. |  |  |  | Niccy / Sam
Post-event reconciliation with boards for stakeholders. |  |  |  | Niccy / Sam
Finance Stages & Reconciliation
Contracts of artists and core team agreed & finalised | 2017-08-01 | 2017-09-01 | complete | Will / Jason
Budget approved | 2016-08-08 | 2017-09-01 | Complete | Tom /Niccy
Payment schedule agreed | 2016-09-01 |  |  | Nicc/ Tom
Artists Contract signed |  |  |  | Will / Jason
T&Cs and payment schedules agreed with suppliers and comunicated to Hull 2017 through a Roles and responsibilities document. |  | 2017-10-21 | ongoing | Jason Bruge team
Purchase orders sent to suppliers |  |  |  | Haith
Budget reconciled | 2018-01-12 | 2018-01-31
General Project
Approval of operational project scope |  |  |  | Chris Clay/Tom
Stakeholder management: Internal and external |  |  |  | Niccy
Programming, interpritation and design Concept and strategy development |  |  |  | Niccy / Sam
Operations management draft complted.
Marketing
Signage & branding requirements identified |  |  |  | Sarah
Design Development | 2017-11-01 | 2017-11-10 |  | Sarah
Design Sign Off | 2017-11-10 | 2017-11-10 |  | Sarah
Print companies identified |  |  |  | Sarah
Design approved |  |  |  | Sarah
Print company confirmed |  |  |  | Sarah
Stage 1: sign off process for all branding and signage |  |  |  | Sarah
All branding and signage sent to print |  |  |  | Sarah
Print adjustments as required | 2017-11-27 | 2017-11-30 |  | Sarah
Branding & signage delivered to site for install |  |  |  | Sarah
Cross check signage is in correct location |  |  |  | Sarah
Light Boxes Instalation | 2017-11-28 | 2017-11-29 |  | Sarah
Leaflet Delivery | 2017-12-01 | 2017-12-01 |  | Sarah
Technical Design - infustructure
Site plans developed |  |  |  | Chris / Jason Bruges Team
Structural licensing and planning if required |  |  |  | Chris / Jason Bruges Team
Site plans issued to key stakeholders |  |  |  | Chris / Jason Bruges Team
Site plans revised and reissued as required |  |  |  | Chris / Jason Bruges Team
Final site plans submitted to key stakeholders and departments. |  |  |  | Chris / Jason Bruges Team
Jason Bruges Production Team Arrive onsite | 2017-11-12 | 2017-11-12 |  | Jason Bruges Team
Robots delivered to Staples Building | 2017-11-13 | 2017-11-13 |  | Jason Bruges Team
Installation begins at Beverley Gate | 2017-11-14 | 2017-11-14 |  | Jason Bruges Team
Installation begins at Museum Gardens | 2017-11-15 | 2017-11-15 |  | Jason Bruges Team
Installation begins at Trinity Square | 2017-11-16 | 2017-11-16 |  | Jason Bruges Team
Installation ends at Beverley Gate | 2017-11-28 | 2017-11-28 |  | Jason Bruges Team
Installation begins at Museum Gardens | 2017-11-28 | 2017-11-28 |  | Jason Bruges Team
Installation begins at Trinity Square | 2017-11-28 | 2017-11-28 |  | Jason Bruges Team
De-rig begins | 2018-01-08 | 2018-01-08 |  | Jason Bruges Team
De-rig ends | 2018-01-12 | 2018-01-12 |  | Jason Bruges Team
Event Capture (Videographer & Photographer)
Engage and contract content capture team |  |  |  | Digital Team
Develop strategy & brief |  |  |  | Digital Team
Delivery of assets from capture team |  |  |  | Digital Team
Complete the post-event internal reporting documents, inclusive of upload of images etc. |  |  |  | Digital Team
Edit and upload to social media where applicable |  |  |  | Digital Team
Accreditation
Passes produced for core Production Team | 2017-11-10 | 2017-11-10 |  | Laura / Melissa
Passes distributed to core Production Team | 2017-11-13 | 2017-11-13 |  | Laura
Press
Press Release - Installation Commencement | 2017-11-13 | 2017-11-13 |  | Ben
Jason Brugges Live Interview | 2017-11-30 | 2017-11-30 |  | Ben
Press Night Invites Sent | 2017-11-24 | 2017-11-24 |  | Ben/Anna Meyer / Corner Shop
Press Night | 2017-11-30 | 2017-11-30 |  | Ben/Niccy/Haith/Laura
Volunteers
Volunteer Request Submitted | 2017-11-13 | 2017-11-13 |  | Haith
Volunteer Briefing Pack Prepared | 2017-11-23 | 2017-11-24 |  | Haith
Lead Volunteer Training | 2017-11-29 | 2017-11-29 |  | Haith
Daily Volunteer Shifts | 2017-11-30 | 2018-01-07 |  | Haith/Laura

## Operations Project Critical Pat
Event Name: Made in Hull
Client: Hull City of Culture
Event Date: 1st January - 15th January
Project Code:
Revision
Current week commencing
KEY
Milestones |  |  | No. of Months | 5 |  |  | 4 |  |  |  | 3 |  |  |  |  | 2 |  |  |  | 1 |  |  |  | 0
Completed |  |  | Month | August |  |  | September |  |  |  | October |  |  |  |  | November |  |  |  | December |  |  |  | January
Needs Immediate Action |  |  | Weeks before Parade
|  |  | Days | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m
Dates
|  | Notes | Name / Responsibility
Key Meetings | Internal Project Team Meetings
Creative Project Team Meetings (face to face)
SAG Meetings
Production agency Conference call (weekly)
Artists Stakeholder Meetings
Internal Debrief
External Debrief
Wash up report meeting
Licensing, Approval & Permissions | Licensing, Approval & Permissions processes commences
Premises License submitted
Newspaper advertising of licence application
Premises notice notice of application (28 consecutive days starting from the day after the day the application is made)
Licensing, Approval & Permissions Secured
No Objection from stakeholders
Temporary Traffic Order
Acoustic consultant - pre event background assessment
Acoustic consultant - on the day monitoring and reporting
Resident Mitigation plan developed
Financials /Contracting - Client | Phase 1 budget prepared
Phase 1 Budget approved
Phase 2 budget prepared
Phase 2 budget approved
Phase 3 budget prepared
Phase 3 budget approved
Budget revisions & updates (weekly)
Payment Schedule/ Cancellation Terms
Project Revenue Target met
Reconciliation & Final Invoicing
Audit File
Drawings/ Plans/ Designs | Site layout / plans amends / updates
Plans issued
Traffic Management | Appoint traffic management company
Traffic Management Planning
Road signage plan produced
Traffic Management Stewarding plan produced
Contingency planning
Health & Safety | Event Safety Plan as part of ESMP
Contingency planning as part of ESMP
Risk assessments produced alongside the ESMP
SAG and Table top exercises
First Aid planning produced
Risk & issue management / risk register development
Crowd Management | Pedestrian Signage Plan produced
Crowd Management Planning as part of ESMP process
Crowd Management Stewarding Plan produced as part of ESMP process
Command and Control panel meetings
Emergency procedures developed
Table Top exercises
Stewarding & Security | Agreement of crowd and traffic management steward resourcing and allocation plans
Site Security planning
Site Security plan produced
Contingency planning
Table top exercises
Steward and security logistical plan agreed
Media Management | Discuss media requirements
Develop accreditation plan
Venue Management | Investigate ELT position
Technical Production | Production Schedule
PA System - Specification produced
Video / Projection Mapping - Specification produced
Site Management | Site Production Schedule
Fencing (including CCB Barrier)
Toilets - Specification produced
Power - Specification produced
Cable management
Trackway
Cabins & Steel Stores
Viewing platforms
Production Compound / Accreditation Compound - Specification
Signage Planning | CM Signage Plans compiled
CM Signage Plan authorised/signed off
CM Art work to graphics company
Health & Safety / CMP Signage produced
CM Signage installed
TM Signage plans compiled
TM Signage plans authorised/sign-off
TM Signage produced
TM Signage Installed
Financials/Contracting - Suppliers | Supplier Terms & Conditions
Supplier Payment Schedule
POs
Hull City of culture and Ground Control Operations | Insurance
Noise Management
ELT Specification
Submit Production Plans to Local Authorities
Radio Communications Plan produced
Onsite IT Requirements/ Scoping Doc
Onsite Financial Requirements
Onsite Equipment Requirements
Project Overview
Onsite Schedule & Key Docs
Job Close Processes
Crew and project team logistics | Accommodation
Travel
Refreshments
Accreditation - different levels and production agreed
Crew and performer Welfare
Crew Handbook
Legal Requirements | Identify legal requirements e.g. planning permission/ licenses
Obtain appropriate permissions/ licenses
Data sharing agreement
Sustainability | Identify project team champion
Stakeholder Register
Communication Plan with stakeholders
Sustainability Management Tracker
Event Impact Assessment

## Stakeholder Meeting Dates
Event Name: Made in Hull
Client: Hull City of Culture | [8 empty] | Current week commencing
Event Date: 1st January - 15th January |  |  |  | Current week commencing |  |  |  |  | `
Project Code:
Revision |  |  | No. of Months | 5 |  |  | 4 |  |  |  | 3 |  |  |  |  | 2 |  |  |  | 1 |  |  |  | 0
|  |  | Month | August |  |  | September |  |  |  | October |  |  |  |  | November |  |  |  | December |  |  |  | January
Weeks before Happening
|  |  | Days | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m
Dates
Key Dates & Trigger Points |  | Notes | Name / Responsibility
Sean holiday and away times | 21st August to the 5th September
6th - 12th October
Chris Holiday | 25th Sept to the 3rd October
Ala holiday | 24th August to the 4th September
5th October 12th October (out of the country)
22nd October to the 30th October (can only work from London)
Niccy | 24th August
Bank Holidays | Christmas
Boxing Day
Bank Holidays
Other relevant dates | Local Authority elections
Possible Dates - Scenarios
Core Group Milestones | First meeting of core group to consider options dates, routes and format of live parade. Discuss possible dates.
Second core stakeholder group meeting (SAG)
Full authority and stakeholder meeting to review key planning documentation regarding format and placemnet
Full authority and stakeholder meeting to review dates, route and format.
Stakeholder (SAG) meeting to update on placement, Live event, finalise command and control structure, review resident mitigation plan etc.
Meetings of sub groups to discuss and agree specific aspects of the parade e.g. – emergency service liaison, publicity, traffic measures, command and control etc.
Final full authority and stakeholder meeting if required.

## Community Engagement Plan
Event Name: Made in Hull
Client: Hull City of Culture
Event Date: 1st January - 15th January
Project Code:
Revision
Current week commencing
|  |  | No. of Months | 5 |  |  | 4 |  |  |  | 3 |  |  |  |  | 2 |  |  |  | 1 |  |  |  | 0
|  |  | Month | August |  |  | September |  |  |  | October |  |  |  |  | November |  |  |  | December |  |  |  | January
|  |  | Weeks before Parade | 14
|  |  | Days | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m
|  |  | Dates | 3rd
Key Dates & Trigger Points |  | Notes | Name / Responsibility
Bank Holidays | Christmas
Boxing Day
Bank Holidays
Other relevant dates | Local Authority elections
Possible Parade Dates - Scenarios
Community Engagement Comms Plan | Agree Locations can take place
Detailed assesement and understanding of impacts
Agree advice and information / develop and finalise factsheet
Submit TMO / Premises Licence
Inform PR & Media?
Community & stakeholder engagement - ongoing comms
Community & stakeholder engagement - letter & map highlighting route / closures / estimated timings
Hull website live with copy & map highlighting route / closures / estimated timings
BHF website live copy & map highlighting route / closures / estimated timings
Day Activity.
Online comms messaging
Hotline for residents to call?