## Sheet1
Item | Supplier | Cost ex vat | option costs | Sub Totals Ex VAT | Description | Notes | Where we're at | More notes 03/04 | Telephone | email | Order wording | Order cost exVAT | Insurance values
MACNAS
Prep/build space
Heating | TGPS | 200 |  |  | 2 x infra red heaters for office | bringing Monday 16th October
bins | b&q | 101.97 |  |  | Get from b&q |  | bought 07/11 CC
.
Furniture | All occasions | 601.25 |  |  | 120 x chairs, 10 stools & 20 x trestles |  | ordered 27/10
catering furniture | All occasions | inc above |  |  | 50 x chairs, 7 x restles & 6 x 6' rounds |  | ordered 27/10
distro | IDE | 415.5 |  |  | 13A extensions etc | or maybe more | ordered 26/10
catering | Gig-a-bite | 3932 |  |  | crew catering |  | maddie ordered
partitions for dressing room spaces | HPSS | 271.5 |  |  | pipe & drape |  | ordered 05/11 | invoice received 24/11
Ladders | HPSS | 30 |  |  |  |  | ordered 05/11 | invoice received 24/11
Additional toilets | Add Plant | 400 |  |  | 8 x single plastics |  | ordered 09/11
delivery & collection | Add Plant | 125 |  |  |  |  | ordered 09/11
Sub-Total |  |  |  | 6077.22
Performance
Get-in crew | TMC | 988.8 |  |  | 8 crew from 1000-1800 |  | ordered 27/10
Get-out crew | TMC | 988.8 |  |  | 8 crew from 1800-0200 |  | ordered 27/10
fencing crew | TMC | 370.8 |  |  | 2 crew Friday night to build savile street 1900-2200. 2 crew saturday to build & break fencing 1300-2000 |  | ordered 27/10
show crew | TGE | 200 |  |  | 1 x tele driver for Friday from 9am | Danny
show crew | TMC | 430.54 |  |  | 2 x telehandler drivers 1000-2100 | 1 needs to be 17m ticketed | ordered 27/10
catering buy out | TMC | 120 |  |  |  |  | ordered 27/10
Site managers | TGE | 400 |  |  | 2 site managers | co-op, C4DI
travel | TGE | 120 |  |  | Danny & Murphy return
Event Controller | TGE | 350 |  |  | Tim for Saturday only
TM | Centurion | 2920 |  |  | as required |  | ordered 06/10
additional TM | Centurion | 1150 |  |  |  |  | ordered 10/11
C4DI Plant | Add plant | 990.5 |  |  | 2 x 17m telehandlers | with fork extensions | ordered 27/10
Lowgate plant | Add plant | 217.5 |  |  | 5 or 7m telehandler |  | ordered 27/10
delivery | Add plant | 550 |  |  | delivered Fri, collected Mon |  | ordered 27/10
barriers | Event solutions | 1354.5 |  |  | ped & Heras, as required |  | ordered 27/10
Toilets | Add Plant | 660 |  |  | 10 x singles and 2 accessible | dropped at different sites | ordered 31/10
Delivery | Add Plant | 240 |  |  | dropped at 4pm, collected at 9pm |  | ordered 31/10
Comms | 900 communications | 411.25 |  |  | 35 x radios, 30 x noise cancelling headsets & 20 x surveillance mic kits | to supplement council radios | ordered 27/10
additional comms | 900 communications | 355 |  |  | additional 30 + 10 n/c & 10 surv |  | ordered 02/11
missing headset | 900 communications | 25 |  |  | 1 x missing headset
delivery collection | 900 communications | 70 |  |  | delivered Thursday 9th | collected Monday 13th | ordered 27/10
scissor lift | AFI | 340 |  |  | 14m scissor lift | For photographer | ordered 27/10
fuel | AFI | 68.4 |  |  | fuel used
MEWP op | TMC | 85
tower lights | Nixon extra | 270 |  |  | 2 tower lights | For wellington street | ordered 25/10
fuel | Nixon extra | 28.08
delivery | Nixon extra | 200 |  |  | delivered Fri, collected Mon | to save weekend costs | ordered 25/10
Extinguishers | TGE | 50
Sub-Total |  |  |  | 13954.17
AND NOW
crew | TMC | 692.16 |  |  | 2 x crew for in & out |  | ordered 27/10
Crane hire | Central cranes | 4140 |  |  | overnight on 3rd & 12th | Contract lift | ordered 27/10
scaff | B&A | 3140 |  |  | edge protection & crate base for Co-op & Hudgells |  | ordered 27/10
scaff | B&A | FOC |  |  | 2 x 6m aluminium scaff tubes for crates at C4DI |  | confirmed 27/10
ratchet straps | ratchetstrapsuk | 101.79 |  |  |  |  | ordered 27/10
bits | various | 0 |  |  | 54mm hole saw & 4 x U-bolts to attach scaff to crates | plus additional timber to make crates good | request from Mandy 14/10
Security | Prestige | 425 |  |  | 2 x SIA for overnight in & out |  | ordered 10/10
plant | Add plant | 225 |  |  | 7m telehandler | to move crates | ordered 27/10
Fencing | Event solutions | 675 |  |  | barriers for in & out |  | ordered 27/10
Work light |  | 0 |  |  | Use Aidens battery floods
Traffic management | Centurion | 1150 |  |  |  |  | ordered 06/10
additional TM | Dynniq | 0 | 500 |  | no longer required | Centurion have asked the council if the can do it | asked Paul & Graham about cost/invoicing
comms | council | 0 |  |  | 6 x radios
Transport | Beverley tool & trailer hire | 210 |  |  | 16' x 6.5' trailer to move crates. Collect on 2nd/return on 13th | need £100 deposit as well | booked 01/11
general lighting | Maplins | 27.49 |  |  | 4 x floods | 2 for each box
Battery | Halfords | 82.5 |  |  | for co-op roof |  | bought 07/11
Additional Battery | Halfords | 82.5 |  |  | for co-op roof |  | bought 09/11
Sub-Total |  |  |  | 10094.28
Handling fee | TGPS | 1549.1415 |  |  | 5% of all hires
TOTALS Ex Contingency, Ex VAT |  | 32531.9715
Contingency |  | -366.6115 |  |  | 5% of costs
AUTHORISED SPEND |  | 33820.7
NEW AUTHORISED SPEND |  | 32165.36 | Katy took £1655.34 back on 07/11