## Sheet1
Blast Theory
|  | 2016-03-01 |  |  |  | 2016-04-01 |  |  |  | 2016-05-01 |  |  |  | 2016-06-01 |  |  |  | 2016-07-01 |  |  |  | 2016-08-01 |  |  |  | 2016-09-01 |  |  |  | 2016-10-01 |  |  |  | 2016-11-01 |  |  |  | 2016-12-01 |  |  |  | 2017-01-01 |  |  |  | 2017-02-01 |  |  |  | 2017-03-01 |  |  |  | 2017-04-01 |  |  |  | 2017-05-01 |  |  |  | 2017-06-01 |  |  |  | 2017-07-01 |  |  |  | 2017-08-01 |  |  |  | 2017-09-01 |  |  |  | 2017-10-01 |  |  |  | 2017-11-01 |  |  |  | 2017-12-01 |  |  |  | 2018-01-01 |  |  |  | 2018-02-01 |  |  |  | 2018-03-01 |  |  |  | 2018-04-01 |  |  |  | 2018-05-01 |  |  |  | 2018-06-01 |  |  |  | 2018-07-01
Actvity | Lead | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Phase 1 - Research (June – Dec 2016)
Recruiting extended team for project management and community engagement
Recruiting core film production team inc. director and production designer
Development of relationships with University of Hull and independent researchers
Kick-off with technical partners and developers
Functional specification for the interactive platform for phone boxes
First development sprint and technical demonstrator for interactive platform
Partner development with schools, community and youth groups for workshops
Workshop preparation including scenario development with researchers
4 x Workshops with invited researchers and community groups
Schools Workshops begin - twenty students from diverse locations in each city
Young People’s Exchange -five young people from each city to travel to the other.
Over 60s Interviews -work with over 60s groups to delve into the recent past of each city
Digital strategy and audience engagement plan
Identity and visual design for the project
Editing and publishing videos and material from workshops
Design of new city map and skyline
Launch of project website
Phase 2: Film and Interactive Development (Jan – Mar 2017)
Recruiting of extended film production team
Resource planning for film shoot
Creative and script development for films with scriptwriter and storyboard artist
Script development for interactive platform and face to face encounter s
Visual and production design for film including sets, costumes and props
Virtual asset development for post-production
Location scouting and documentation
Casting and community call out for participation in film production
Production planning for shoot
Call out for members of the public to suggest and photograph potential locations for the films.
Site visit 1 to Hull to scout locations cast and rehearse with key cast members, plan for camera tracking and effects compositing and to shoot test material.
Site visit 2 to Hull to scout locations cast and rehearse with key cast members, plan for camera tracking and effects compositing and to shoot test material.
Production planning for face to face encounters
Production planning and location scouting for community screenings
Second development sprint for interactive platform
Interactive platform demonstrator with smartphone app and phone box integration
Publishing production designs and location photos via social media and website
Editing and publishing videos from casting via social media and website
Phase 3: Filming and Final Production (Apr – Aug 2017)
Planning for launch and public event
Delivery of final storyboard and script for films and interactive platform
Liaison with community cast and at locations during shooting
5 x 5 day shoots on location around Hull
5 x 15 days editing, sound and colour
5 x 15 days effects including 3d compositing, camera tracking
Build and scheduling for projection platform
Production, schedule and recruiting for face to face encounters
Final development and testing for interactive platform and app
Final platform demonstrator
Publishing production blog and stills via social media and website
Production of stills and video for press
Pre-launch publicity campaign
Phase 4 – Public Event and Finale ( Sept - Dec 2017)
Oversight of launch and planning for Finale
Film 1 Released
Film 2 Released
Film 3 Released
Film 4 Released
Film 5 Released
20 days of 1-to-1 interactions via electric vehicles
Community screenings
Monitoring and maintenance of the interactive platform
Press launch event
Social media campaign
Filming and photography for documentation
Publishing videos from face to face encounters on YouTube and website
Finale Event
Phase 5 – Legacy ( Dec 2017 onwards)
Editing videos from face to face encounters and documentation
Compiling participants’ contributions and data from the interactive platform