Volunteer Meeting 28.06.17

Attending: Sara, Lily, Haley, Maxine, Harriett

Ferens currently have:

- 450 core Volunteers (but not all sign up – nearer 200/250 are active)

- 7 volunteers per day (Ideal number, not critical)

- Volunteers are a bonus to their paid staff who are already in the galleries

Turner Prize:

- If critical of numbers, we need to compromise on the depth of knowledge

- Agreed on 12 critical, 16 ideal for most shifts but increasing for opening week, possibly weekends and half term etc.

- Each volunteer has to commit to a minimum of 6 shifts

Turner Prize Volunteer training:

- Ferens training if they haven’t already had it – This can be cut down from 2 ½ hours with Jane to ½ hour with Maxine as they don’t need all the artwork training and only need the building safety training.

- Late August – more intense training session on the artworks and artists (same session as above?)

- Homework?

- Late Sept – Orientation – tour by the curators through the gallery

- Sunday 24th (3pm TBC) – Volunteer preview

- Training brochure – each artwork, photograph and information

Risk Management:

- Train Turner Ambassadors or Leader Volunteers – at least one on shift per day. Gives them a responsibility and a specific job. Can help manage the volunteers and support the TP Supervisors

- Badge rewards system? – different colours for the number of shifts or phrases i.e. ‘I am a Turner Prize Expert’ – badges are £900 for 3000

- All volunteers are Police Checked so fine to invigilate Explore Art – Leader Volunteers are DBS checked

- Alison Walker is the HCAL safeguarding officer