Journey for Ballad:

- Audience of 200-250 is in the budget. But 250 will be the maximum limit on it, but we can try and look at 200 initially.

- Recreate the pram race outside, Big Lil will open the doors of the entrance and take people upstairs to the ballroom.

- The band will be in ballroom and connecting door.

  - A fight happens, along with introductions and some choreography.

- The group are then split into 2 groups. Group A taken down corridor to Council Chamber.

  - A working kitchen from Hessle Road will be created and in the room.

  - Want to use headphones in the room, using the microphones present in there already.

  - 10 mins installation and soundscape will take place in the room.

  - Want to make it as lowly lit as possible in the Council Chamber with candles/or gas lights.

  - Should be just enough room for 100 to sit in there but need to check this.

- Audience come out of Council Chamber and down a different corridor/route.

- Committee Room is the next stop. We saw one but were told there were others.

  - Recreate Victoria Hall where the women met each other. Room doesn’t need to be anything other than sitting and standing.

- Head off to the Banqueting Room. Band are there already. Last room of the evening. Try to avoid a big change by just turning the band round.

  - Potentially in the link between rooms.

- Second group head to the Committee Room.

  - They do the journey in reverse.

- 10 mins in each room except for Banqueting Room being 20-25 mins.

- Using both corridors.

  - One themed with ship and sea and one with sea shore.

  - There’ll be images, sound, etc in each corridor. For example a door is open that you walk past, dressed that you just catch a glimpse of. Doesn’t need to dress the whole room but what we can get away with.

- We need to put a plan together of swiftly moving more than 100 people.

- Community ensemble will be mainly men but might have a few women

- In the Ball Room a dinner dance will be created.

  - 3 day millionaires will disrupt this.

  - Big Lil will instigate each journey, helped by volunteer guides.

  - Ensemble will also create some moments in the corridor.

  - 2 actors will welcome people back into the space – was this every space or the last room?

- At the end Big Lil’s song is sung.

- Leave the building by the back door for a different sensation.

Things to think about:

- Volunteer training.

- Access when we have a route.

- Trying to keep it all on one level.

- Find committee Room we can hold 150 in.

- Writing week happening in 3rd week of Feb.