WOW Hull

21st November 2017

Mercure Hotel Edwardian Suite

6pm – 8pm

Arrangements

Room Set Up

- Tables set in a cabaret style arrangement

- A small stage/raised area for Jude, Kate, and our circle of friends Tish, Suzanne, Burnsy TBC.

- Badges, paper and pens/pencils on each table for attendee

- Drinks Area/Refreshments area

- A means to display our trailblazer boards.

- 4 Pop Up Screens to be displayed, in foyer and in the room.

- Copies of Revolutionary Makers Info - to take away

Technical

- 3 wireless Mics for introductions and circle of friends. (costs?)

- Projector

- Projectors Screen and link to PA or speakers

- I-pads for signing into WOW and email addresses.

Digital

- Power Point of the evening, including trailblazers, dates, website etc. and embed Hull 2017 launch films.

- Southbank Centre to supply new WOW film in advance.

- Means to display / type live the WOW Hull Manifesto of the evening

Access

- BSL interpreter – Amy Tomlinson

WOW HULL Team

Henrietta Duckworth		Exec Producer

Lindsey Hammond		Producer

Siana Mae Heppell Secker	Team Assistant

Jenny Hutt			Event Manager

Aidan Lesser			Production Manager

Madeleine O’Reilly		Programmer

Hull 2017 Volunteers  x 6 – called for 4.30 – 8.30pm

Schedule for the Evening

16:00		Room setup and technical checks,

16:30		2017 Volunteers arrive

17:30	 	Doors open, sign in with Ipads, refreshments served.

EVENT START

18:00             	EVENT START

Henri’s introduction – to the evening and housekeeping.

18:05	Henri introduces 
Kate Fox – Poem and her poetry challenge for the evening.

18:10	Rosie Millard introduces 
Jude Kelly, founder of WOW, Artistic Director, Southbank Centre, London

Jude Kelly speaks about WOW, the origins of the festival and how the

movement has grown.
 	WOW Film - new film to be shown (7m21s)

[18:20		Either Jude leads introduction session of all attendees

Make a call on the day depending on numbers

3 Roving mics available.

OR

Extend time Jude Introduction (+5mins)  and  for Panel (+10mins)]

18:35		WOW Hull Panel
		Jude leads conversation with guests

Expectations for WOW Hull, Why it’s important to do

Suzanne Clisby (The State of Girls Rights in the UK – Senior Lecturer,  Gender    		Studies, University of Hull)

Tish Lamb (the Women’s Equality Party – Manager, Cornerhouse Hull)

Burnsy (Equality in local media and awareness – BBC Radio Humberside)

Melanie Eusebe (Intersectionality & Diversity – Southbank Centre, WOW  Team)

Bea Campbell (Writer and Activist)

18:55	Henri introduces Ian Read to launch the artist & participant out for Revolutionary Maker’s craft project.

19:00	Thinkin Section.  Henri introduces Madeleine O’Reilly, Programmer for WOW-Hull, Artistic Director, Assemble Fest.
Maddie starts session: 
Introductions around the table – your name and why you’ve come tonight?

19:05 		Exercise from previous Hull Thinkins.

Amongst your table, discuss and write down times when you’ve experienced gender inequality and times where you experienced gender equality?

19:10 		Feedback around the room.

19:20		Jude and Maddie introduce the WOW HULL Manifesto which starts the plans   		for a future global WOW Manifesto.

WOW HULL Manifesto to be created in session; to inform festival; to be updated and adopted at WOW Hull in March 2017.

For example:
Pledges

- We would like to see more women in positions of political power -locally – regionally – nationally.

- We want to see the women’s football matches and rugby matches screened in local pubs on Saturdays alongside the men’s matches.

- We want to tackle low level sexism in workplaces/schools.

Actions

- We will launch the Hull branch of the Women’s Equality Party at the WOW Hull festival in March.

- Finding media companies to film matches and talk to pubs about finding ways of screening women’s matches (following model BBC Olympics coverage)

- We’ll create misogyny swear boxes all proceeds going to domestic violence charities.

19:35               	Feedback around the room from the tables. 
 		To manage the room, and ensure everyone is involved, we ask people their 		top 3 ideas for pledges/actions for the WOW HULL Manifesto.

19:50 		Kate Fox performs another freshly written poem inspired by the evening.

19:55           	Henri wraps up.     	
Thank you to attendees, Jude, Kate and circle of friends

Next Key Dates - Tickets on Sale in January - Festival Dates March

Revolutionary Craft project sign up.

Send info on IWD projects
News of forthcoming events

Keep sharing views #wowhull

You can always contact us on wow@hull2017.co.uk

20:00 		EVENT END