## Top Level Budget
Hull Comedy Festival Student Night 26 September |  |  |  | PO Number | Code
Production | Budget | Actual
Projection/LX/PA | 4501 | 4501 |  | 201705205
Room Dressing
Comedy Festival Banners | 1570 | 1570 |  | 201705158 | ZK109.K138.C175
Giant Letter | 250 | 250 |  | CC | ZK201 K304
Table Centrepieces | 432 | 432 |  | 201705288 | ZK201 K304
Design | 80 | 80 |  | PO'd
Gobos | 147.2 | 147 |  | CC
Tables x 14 | 113 | 77 |  | 201706098 | ZK106.K245.C175
Table Cloths | 72 | 72 |  | CC
Pens | 50 | 36 |  | CC
Lights | 60 | 49 |  | CC
Marketing
Invite | 200 | 118 |  | Coded elsewhere | ZK204 k334
Posters | 200 | 0
EDM
Design of student invite | 200 | 120 |  | Coded elsewhere | ZK204 K334
Design for floor vinyls |  | 120 |  | 201705026 | ZK204 K334
Design of 6 table centre pieces |  | 150 |  | 201705289 | ZK201 K304
Vinyls install and print |  | 1326 |  | 201705280 | ZK204 K334
Removal of student highlight vinyls |  | 75 |  | 201705366 | ZK204 K334
Design and print of student highlights (3000) |  | 911 |  | 201706031 | ZK204 K334
Delivery of giant deckchairs to Hull Uni |  | 40 |  | 201706054 | ZK204 K334
Delivery of deckchairs to City Hall |  | 100 |  | 201705334 | ZK201 K304
Photography/Filming | 1000 |  |  | Coded elsewhere
Performance
Comedians | 13000 | 13000 |  | 201705283 | ZK104.K232.C175
Rider | 150 | 50
BSL | 500 | 0 |  | Not required
Operations
Event Manager | 150 | 150 | Danielle | PO'd
Venue Hire | 1830 | 1830 |  | 201706098 | ZK106.K245.C175
First Aid | 102 | 51 |  | 201706098 | ZK106.K245.C175
Venue Staff |  |  |  |  | ZK106.K245.C175
Venue Security | 125 | 225 |  | 201706098 | ZK106.K245.C175
Buses | 800 | 800 |  | Coded elsewhere | ZK204 K115
Press Drinks | 200 | 0 |  | Not used
Total | 25732.2 | 26280
Budget | 26000 | 26001
Remaining | 267.8 | -279
ZK106.K245.C175 | 21838
ZK204 K115 | 4442
26280

## Timeline
Date | Activity
2017-08-28
2017-08-29 | Confirmed Line Up
Marketing Material designed
Site dressing designed
2017-08-30 | Off the Kerb contracted
2017-08-31
2017-09-01 | Feedback on marketing material designed and site dressing materials
2017-09-02
2017-09-03
2017-09-04 | Receive Final Marketing designs
2017-09-05 | Send marketing to print
2017-09-06
2017-09-07
2017-09-08 | Receive Marketing Materials
All production confirmed
2017-09-09
2017-09-10
2017-09-11 | Deliver marketing to university
2017-09-12
2017-09-13
2017-09-14
2017-09-15
2017-09-16
2017-09-17
2017-09-18 | Hull Comedy Festival Miniguide to print
2017-09-19
2017-09-20
2017-09-21
2017-09-22
2017-09-23
2017-09-24
2017-09-25 | Delivery of site dressing
Receive Hull Comedy Festival mini guide
2017-09-26 | Comedy Festival Launch and Student Comedy Festival