## Sam Lee
PRS Residencies - sesssion schedule
SAM LEE
Sam Lee visits | dates |  | no days
| 14 & 15 Nov 2016 |  | 2
| Thurs 2 & Fri 3 Feb |  | 2 |  | first visit to meet participants
| Tues 21 Feb |  | 1
| Tues 14 Mar |  | 1
| Tues 21 Mar |  | 1
| Tues 25 April |  | 1
| Tues 9 May |  | 1
| Tues 23 May |  | 1
|  | TOTAL | 10
DRAFT PROGRAMME FOR TRINITY ACADEMY
Tuesdays and Thurs mornings
| W/C 30 Jan | W/C 6 FEB | W/C 13 FEB | HALF TERM | W/C 27 FEB | W/C 6 MAR | W/C 13 MAR | W/C 20 MAR | W/C 27 MAR | WC 3 APR | EASTER | W/C 24 APR | W/C 1 MAY | W/C 8 MAY | W/C 15 MAY | W/C 22 MAY | HALF TERM | W/C 5 JUN | W/C 12 JUN | W/C 19 JUN | W/C 26 JUNE | Sun 2 Jul
MUSIC LEADER | [15 empty] | FINISH & SUBMIT FINAL PIECE
SAM LEE
GUEST |  |  | Leafcutter John |  |  |  | Alasdair Roberts |  | Beccy Unthank |  |  | Cosmo Sheldrake
Topic | Collecting stories |  | Sound recording |  | Sharing of recordings |  | How to write a folk song |  | Learn a folk song |  |  | Song writing - inc recordings? | [6 empty] | rehearsal | rehearsal | Perf to other comm groups | Performance

## Jason Singh
PRS Residencies - sesssion schedule
JASON SINGH
Jason Singh visits | dates |  | no days
| 2016-11-09 |  | 1
| 2016-12-15 | Masterclass | 1
| 27th + 28th Feb |  | 2 |  | 27 Feb Warren
| 13th + 14th Mar |  | 2 |  | 14 Mar Warren
| 27th + 28th Mar |  | 2
| 10th + 11th April |  | 2
| 24th + 25th April |  | 2 |  | 25 April Warren
| 8th + 9th May |  | 2
| 22nd + 23rd May |  | 2
| 5th + 6th June |  | 2
|  | TOTAL | 18
Jez Riley French | dates |  | no days | day rate £180.00
half day rate £120.00
Dates Jez is already busy from Feb - July 2017.9 day section from 30th April - May 9th might change & if it does it will likely be still in May or June.
Feb:
15th in Leeds
17-19th - Kirchin festival
22nd in Manchester
March:
24th - 27th - away
28th - 4th April - around but have a few things to do locally. These can be moved if needed.
April:
certain days in April will be taken up with the Humber Bridge / Opera North project - as far as i'm aware my involvement will be perhaps 4 days during the install & the performance / public launch section.
28th - 30th - nordic festival / hull
May:
30th april - 9th May - in Estonia
11th May - performance
22nd-24th - folkestone
26th - 28th
June:
9th - 12th - northumbria
16th-20th
29th - 3rd July - involved in the Hull Uni sound & ecology symposium - this is same weekend as the PRS event so it'd be good to know when Jason't piece will be opening etc & of course any involvement you'd like from me (it'll be a weekend of running around to all the things going on that sound (!) very interesting)

## Eliza Carthy
PRS Residencies - sesssion schedule
ELIZA CARTHY
ELIZA CARTHY | dates |  | no days
| 2016-09-14 |  | 1
Mon | 2017-02-06 |  |  | Boxing club (5-6pm) tbc
Tues | 2017-02-07 | 12-5pm | 1 | wyke college pm (music students and creative writers)
Wed | 2017-02-08 |  | 1 | Walton ST Market am walkabout, Indoor Market, North Point market |  | Meeting Mikey 12 noon | 2:30
Thurs
Fri
Mon | 2017-02-13 |  |  | Boxing club (5-6pm) tbc | Spring Cottage
Tues | 2017-02-14 |  |  | Boxing club (5-6pm) tbc | Spring Cottage
Thur | 1900-01-15 |  | 1 | Boulevard Village Hall (community coffee morning group am)
Fri | 2017-02-17 |  |  | Wyke College
Mon | 2017-02-20 |  |  | Boxing club (5-6pm) tbc
tues | 2017-02-21 |  |  | mon or tues eve (5-6pm) boxing club
2017-02-27
2017-02-28
2017-03-01
2017-03-02
2017-03-03
2017-03-06
2017-03-07
2017-03-08
2017-03-09
|  | TOTAL | 4
2017-03-10
| 13-16 mar |  |  | sam & gary

## Errollyn Wallen
PRS Residencies - session schedule and planning
ERROLLYN WALLEN
Errollyn Wallen | dates | Detail | no days | EWB | Hotels | Sarah | Michael Harper | Mambo? | Gary H | Nola marshall | Orch X | Students
Thurs | 2017-01-26 | Visit Open Doors, meet key contacts working in the community, event showcasing musical achievements of local groups working with Open Doors, meet staff of Pearson and Thoresby Primary Schools at Thoresby Primary school, possibly meet local supporting artists - tbc | 1 | x6 hrs meeting & planning | accom booked |  |  | 3 hrs meeting
Fri | 2017-01-27 | planning and meet supporting artists/ student morning | 1
Thurs | 2017-03-09 | Thoresby am , Open Doors visit | 1 | 1 | accom booked |  |  | 1 |  | x
Fri | 2017-03-10 | Pearson Primary am ??? pm | 1 | 1 | accom booked
Sat | 2017-03-11 | Masterclass at Albemarle WOW | 1 |  | accom booked | 1
Sun | 2017-03-12 | contribute to panel discussion as part of WOW
Thurs | 2017-03-23 | Thoresby Primary am Open Doors pm | 1 | 1 |  |  |  |  | 1 | x
Fri | 2017-03-24 | Pearson Primary am - Gary alone |  | x |  |  |  |  | 0.5
Thurs | 2017-04-06 | Pearson Primary am Open Doors pm | 1 |  |  |  |  | 1 |  | x
| 2017-04-20 | Open Doors 10am-3pm | [6 empty] | 1
Tues | 2017-04-25 | Pearson at Thoresby am all day - Em and Mambo Jambo - twilight with parents |  | 1 |  |  |  | 1 |  | x
Tues | 2017-05-02 | Thoresby at Pearson all day - Em and Mambo Jambo - twilight with parents |  | 1 |  |  |  | 1
thurs | 2017-05-11 | workshops Errollyn and Mambo Jambo | 1 |  |  |  |  | 1
| from 15/5/17 | Workshops in first week of Kaleidoscope for Thoresby and Pearson |  | x |  |  |  | x | x
Sat | 2017-05-20 | Michael Harper with Errollyn - workshop Spirituals | 1 | participant |  |  | 1
Thurs | 2017-05-25 | Open Doors, plus in school workshop - Kaleidoscope week 2 at Thoresby | 1 | 1 | accom booked | 1 |  | 1 | 1
Fri | 2017-05-26 | workshops in schools - finale of Kaleidoscope week at Thoresby | 1 | 1 |  | 1 |  | 1 | 1
Thurs | 2017-06-15 | workshops open doors schools together 9-5 | 1 | 1 | accom booked | 1 |  | 1 | 1 |  | x
Thurs | 2017-06-22 | workshop coming together rehearsal 9-5 |  | 1 |  |  |  | 1 | 1 |  | x
| 2017-06-24 | Residency showcase day at Hull City Hall | 1 | 1 | accom to book | 1 |  | 1 | 1 |  | x
| 2017-06-29 | Rehearsal for supergroup moment 3.30 onwards | 1 | ? |  |  |  | 1 | 0.5 |  | x
| 2017-07-01 | Mighty River performance - 2pm
| 2017-07-02 | Performance at Festival weekend | 1 | 1 |  |  |  | 1 | 1 |  | x
|  | TOTAL of days | 15 | 11 |  | 8 | 1 | 12 | 9 |  | 5
|  |  |  | EWB | Hotels | Sarah | Michael Harper | Mambo? | Gary H |  | Orch X | Students
Draft Budget
EW travel & expenses |  |  | Fee |  | Travel | Accom | Expenses
|  |  | 6000 |  | 1920 | 630 | 320
Local supporting artists |  |  | Fees |  | Travel | Accom | Expenses
Em Whitfield Brooks | 1/2 day planning workshop activity in school and community on 26 Jan |  | 150 | ? | 50
| 11 days in schools & open doors re vocal confidence & performance |  | 4400 |  | 450
including working with parents in twilight sessions
| 2 x 2 day intensives with Mambo Jambo/Gary Hammond - 1st week Kaleidoscope |  | 900 |  | 100
Mambo Jambo | 12 days with open doors and schools |  | 4200
Gary Hammond | 10 sessions with EW - workshop support in Open Doors and with Schools - percussionist |  | 1800
Sandy Clarke and Stanislava |  | Student support up to 4 days - DBS checks
| TOTAL Local supporting artists |  | 11450 |  | 600 | 0 | 0
Visiting supporting artists
Michael Harper | one day workshop/performance with Errollyn - Em WB to be present |  | 600 |  | 120 | 80
Tom Armitage | 1 day with Errollyn - assistant composer |  | 300 | ? | 200
| 2 days on own with adults at Open Doors |  | 600 | ?
| further 3 days |  | 900 | ? | 200
Members of Orchestra X | 5 days with EW - 2 members at day rate of £300 plus travel |  | 3000 |  | 1500 | 650
Sarah Suckling (Cellist) | 1 day on 10 March - Albemarle Saturday |  | 300 |  | 120 | 65
| 7 project days |  | 2100 |  | 840 | 90
|  | TOTAL visiting supporting artists | 5700 |  | 2140 | 795 | 0
|  | Total fees | 23150
Open Doors schedule
| 2017-03-09 | afternoon at Open Doors, with Errollyn Wallen, Em Whitfield Brooks, and Mambo Jambo
| 2017-03-23 | afternoon at Open Doors, with Errollyn Wallen, Em Whitfield Brooks, and Gary Hammond (percussionist)
| 2017-04-06 | afternoon at Open Doors with Errollyn Wallen and Mambo Jambo
| 2017-04-20 | Open Doors 10am-3pm - Gary Hammond
| 2017-05-20 | Michael Harper with Errollyn - workshop Spirituals - a day of singing for everyone involved in the residency
| 2017-05-25 | Open Doors in the afternoon, plus in school workshop - Kaleidoscope week 2 at Thoresby
| 2017-05-26 | workshops in schools - finale of Kaleidoscope week at Thoresby, Open doors clients invited to join in
| 2017-06-15 | workshops open doors schools together 9-5 - all artists
| 2017-06-22 | workshop coming together rehearsal 9-5 - all Residency participants during the day - all artists
| 2017-06-24 | Residency showcase day at Hull City Hall - everyone
| 2017-06-29 | Rehearsal for supergroup moment 3.30 onwards - involvement tbc
| 2017-07-02 | Afternoon 'supergroup' performance at Festival weekend

## Brian Irvine
PRS Residencies - sesssion schedule
BRIAN IRVINE
BRIAN IRVINE | dates |  | no days |  |  |  | P&F Just before lunch or afternoon sessions best
| 2016-11-30 |  | 1 |  |  |  | Emmaus - separate from Crossings because of issues around sobriety
| 02/3 March 2017 |  | 2
| 6/7 Apr 2017 |  | 2
| 13/14 Apr 2017 |  |  | pencil | easter holidays
| 20/21 Apr 2017 |  |  | pencil | easter holidays
| 27/28 Apr 2017 |  |  | pencil
| 4/5 May 2017 |  | 2
| 11/12 May 2017 |  |  | pencil
| 25/26 May 2017 |  | 2
| 2017-05-27 |  | 1 | tbc | albemarle | possible
| 1/2 June 2017 |  | 2
| 8/9 June 2017 |  |  | pencil
| 15/16 June 2017 |  |  | pencil | albemarle sat pos on 17
| 22/23 June 2017 |  | 2
| 28/29 June 2017 |  | 2
|  | TOTAL | 16
02/3 March 2017
6/7 Apr 2017
4/5 May 2017
18/19 May 2017
27 May tbc
1/2 June 2017
15/16 June 2017
22/23 June 2017
28/29 June 2017

## James Redwood CPD
James Redwood CPD sessions
CPD sessions for students and local musicians
Date | Venue | Details
Friday 4 November | University of Hull | am local leaders, pm joined by students
Friday 24th Feb | University of Hull
Friday 21st April | University of Hull

## Other relevant dates
Albemarle Saturdays
2016-03-11 | pos Errollyn Wallen (tbc)
2016-04-08
13 or 20 May
2016-06-17
2016-07-08
2016-08-05
2016-09-09
2016-10-07
2016-11-04
2016-12-15 | Jason Singh Masterclass