|  | Greatfield 60 Years On – Production Schedule |  |  |
| --- | --- | --- | --- |
| Dates | Activity | STATUS | NOTES |
|  |  | COMPLETE / ON-TIME / BEHIND |  |
| Aug. – Dec. 2016 | Planning for and delivery of community TV production course in partnership with Estuary TV |  |  |
| January 2017 | Opening of pop-up-gallery. Launch event and promotion of Greatfield 60 Years On including introducing plans for a community garden and other environmental works for Greatfield. First community TV shorts screenings. Start weekly ‘Creativity begins at Home’ workshops Teatime Talk 1 –About Greatfield famous son Mick Ronson |  |  |
| February 2017 | Begin to build curated collection of Greatfield photographs to be displayed at the pop-up gallery. Weekly ‘Creativity begins at Home’ workshops Teatime Talk 2 |  |  |
| March 2017 | Recruitment of volunteers and participants for ‘Art in a Cart’ workshops. Workshop planning/materials purchased. TV shorts screenings. Weekly ‘Creativity begins at Home’ workshops Teatime Talk 3 |  |  |
| April - May 2017 | Delivery of ‘Art in a Cart’ workshops at sites around Greatfield throughout April and May. Exhibition of ‘Boxes of Beauty and Hope’ at the pop-up gallery. Weekly ‘Creativity begins at Home’ workshops Teatime Talk 4-5 |  |  |
| June 2017 | ‘Freedom from Worry’ carnival costume workshops delivered with local schools and community groups. TV shorts screenings. Weekly ‘Creativity begins at Home’ workshops Teatime Talk 6 |  |  |
| July – September 2017 | Planning, preparation and promotion of Street Party event Street Party with screenings, family activities, carnival costume parade and dance performances. Weekly ‘Creativity begins at Home’ workshops Teatime Talk 7-9 |  |  |
| October - December 2017 | End party will act as official launch of new community garden/environmental works for Greatfield including new permanent artworks/art trail. Weekly ‘Creativity begins at Home’ workshops. Exhibition of photography done through the year. TV shorts screenings Teatime Talk 11-12 |  |  |
| January – February 2018 | Evaluation of Greatfield 60 Year On including continuation plans. |  |  |