## production schedule
DAY/DATE | TIME | DETAIL | NOTES | WHO | COMPANY | CREW REQD | VEHICLES
Mon 7th August | 800 | Security on site |  | AL | Prestige | 0
| 800 | Begin Trakway install |  | AL | LIVE | 0
| 900 | Fencing delivered |  | AL | Actavo | 0
| 900 | Plant delivered | Forks & telehandler | AL | Nixons | 0
| am | Do Ground survey? |  | AL |  | 0
| am | build production compound |  | AL |  | 0
| am | toilets delivered |  | AL | Add Plant | 0
| pm | Distro delivered | Telehandler required | AL | IDE | 0
| 2000 | security changeover |  |  | Prestige | 0
| 2000 | Finish |  | AL |  | 0
Tues 8th August | 800 | security changeover |  |  | Prestige
| 800 | continue Trakway |  |  | LIVE
| am | cone off truck parking area |  | AL | TGE | 1 site
| 900 | Generators delivered | fork in to position | AL | John F Hunts | 1 site
| 1000 | Marquees delivered | Build production tent | AL | Nationwide
| am | Bins delivered | 4 x 1100l |  | Hull CC
| pm | collect comms | from 2017 office | AL
| pm | install backstage power | Test | AL |  | 1 site
| 1600 | trakway handover |  | AL | LIVE
| pm | build show/build compound | ped barrier | AL |  | 1 site
| pm | install production power | Test | AL |  | 1 site
| eve? | Trucks arrive | park up ready for Wednesday | AL | Cirk Vost
| 2000 | security changeover |  |  | Prestige
| 2000 | Finish |  | AL |  | 1 site
Weds 9th August | 800 | security changeover |  |  | Prestige
| 800 | Jan on site | Do mark-up | AL | Cirk Vost
| 800 | unload trucks | forks & telehandler | AL | Cirk Vost | 1 site
| 900 | Crew on site | assist with unload |  | TMC & freelancers | 1 site, 4 stage, 2 lx
| am | toilets serviced |  |  | Add Plant
| 1300 | LUNCH |  | ALL
| 1400 | finish unload and begin build | start heras compound for match? | AL | Cirk Vost | 1 site, 4 stage, 2 lx
| pm | Trucks off site | Walton St?? | AL | Cirk Vost
| pm | Distribute fire extinguishers |  | AL | TGE | 1 Site
| 1800 | crew finish |  |  | TMC & freelancers | 4 stage, 2 lx
| 1900 | Continue and prepare for crane |  | AL |  | 1 site
| 2000 | security changeover |  |  | Prestige
| 2200 | finish |  | ALL | Cirk Vost | 1 site
Thurs 10th August | 800 | security changeover |  |  | Prestige
| 800 | On site |  | AL | Cirk Vost | 1 site
| 800 | Crane on site & set-up | Jan to position | AL | Central cranes
| 900 | Crew on site | assist with build |  | TMC | 4 stage
| 900 | Crew on site | begin rig |  | Freelancers | 3 lx
| 1300 | Crane off site |  |  | Central cranes
| 1300 | LUNCH
| 1400 | Continue |  | All | All | 1 site, 4 stage, 3 lx
| pm | Production meeting? | production tent | AL, KF, HW-W, LM, GH, CT
| 1400 | remove some Trak | To make space for stakes |  | LIVE | 1 site
| 1800 | crew finish |  |  | TMC | 4 stage
| 1800 | Dinner |  | All | All | 1 site, 3 lx
| 1900 | Focus & Plot |  | AL | Cirk Vost | 1 site, 3 lx
| 2000 | security changeover |  |  | Prestige
| 2200 | finish | Lighting may go longer? | ALL | Cirk Vost | 1 site
Fri 11th August | 700 | Remove Trak |  | AL | LIVE
| 800 | security changeover |  |  | Prestige
| 800 | On site |  | AL | Cirk Vost | 1 site
| 900 | Crew on site | Deckchairs and finalise |  | TMC | 4 stage
| 900 | PA company on site | Set-up FOH PA | AL | 3d productions
| am | toilets serviced |  |  | Add Plant
| am | Site safety walk round |  | AL, GH +??
| am | Set-up site lighting |  | AL | TGE | 1 site
| 1300 | Lunch
| 1400 | Continue |  |  | ALL
| 1400 | Continue site lighting check |  | AL | TGE | 1 site
| pm | soundchecks |  |  | 3d/Cirk Vost
| pm | Public toilets delivered | AL to site | AL | AddPlant
| 1800 | Dinner |  |  | ALL
| 1900 | continue as required |  | AL | ALL | 1 site
| 2000 | security changeover | 2 additional SIA on site to cover rehearsal |  | Prestige
| 2300 | Finish | Lighting may go longer? | ALL | Cirk Vost | 1 site
Sat 12th August | 800 | security changeover |  |  | Prestige
| 900 | Work as required |  |  | Cirk Vost
| 900 | build heras compound | for football match | AL | TMC | 6 x crew
| 900 | tidy site | Inc. site dressing | AL | TGE | 1 site
| am | Production meeting | in café/production tent | AL, KF, HW-W, LM, GH, CT
| 1300 | Lunch
| 1400 | continue as required |  | AL | ALL | 1 site
| pm | final site checks |  | AL |  | 1 site
| pm | sound checks |  |  | Cirk Vost, 3d productions
| 1700 | De-rig Heras compound | when safe to do after match | AL | TMC | 6 x crew
| 1800 | Dinner |  |  | ALL
| 1900 | medical on site |  |  | Heart
| 1900 | Pre show checks |  |  | Cirk Vost
| 1900 | Volunteer briefing |  | ???
| 1930 | Show security on site | Gareth to brief | GH | Prestige
| 2000 | carpark up & running |  |  | Prestige
| 2030 | gates to deckchairs open
| 2130 | SHOW 1
| 2230 | Show finish
| 2300 | Clear site
| 2300 | Finish & Turn off
| 2330 | security changeover |  |  | Prestige
Sun 13th August | 800 | security changeover |  |  | Prestige
| am | toilets serviced |  |  | Add Plant
| 1100 | Work as required |  | AL | Cirk Vost | 1 site
| 1300 | Lunch
| 1400 | continue as required |  | AL | ALL | 1 site
| pm | Soundchecks |  |  | Cirk Vost, 3d productions
| pm | final site checks |  | AL |  | 1 site
| 1800 | Dinner |  |  | ALL
| 1900 | medical on site |  |  | Heart
| 1900 | Pre show checks |  |  | Cirk Vost
| 1900 | Volunteer briefing |  | ???
| 1930 | Show security on site | Gareth to brief | GH | Prestige
| 2000 | carpark up & running |  |  | Prestige
| 2030 | gates to deckchairs open
| 2130 | SHOW 1
| 2230 | Show finish
| 2230 | Begin get-out - Finish @ 0100 | deck chairs, lighting & sound | AL | Cirk Vost, freelancers, TMC | 1 site, 6 stage, 3 lx
| 2230 | sound get-out |  |  | Cirk Vost, 3d productions
| 2300 | Clear site
| 2300 | re-instate build barriers | set-up tower lights | AL |  | 1 site
2330
| 2330 | security changeover |  |  | Prestige
| midnight | re-install trakway | to be finished by 8am | AL | LIVE
| 100 | Finish
Mon 14th August | 800 | security changeover |  | AL | Prestige
| 800 | On site |  | AL | Cirk Vost | 1 site
| 800 | Crane on site |  | AL | central crane services
| 800 | crew on site | De-rig | AL | Cirk Vost | 4 stage, 2 lx
| am | Cleansing on site | clean audience areas |  | HULL CC
| am | Public toilets collected |  |  | Add Plant
| am | De-rig site lighting |  | AL |  | 1 site
| 1000 | Trucks on site |  |  | Cirk Vost
| 1300 | Crane off site |  |  | central crane services
| 1300 | Lunch
| 1400 | Contnue & load | De-rig show compound |  | Cirk Vost | 4 stage, 2 lx
| pm | production power out |  | AL | TGE | 1 site
| 1630 | Cirk Vost leave |  |  | Cirk Vost
| 1700 | Tidy show site |  | AL | TGE | 1 site
| 2000 | Finish |  | AL | TGE | 1 site
| 2000 | security changeover |  |  | Prestige
Tues 15th August | 800 | On site | de-rig backstage power | AL | TGE | 1 site
| 800 | Remove trak |  |  | LIVE
| 900 | remove marquee |  |  | Nationwide
| 1000 | Remove production compound |  | AL | TGE | 1 site
| am | Cleansing on site | clean all |  | HULL CC
| am | return comms |  | AL | TGE
| 1100 | Distro collected | telehandler required | AL | IDE
| 1200 | Generators collected | Forks required | AL | John F Hunts
| 1300 | Lunch
| 1400 | Barriers collected | telehandler required | AL | Actavo
| pm | bins collected |  |  | Hull CC
| 1700 | Trakway finished |  |  | LIVE
| 1700 | plant collected | Forks & telehandler |  | Nixons
| 1800 | final tidy & site check | Hand back to park | AL | TGE | 1 site
| 1900 | Off site |  | AL | TGE | 1 site

## production contacts
NAME | COMPANY | WHAT | MOBILE NUMBER
Adam Long | TGE | Prodction manager | 07754 728316
Katy Fuller | Hull 17 | Exec producer | 07771 764656
Gareth Hughes | Hull 17 | Event manager | 07733 112272
Hannah Williams-Walton | Hull 17 | Producer | 07500 838553
Lily Mellor | Hull 17 | Assistant Producer | 07740 557720
Carys Taverner | Hull 17 | Assistant PM | 07851 077582
Steve McKee | Hull cc | Cleansing | 07789 372506
HCAL
HCAL
Jan Naets | Cirk Vost | Technical manager | 33698921034
Gaz Harding | 3d Productions | Sound engineer | 07834 058259
Mark Hare | LIVE events | Trakway | 07725 028122
Dave Graham | Nixon Extra | Plant hire | 07917 507314
Brian | Nationwide | Marquee Hire | 07775 515398
Stuart Barnett | IDE | Distro Hire | 01543 574111
Jean Byers | John F Hunt | Generators | 0191 4111200
Joy Whitley | Actavo | Barriers & fencing | 01652 601390
Paul | Heart Medical | Medical | 07764 926970
Justine peacocock | Prestige | Stewarding & child protection | 07886 838597
Jon Masters | Add Plant | toilets & plant | 07738 817940
Rona | The Music consortium | local crew | 07710 024749
Josh | Freelancer | lighting tech
| Freelancer | lighting tech
| Freelancer | lighting tech
| Freelancer | Site crew