## Sheet1
Project 22 Timelines
| Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug
Activity | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Venue budgets due | bar: Aug; Aug to Aug; Aug to Aug; Aug to Aug
Collate budgets | bar: Aug to Aug; Aug to Aug; Aug to Aug; Aug to Aug
Final schedule agreed with PRs | bar: Aug; Aug to Aug; Aug to Aug; Aug to Aug
Communicate schedule to staff | bar: Aug to Aug; Aug to Aug; Aug to Aug
Finalise: Schedule for the day | bar: Aug to Aug; Aug to Aug
Finalise: Walking route | bar: Aug to Aug; Aug to Aug; Aug to Aug; Aug to Aug
Finalise: Launch content | bar: Aug to Aug; Aug to Aug
Finalise: Participants | bar: Aug to Aug; Aug to Aug
Finalise: Running order | bar: Aug to Aug; Aug to Aug; Aug to Aug
Finalise: Volunteer activity | bar: Aug to Aug; Aug to Aug; Aug to Aug
Finalise: Volunteer participation | bar: Aug to Aug; Aug to Aug
| Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
RSVP Deadline | bar: Sep
Collate rsvps | bar: Sep to Sep; Sep to Sep
Confirm attendees | bar: Sep to Sep
Confirm Venue | bar: Sep to Sep
Martin to finalise content | bar: Sep to Sep; Sep to Sep; Sep to Sep
Final final running order | bar: Sep to Sep; Sep to Sep
Venue Get in | bar: Sep to Sep
Venue fit up | bar: Sep
Participant rehearsals | bar: Sep to Sep
Rehearsals | bar: Sep to Sep
Event Day | bar: Sep
Get Out | bar: Sep to Sep
Advisory Panel meeting | bar: Sep

## Sheet2
Thursday 22 September
Media Schedule
6 | BBC live in Hull
9.48 | Press board the train in London
12.18 | Press arrive at Paragon | Greeted by Freedom Chorus
12.3 | Press briefing at Hull Truck | Martin Green to brief - possible HCC
13.15 | Media tour of city | Route to be finalised
14.15 | Media/Artist lunch stop | Possible Butler Whites
15 | Media move to Dock
15.15/15.30 | Full launch | Dock or Hull Truck weather dependent