LOGG FORTNIGHTLY ACTIVITY UPDATE

|  | PUBLIC FACING EVENTS/MOMENTS | INTERNAL | PRESS | DIGITAL | OTHER |
| --- | --- | --- | --- | --- | --- |
| Monday 30 October | Micropolis live 14:00-20:30 | Partial LOGG team travel back from Galway to Hull |  |  | Macnas performing in Dublin |
| Tuesday 31 October | Micropolis live 14:00-20:30 Halloween |  |  |  |  |
| Wednesday 1 November | Micropolis live 14:00-20:30 | LOGG Weekly catch up |  |  | Back to Ours begins |
| Thursday 2 November | Micropolis live 14:00-20:30 | Artist thank you drinks with McGuires location & time TBC |  |  | Noeline and Alex arrive in Hull |
| Friday 3 November | Micropolis live 14:00-20:30 Macnas Crates on roofs and along route |  |  |  | Simon Sharkey visits Micropolis Shapeshifter & Torch troupe rehearsals at Staples |
| Saturday 4 November | Micropolis live 14:00-20:30 Crates continue to be installed |  | HDM full page ad for Unleashed! |  | Stilts, Shapeshifters, Pegasus troupe rehearsals at Staples |
| Sunday 5 November | Micropolis closing night 14:00-20:30 Bonfire Night! |  |  |  | Ballerinas, hares, stag troupe rehearsals at Staples Macnas FOH vol briefing at Staples |
| Monday 6 November |  | Project Monitoring meeting for Micropolis |  |  | Musician, stag and hare rehearsals at Staples |
| Tuesday 7 November |  |  |  |  | Shadow wagon, birds and Crom puppeteer rehearsals at Staples Costume fittings all day at Staples Remaining Macnas performers arrive in Hull |
| Wednesday 8 November |  |  |  |  | Rehearsals at Staples for: Ballerinas, Shadow Puppeteers, Bandanarama, Mystic Puppeteers, Wolf Puppeteers, Stilts. Also costume fittings all day at Staples. |
| Thursday 9 November |  | Weekly catch up Budget catch up |  |  | Rehearsals at Staples for: Shadow Puppeteers, Crom Puppeteers, Wolf Puppeteers, Mystic Puppeteers Costume fittings all day Hair and makeup workshop 6pm at Staples And Now arrive in Hull |
| Friday 10 November |  |  |  |  | 6-9pm ALL CAST REHEARSAL, Staples carpark |
| Saturday 11 November | Land of Green Ginger Unleashed! 6:30pm VIP reception at Humber St Gallery 8pm | Land of Green Ginger after party at Humber St Gallery 10pm-1am |  |  | Simon Sharkey, Periplum, Thor, The McGuires all in Hull to attend Unleashed! |
| Sunday 12 November |  | Team Green Ginger curl up into a ball |  |  |  |

Updates

Too busy to update!

Key Dates:

17 June: Gold Nose of Green Ginger shop opens at North Point

3 – 6 July: Project VEAR voice collection

12 – 16 July: Project VEAR voice collection

10th, 13-14 July: And Now: community activity in Longhill

15 July: And Now: The Longhill Burn

19 August: Gold Nose of Green Ginger closing procession at North Point and reception at the History Centre

6 – 10 September: Project VEAR voice collection

24 September: Voice Park soft launch

26 September – 1 October: Voice Park live at Pickering Park

21 October – 5 November: Micropolis live at Springhead Pumping Station

11 November: Land of Green Ginger Unleashed

30 November: Chrissie and Elizabeth’s final day at Hull 2017