## Version control
Date | Who | Updated sheet/s | Updated LIVE budgets?
2017-04-09 | KF | Across all | Periplum, Sofaer - Sharepoint playing up so stopped!
2017-04-10 | KF/KS | Marketing spend-scoped out Periplum, still to scope out other marketing spend | Updated live budget templates (Cashflows to be checked by KF/EB)
2017-04-23 | KF | Updated Umbrella | Updated Umbrella
2017-04-26 | KS | Updated each sheet to automatically pull in actual spend | Updated so far live budgets I001 to I004, to continue with the rest

## TOTALS
TOTAL SHOULD BE |  |  | BUDGET NAME | BUDGET CODE | ALLOCATED BUDGET | CURRENT WORKING BUDGET
Original |  | 1400000 | Umbrella | I001 | 117124.03 | 117124.03 |  | 0
Moved to corporate for salaries | EB, GH, MM | 105000 | 2016 | I002 | 137650 | 137650 | C code closed | 0
Contribution to storage |  | 7000 | House | I003 | 33046.37 | 33046.37 |  | 0
Added from cotingency re Lone Twin |  | 5000 | Periplum | I004 | 140389.5 | 140389.5 | C code closed | 0
Budget remaining |  | 1293000 | Joshua Sofaer | I005 | 104020.23 | 104020.23 |  | 0
|  |  | Lone Twin | I006 | 107117.82 | 107117.82 |  | 0
|  |  | Aswarm | I007 | 123403 | 123403 |  | 0
Current budget splits |  |  | Davy & Kristin McGuire | I008 | 132100 | 132100 |  | 0
| was | currently | Macnas | I009 | 168449.05 | 168449.05 |  | 0
Umbrella | 363000 | 328000 | Crates | I010 | 61000 | 61000 |  | 0
2016 | 140000 | 135888 | Time Capsule | I011 | 15000 | 15000 |  | 0
2017 | 827000 | 830742 | Book | I012 | 120000 | 120000 |  | 0
|  |  | Fellowship | I013 | 19500 | 19500 |  | 0
| 1330000 | 1294630 | MarComms | I014 | 14200 | 14200 | Movement of marketing budgets to respective projects | 0
storage not moved out yet.
|  |  |  | TOTAL | 1293000 | 1293000
|  |  |  | under/over | 0 | 0
Note on G9: Kirsty Sutcliffe: £5k added into this budget from contingency towards payment to Love Twin

## I001 - Umbrella
|  | LOGG I001 - Umbrella |  |  |  |  | Allocated Budget |  | 117124.03 | Committed |  | Actuals | Purchase Order | Notes
[7 empty] | Working Budget | Sum of below | 117124.03 | 23.04.2017 - manual input |  | (Automated)
|  | Cost Centre | Sub code | Analysis code | Item | Notes | Calculation
[5 empty] | PROJECT TEAM - ADDITIONAL STAFF |  |  |  | 66562
ZK103.K161.I001 | . | ZK103 | K161 | I001 | Artistic Advisor | Simon Sharkey |  | 5950 |  | 4550 |  | 4550
ZK103.K226.I001 | . | ZK103 | K226 | I001 | Production Management 2016 | TGE |  | 7500 |  | 7500 |  | 7500
ZK103.K226.I001 | . | ZK103 | K226 | I001 | Production Management 2017 | TGE | To be negotiated | 29000 |  | 29000 |  | 15000 | 201702969 | £7k forecast for Aug, came out in july
ZK101.K207.I001 | . | ZK101 | K207 | I001 | MarComms Coordinator | Chrissie | March - Nov. 10 days p/m | 13500 |  | 13500 | } | 12900 | 201702961
ZK101.K207.I001 | . | ZK101 | K207 | I001 | Digital Coordinator | Phase 1 - Chrissie | March - May 8 days p/m | 3600 |  | 3600 | } |  | 201702961
ZK101.K207.I001 | . | ZK101 | K207 | I001 | Digital Coordinator | Phase 2 | Jun - Nov. 6 days per month | 5400 |  | 5400 | } |  | 201703886 | Reduced to 6 days per month instead of 7. Remainder moved to exec pot
ZK103.K227.I001 | . | ZK103 | K227 | I001 | Project team expenses | Various spent in 2016 |  | 1612 |  | 1611.93 |  | 1611.93
[5 empty] | CREATIVE DEVELOPMENT SESSIONS TO FEB 2017 |  |  |  | 17669.71
ZK103.K225.I001 | . | ZK103 | K225 | I001 | April, 2016 and October 2016 | All costs |  | 13230 |  | 13229.94 |  | 13229.94
ZK103.K224.I001 | . | ZK103 | K224 | I001 | November 2016 and February 2017 | All costs |  | 3735 |  | 3735 |  | 3735
ZK103.K224.I001 | . | ZK103 | K224 | I001 | Macnas; 122 - travel expenses foreign payment chg |  |  | 406.64 |  | 406.64 |  | 406.75
|  | ZK103 | K224 | I001 | Tech Petty Cash Claim 6 | Lunch for Aswarm 4 April |  | 43.1 |  | 43.1 |  | 43.1
|  | ZK103 | K224 | I001 | Macnas travel May 2017 |  |  | 254.97 |  | 254.97 |  | 254.97
ZK103.K223.I001 | . | ZK103 | K223 | I001 | CREATIVE DEVELOPMENT SESSIONS MAY 2017 ONWARDS |  |  |  | 3855.05 |  |  | 0
|  | ZK103 | K223 | I001 | Accommodation for Thor in May |  |  | 42 |  | 41.67 |  | 41.67 | 201703034
|  | ZK103 | K223 | I001 | accommodation for other artists in May |  |  | 240 |  | 240 |  | 240 | 201703035
|  | ZK103 | K223 | I001 | Catering for artist breakfast & 7 Alleys staff meals |  |  | 419 |  | 419 |  | 419
|  | ZK103 | K223 | I001 | And Now travel expenses May 2017 |  |  | 120 |  | 120 |  | 120
|  | ZK103 | K223 | I001 | Lunch for McGuire's visit |  |  | 34.05 |  | 34.05 |  |  |  | Petty Cash - to appear in live
|  | ZK103 | K223 | I001 | Dinner for Noeline visit 24.8 | Gusto |  | 226.3 |  | 226.3 |  | 226.3 | 201704806
|  | ZK103 | K223 | I001 | Dinner for Joshua | No. 6 Kitchenette - KF Sept expenses |  | 139.15 |  | 139.15 |  |  | expenses
|  | ZK103 | K223 | I001 | Drinks for Joshua | Sainsbury's - KF Sept expenses |  | 50 |  | 50 |  |  | expenses
|  | ZK103 | K223 | I001 | Noeline's travel August 2017 | euros |  | 465
|  | ZK103 | K223 | I001 | to be scoped |  |  | 2119.55 |  | 0
.. | . |  |  |  | ACCESS INITIATIVES |  |  |  | 7348.8
ZK110.K281.I001 | . | ZK110 | K281 | I001 | Periplum | Vocaleyes audio description |  | 1875 |  | 1875 |  | 2114.8 | 201703100
ZK110.K281.I001 | . | ZK110 | K281 | I001 | Joshua Soafer | AA Global - BSL interpreters | awaiting final quote | 324 |  | 324 |  | 162 | 201704804 | First invoice received 21/8 next invoice in Sept
ZK110.K281.I001 | . | ZK110 | K281 | I001 | Joshua Soafer | HERIB - Audio version pamphlet x 50 |  | 200 |  | 200 |  | 200 | 201703632
|  | ZK110 | K281 | I001 | Lone Twin | Ear defenders x 20 | Amazon - ordered with cc | 239.8 |  | 239
ZK110.K281.I001 | . | ZK110 | K281 | I001 | Aswarm | To be scoped |  | 1500
ZK110.K281.I001 | . | ZK110 | K281 | I001 | Davy and Kristin McGuire | To be scoped |  | 1500
ZK110.K281.I001 | . | ZK110 | K281 | I001 | Macnas | To be scoped |  | 1500
|  | ZK110 | K281 | I001 | Sensory Crates | Beckie May crates make |  | 210 |  | 210 |  |  | 201704623
[5 empty] | VOLUNTEER SUPPORT |  |  |  | 3035
ZK111.K283.I001 |  | ZK111 | K283 | I001 | Volunteer Uniform | High-Vis and cheap jackets |  | 452.42 |  | 452.42 |  | 452.42 |  | Claire Drury credit card - May 2017
ZK111.K283.I001 |  | ZK111 | K283 | I001 | Volunteer Uniform | Jackets |  | 544.69 |  | 544.69 |  | 544.69 | 201703083 | Arco
ZK111.K283.I001 | . | ZK111 | K283 | I001 | Volunteer lead | 7 Alleys - Sarah Harris |  | 750 |  | 750 |  | 750 | 201703612 | Sarah Harris
|  | ZK111 | K283 | I001 | Volunteer lead | The Longhill Burn - Sarah Harris |  | 225 |  | 225 |  | 225 | 201704246 | Forecast for August, paid out in july
|  | ZK111 | K283 | I001 | Land of Green Ginger badges | 1000 for Ambassadors and Participants |  | 424.5 |  |  |  |  | 201704859 | September
ZK111.K246.I001 | . | ZK111 | K246 | I001 | Other costs to be fully scoped |  |  | 638.39
[5 empty] | PRODUCING TEAM COSTS |  |  |  | 2822.18
ZK114.K299.I001 | . | ZK114 | K299 | I001 | Miscellaneous expenses | 70020672 K Fuller | 391.43 | 1328.58 |  | 1328.58 |  | 1328.58
[6 empty] | 70022176 E Bergeron | 16.36
[6 empty] | Excel Training Level I for Programming Team | 75
[6 empty] | Hull City Council; April rent Louis Pearlman Centre | 318
[6 empty] | July 2016 Taxi travel | -50
[6 empty] | July 2016 Taxi travel - LOGG - ZK114 K299 I001 | 50
[6 empty] | Licensing notification in HDM for East Park events | 344
[6 empty] | T Kagbala Credit Card Nov'16 | 75.99
[6 empty] | T Kagbala Credit Card Sept'16 | 77.5
[6 empty] | Tech Team Petty Cash Claim 4 (Mike Covell tour) | 20
[6 empty] | Tech Team Petty Cash Claim 5 (Postage Nolene Kindle) | 10.3
1328.58
ZK114.K115.I001 | . | ZK114 | K115 | I001 | May 2017 Taxi travel |  |  | 25.7 |  | 25.7 | } | 25.7 | expenses
|  | ZK114 | K115 | I001 | Elizabeth's mileage June & July | EB July expenses |  | 34.88 |  | 34.88 | } | 34.88 | expenses
|  | ZK114 | K115 | I001 | Gareth expenses |  |  | 23.17 |  | 23.17 |  | 23.17
|  | ZK114 | K227 | I001 | Lunch for staff meeting 11/5/17 | M&S - EB July expenses |  | 18.68 |  | 18.68 |  | 18.68 | expenses
|  | ZK114 | K227 | I001 | Lunch for staff meeting 19/7/17 | Unos - EB July expenses |  | 23.7 |  | 23.7 |  | 23.7 | expenses
|  | ZK114 | K227 | I001 | Lunch for staff meeting 13/6/17 | Tesco - EB July expenses |  | 23.12 |  | 23.12 |  | 23.12 | expenses
|  | ZK114 | K227 | I001 | Lou's flights to Dublin | Aer Lingus - paid by credit card May '17 |  | 297.97 |  | 297.97 |  | 297.97 | cc
|  | ZK114 | K227 | I001 | Lou's trains for Dublin |  |  | 83.46 |  | 83.46 |  | 83.46 | cc
|  | ZK114 | K227 | I001 | Lou's hotel room in Dublin | Ballsbridge Hotel - paid with cc |  | 158.65 |  | 158.65 |  | 158.65 | cc
|  | ZK114 | K227 | I001 | Business rates for LPC storage unit |  |  | 5.06 |  | 5.06 |  | 5.06 | 201703370
|  | ZK114 | K227 | I001 | Expenses for crates & Periplum | GH August expenses |  | 167.92 |  | 167.92 |  | 167.92 | expenses | Have only just seen this, but not sure if it's been paid yet as there is a conversion rate that needs to be calculated
|  | ZK114 | K227 | I001 | Expenses for trip to Ireland | LY May expenses - taxis and food |  | 111 |  |  |  |  | expenses
|  | ZK114 | K227 | I001 | Lunch for staff meeting 30/8/17 | M&S - petty cash |  | 21.6
ZK114.K227.I001 | . | ZK114 | K227 | I001 | Admin exp | To be scoped |  | 498.69 |  |  |  | -5.6843e-14
[5 empty] | PROJECT COSTS |  |  |  | 14931.29
ZK114.K225.I001 | . | ZK114 | K225 | I001 | Exec pot for allocation | Added £2450.61 from I004, taken £6,755 & £500 to I006, added £1750 from I006, added from I013 £21000, taken £11k to I009, taken £4675 to I007, added £3342.78 from I009, £1000 taken to I007 |  | 14931.29 |  |  |  | 0 |  | £900 added from Digital Coordinator Phase 2
[5 empty] | Marketing |  |  |  | 700
ZK109.K270.I001 | . | ZK109 | K270 | I001 | Historical marketing spend (£350 LOGG brand, £350 Fellowship brand) |  |  | 700 |  | 700 |  | 700
[5 empty] | Historial costs |  |  |  | 200
ZK100.K201.I001 | . | ZK100 | K201 | I001 | Macnas Ltd; invoices 5 & 6 (£600), returned BACS payment (£400) |  |  | 200 |  | 200 |  | 200
[10 empty] | 92012.75 |  | 67818.46

## I002 - 2016 (closed)
LOGG I002 - 2016 |  |  |  |  | Allocated Budget |  | 137650
[5 empty] | Working Budget | Sum of below | 137650
Cost Centre | Sub code | Analysis code | Item | Notes | Calculation
|  |  | COMMISSIONS |  |  |  | 130700 | All paid in actuals
|  |  | Joshua Sofaer | Total commission fee |  | 18934
|  |  | Davy and Kristin McGuire | Total commission fee |  | 18658
|  |  | Aswarm | Total commission fee |  | 18831
|  |  | Periplum | Total commission fee |  | 17687
|  |  | Scottee | Total commission fee |  | 19487
|  |  | Dominic Wilcox | Total commission fee |  | 18130
|  |  | Lone Twin | Total commission fee |  | 18973
|  |  | ALL OTHER COSTS |  |  |  | 6950 | All paid in actuals
|  |  | Detailed out in budget record / Dedbod | includes Bingo Hall air testing and Periplum licence fee |  | 6950

## I003 - House (2017)
|  | LOGG I003 - House (2017) |  |  |  |  | Allocated Budget |  | 33046.37 | Committed |  | Actuals | Purchase Order | Notes
[7 empty] | Working Budget | Sum of below | 33046.37
|  | Cost Centre | Sub code | Analysis code | Item | Notes | Calculation
[5 empty] | RENT AND BILLS |  |  |  | 16457.94
ZK105.K237.I003 | . | ZK105 | K237 | I003 | Rent | Jan -Nov | 12 x £1100 | 13200 |  | 13200 |  | 8800
ZK114.K147.I003 | . | ZK114 | K147 | I003 | Gas and Elec | Estimate for DD | 12 x £122 | 1464 |  | 1464 |  | 577.33 |  | First pymt £131.04 on card, then mthly DD of £99 oer mth
ZK105.K207.I003 | . | ZK105 | K207 | I003 | Council Tax |  |  | 1535.94 |  | 1535.65 |  | 1535.65
ZK105.K147.I003 | . | ZK105 | K147 | I003 | Water | Estimate |  | 258 |  | 258 |  | 19
[5 empty] | SET UP COSTS |  |  |  | 200
ZK105.K240.I003 | . | ZK105 | K240 | I003 | Sofa purchase |  |  | 200 |  | 200 |  | 200
[5 empty] | RUNNING COSTS |  |  |  | 1482.35
ZK105.K239.I003 | . | ZK105 | K239 | I003 | Cleaning |  |  | 1400 |  | 1200 |  | 738 | 2017025377
ZK114.K145.I003 | . | ZK114 | K145 | I003 | Ongoing supplies | Pot for misc house spend |  | 80.6 |  |  | } | 0
|  | ZK114 | K145 | I003 | Registered letter to British Gas | Royal Mail - EB July expenses |  | 1.75 |  | 1.75 |  | 1.75
ZK114.K116.I003 |  |  |  |  | ADDITIONAL ACCOMMODATION |  |  |  | 11709.86 |  |  | 0
ZK114.K116.I003 | . | ZK114 | K116 | I003 | Hotel capacity needed - Joshua and Adam |  |  | 541.67 |  | 541.67 |  | 541.67 | 201702970
|  | ZK114 | K116 | I003 | Hotel capacity needed - Periplum lighting crew |  |  | 312.5 |  | 312.5 |  | 312.5 | 201703105
|  | ZK114 | K116 | I003 | Accommodation for Lone Twin May '17 |  |  | 162.5 |  | 162.5 |  | 162.5
|  | ZK114 | K116 | I003 | Accommodation for Adam 5th - 17th July | For Lone Twin's project (Ibis) |  | 750 |  | 750 |  | 750 | 201704019
|  | ZK114 | K116 | I003 | Accommodation for And Now | 6 - 16 July (Pure) |  | 4195 |  | 4195 |  | 4195
|  | ZK114 | K116 | I003 | Additional accommodation for And Now | 8 - 16 July (Ibis) |  | 500 |  | 500 |  | 500 | 201704127 | PO value was for £825, so £325 o/s (relates to £325 below)
|  | ZK114 | K116 | I003 | Accommodation for McGuires 4 July | Britannia Royal |  | 125.02 |  | 125.02 |  | 125.02 | 201704020
|  | ZK114 | K116 | I003 | Accommodation for Davy 5 July | Britannia Royal |  | 62.5 |  | 62.5 |  | 62.5
|  | ZK114 | K116 | I003 | Accommodation for Adam 5-8 Sep | Hideout |  | 324 |  | 324 |  | 324 | 201704932 | September payment. Invoice signed off.
|  | ZK114 | K116 | I003 | Accommdation for Periplum 14-16 July | Ibis 2 rooms 2 nights £75 each |  | 325 |  | 325 |  |  | 201704127
|  | ZK114 | K116 | I003 | Accommodation for McGuires 4 July | Ibis 4-9 & 18-23 Sept |  | 935 |  | 935 |  |  | 201704897 | Invoices for £660 received 13/9/17.
|  | ZK114 | K116 | I003 | Accommodation for Noeline and Peter | Ibis 10 July 2 rooms 1 night |  | 110 |  | 110 |  |  | 201704925 | Invoice came at £110 instead of 91.67; received 13/9/17
|  | ZK114 | K116 | I003 | Accommodation for Rosie and Katie | Ibis 2 rooms 11-15 Sept |  | 366.67 |  | 366.67 |  |  | 201704925
ZK114.K116.I003 | . | ZK114 | K116 | I003 | Hotel / Air BnB - artists, Adam etc | If competing demand on house |  | 3000
ZK105.K238.I003 | . |  |  |  | HISTORIC SET-UP COSTS |  |  |  | 3196.22 |  |  | 3196.22
ZK105.K238.I003 | . | ZK105 | K238 | I003 | Running costs | Asda supplies + key cutting | EB expenses | 130.69 |  | 130.69
ZK105.K238.I003 | . | ZK105 | K238 | I003 | House council tax | Initial payment |  | 322.29 |  | 322.29
ZK105.K238.I003 | . | ZK105 | K238 | I003 | House deposit & admin fee |  |  | 1300 |  | 1300
ZK105.K238.I003 | . | ZK105 | K238 | I003 | running costs | Initial deep clean |  | 288 |  | 288
ZK105.K238.I003 | . | ZK105 | K238 | I003 | Setup costs | Asda supplies II | credit card | 630.09 |  | 630.09
ZK105.K238.I003 | . | ZK105 | K238 | I003 | Setup costs | Argos-Tumble dryer | credit card | 217.65 |  | 217.65
ZK105.K238.I003 | . | ZK105 | K238 | I003 | TV licence |  |  | 145.5 |  | 145.5
ZK105.K238.I003 | . | ZK105 | K238 | I003 | Water |  |  | 162 |  | 162
[10 empty] | 29765.48 |  | 22041.14

## I004 - Periplum(closed)
|  | LOGG I004 - Periplum |  |  |  |  | Allocated Budget |  | 140389.5 | Committed | Actuals | Purchase Order | Notes
[7 empty] | Working Budget | Sum of below | 140389.5
|  | Cost Centre | Sub code | Analysis code | Item | Notes | Calculation
[5 empty] | CREATIVE COMMISSION |  |  |  | 85307
ZK101.K207.I004 | . | ZK101 | K207 | I004 | Periplum Commission and Production Agt |  |  | 85307 |  | 85307 | 85307 | 201702631 | Committed & budget amended to reduce final payment less £338 contingency to cover additional H2017 oncosts
[5 empty] | PRODUCTION COSTS |  |  |  | 49080.11
ZK103.K161.I004 | . | ZK103 | K161 | I004 | Production Budget devolved to TG | To be fully scoped |  | 45272.96 |  | 45272.96 | 45272.96 | 201702984 | Altered for final budget = kf
ZK106.K244.I004 | . | ZK106 | K244 | I004 | Park costs | Hire, admin, licence |  | 2707.5 |  | 2707.5 | 2707.5 | 201703125
ZK106.K244.I004 | . | ZK106 | K244 | I004 | Park costs | Pavilion Hire - HCAL |  | 300 |  | 300 | 300 | 201703562
ZK106.K245.I004 | . | ZK106 | K245 | I004 | Elizabeth's May expenses | Batteries & consumables |  | 51.74 |  | 51.74 | 51.74 | Credit card or Expenses
|  | ZK106 | K245 | I004 | Community cast drinks | Paid using petty cash |  | 193.9 |  | 193.9 | 193.9 | Credit card or Expenses
|  | ZK106 | K245 | I004 | Gifts for artists | KF May expenses |  | 21 |  | 21 | 21 | Credit card or Expenses
|  | ZK106 | K245 | I004 | Grip tape for Periplum | MM May expenses |  | 48.15 |  | 48.15 | 48.15 | 201703329 | May be recharged
|  | ZK106 | K245 | I004 | Meeting refreshments | MM May expenses |  | 18.2 |  | 18.2 | 18.2 | 201703329
ZK106.K245.I004 | . | ZK106 | K245 | I004 | Car park hire | Mallet lambert |  | 450 |  | 450 | 450
ZK107.K133.I004 | . | ZK107 | K133 | I004 | Tech Petty Cash Claim 6 | Laminating pouches for signage |  | 16.66 |  | 16.66 | 16.66
|  | MARKETING SHEET SPEND - HERE DOWN | [5 empty] | Marketing total | 6002.39
ZK109.K270.I004 | . | ZK109 | K270 | I004 | Horses and scrolls |  |  |  | 1315.39 |  | 1315.39
[5 empty] | Horses |  | 2 days @ £500 | 1000 |  | 1000 |  | 201703112
[5 empty] | Scrolls design | Prop maker |  | 168.39 |  | 168.39 |  | 201703116
[5 empty] | Scrolls print |  |  | 53 |  | 53 |  | 201702922 |  | x
[5 empty] | Business cards print |  |  | 29 |  | 29 |  | 201702923 |  | x
[5 empty] | Business cards additional print run |  |  | 65 |  | 65 |  | 201703146
ZK109.K271.I004 | . | ZK109 | K271 | I004 | Invitations and posters |  |  |  | 2713.7 |  | 0
[5 empty] | Invitations print and delivery | Bluestorm | 10000 | 1385 |  | 1385 | 1385 | 201703158
[5 empty] | Distribution | BKR (Bluestorm) |  | 950 |  | 950 | 950 | 201703158
[5 empty] | Additional print run of invites | Bluestorm | 500 | 362 |  | 362 | 362 | 201703113
[5 empty] | More print for Periplum |  |  | 16.7 |  | 16.7 | 16.7
ZK109.K138.I004 | . | ZK109 | K138 | I004 | Ecowash |  |  |  | 500 |  | 500
[5 empty] | All costs | Andy Pea |  | 500 |  | 500 |  | 201703145
ZK109.K158.I004 | . | ZK109 | K158 | I004 | Resident notification |  |  |  | 445.3 |  | 445.3
[5 empty] | Print and fulfilment | Kall Kwik | 835 homes | 205.3 |  | 205.3 |  | 201702924 |  | x
[5 empty] | Distribution | Bluestorm | 835 homes | 240 |  | 240 |  | 201702925 |  | x
ZK109.K159.I004 | . | ZK109 | K159 | I004 | Wayfinding and signage |  |  |  | 740 |  | 740
[5 empty] | Print and install | John E Wright |  | 740 |  | 740 |  | 201703117 |  | x
ZK109.K272.I004 | . | ZK109 | K272 | I004 | Confetti pages |  |  |  | 288 |  | 288
[5 empty] | design | Process Black |  | 50 |  | 50 |  | 201703336
.. | . |  |  |  | print | Bluestorm |  | 238 |  | 238 |  | 201703335
[5 empty] | Other |  |  |  | 0 |  | 0
.. | . |  |  |  | Balance until fully scoped |  |  | 0
[10 empty] | 140389.5 | 140389.5

## I005 - Joshua Sofaer
|  | LOGG I005 - Joshua Sofaer |  |  |  |  | Allocated Budget |  | 104020.23 | Committed |  | Actuals | Purchase Order | Notes
[7 empty] | Working Budget | Sum of below | 104020.23
|  | Cost Centre | Sub code | Analysis code | Item | Notes | Calculation
[5 empty] | CREATIVE COMMISSION |  |  |  | 80116
ZK101.K207.I005 | . | ZK101 | K207 | I005 | Joshua Sofaer Commission and Production Agt |  |  | 80116 |  | 80116 |  | 75618.7 | 201702199 | Added staffing costs of £540 (4 days at £135/day) to be paid with final payment. Final bill Sept
Final invoice received 29/8
[5 empty] | PRODUCTION COSTS |  |  |  | 18291.23
ZK103.K161.I005 | . | ZK103 | K161 | I005 | Production Budget devolved to TG |  | To be fully scoped | 6000 |  | 6000 |  | 3000 | 201703107
ZK103.K245.I005 | . | ZK103 | K245 | I005 | Horses |  |  | 1000 |  | 1000 |  | 1000 | 201703836 | 2 invoices - 1st received and signed 22/6, 2nd received and signed 16/8 note: there's £100 left in the PO that I've final matched
ZK107.K136.I005 | . | ZK107 | K136 | I005 | Shop Unit rental |  |  | 4000 |  | 4000 |  | 4000 | 201703003
ZK107.K150.I005 | . | ZK107 | K150 | I005 | Shop unit business rates | To be paid by direct debit | June £240.90 followed by 3 payments of £242 | 966.9 |  | 966.9 |  | 724.9 | Direct Debit | Paid over 10 months
ZK106.K245.I005 | . | ZK106 | K245 | I005 | Shop beam counter | Lab Tek Instruments |  | 87 |  | 87 |  | 87 | credit card
ZK106.K247.I005 | . | ZK106 | K247 | I005 | Coaches for closing ceremony | EYMS | 2 coaches, 1x £100, 1x £320 | 420 |  | 420 |  | 420 | 201704616 | August-EB signed invoice 18.08.17
ZK106.K120.I005 | . | ZK106 | K120 | I005 | Catering costs closing ceremony | Hull Culture & Leisure | 90 people @ £7.45 per head, plus staff member at £25 - discount included | 621.25 |  | 621.25 | } | 0 | 201704661 | Sept
|  | ZK106 | K120 | I005 | Other catering closing ceremony | Drinks | Tab on day - will be invoiced with food. | 250 |  | 250 | } |  |  | Sept
ZK106.K248.I005 | . | ZK106 | K248 | I005 | PA and staging for NP closing ceremony | Saville Audio and Visual |  | 593.6 |  | 593.6 |  | 0 | 201704685 | Sept
ZK106.K265.I005 | . | ZK106 | K265 | I005 | Stewards and First Aid - closing ceremony | Prestige Support Limited |  | 104 |  | 104 | } | 104 | 201704735 | invoice received 22/8
|  | ZK106 | K265 | I005 | Pedestrian Barrier | All Occasions |  | 92.5 |  | 92.5 | } | 92.5 | 201704737 | Invoice received 22/8
ZK106.K232.I005 | . | ZK106 | K232 | I005 | Honey G closing ceremony | Fee and transport | boo | 2550 |  | 2550 | } | 2550 | 201704638 | August
|  | ZK106 | K232 | I005 | Closing Ceremony Guests | Gold Man |  | 150 |  | 150 | } | 150 | 201704746 | invoice received 23/8
|  | ZK106 | K232 | I005 | Closing Ceremony Guests | White Rabbit Costume |  | 40 |  | 40 | } |  | credit card
|  | ZK106 | K232 | I005 | Closing Ceremony Guests | deposit for Santa costume |  | 200 |  | 200 |  | 200 | BACS
|  | ZK106 | K232 | I005 | Closing Ceremony Guests | Santa |  | 225 |  | 225 |  | 225 | BACS & petty cash | Santa costume to be paid by BACS 17/8 (£175 + £200 deposit). Santa to be paid with petty cash on Saturday 19th (£50)
ZK106.K227.I005 | . | ZK106 | K227 | I005 | Other costs to be met by Hull 2017 |  |  | 338.19 |  |  | } | 0
|  | ZK106 | K227 | I005 | Refreshments for staff and artists | Cooplands - EB July expenses |  | 5.56 |  | 5.56 |  | 5.56 | Expenses | To be coded
|  | ZK106 | K227 | I005 | Shop Electricity |  |  | 400 |  | 400 | } |  | Direct Debit
|  | ZK106 | K227 | I005 | PPL |  |  | 180 |  | 180 | } |  |  | Paying via Northpoint Shopping Centre
|  | ZK106 | K227 | I005 | PRS |  |  | 37.23 |  | 37.23 | } |  |  | To be journalled from Tech and Ops
|  | ZK106 | K227 | I005 | Chaperones for YP closing ceremony |  | 1 chaperone, 3 hours @ £10 per hour | 30 |  | 30 |  | 0 | 201704738 | Invoice received 13/9/17
.. | .
.. | .
ZK109.K159.I005 | . | ZK109 | K159 | I005 | Documentary Film |  |  |  | 3000 |  |  | 2045.45 | 201703790
[5 empty] | Electric Egg | Contribution to M&E |  | 3000 |  | 3000 |  |  |  | £1500 to be paid in July, £1500 to be paid in Aug/Sept
.. | . |  |  |  | Ecowash |  |  |  | 375
ZK109.K138.I005 | . | ZK109 | K138 | I005 | All costs | Andy Pea |  | 375 |  | 375 |  | 375 | 201703563
[5 empty] | Pamphlet |  |  |  | 907
ZK109.K271.I005 | . | ZK109 | K271 | I005 | Gold Nose of Green Ginger in-shop leaflet | Bluestorm | Print 10,000 | 907 |  | 907 |  | 907 | 201703702
[5 empty] | Design Time |  |  |  | 150
ZK109.K270.I005 | . | ZK109 | K270 | I005 | Process Black | Pamphlet design work | 1.5 days @ £300 p/6hrs | 150 |  | 150 |  | 150 | 201704309 | August Payment
[14 empty] | There is a PO on this code for £600-201704191 (To close PO as per MM). Email sent 09.08.17 | 201704191
[5 empty] | Window Vinyl |  |  |  | 115
ZK109.K245.I005 | . | ZK109 | K245 | I005 | Design | Process Black |  | 50 |  | 50 |  | 50 | 201703834
|  | ZK109 | K245 | I005 | Print/Installation | John E Wright |  | 65 |  | 65 |  | 65 | 201703876
ZK109.K310.I005 | . | ZK109 | K310 | I005 | Closing |  |  |  | 1066 |  |  | 0
[5 empty] | Gold invite design and print | Bluestorm |  | 362 |  | 362 |  | 362 | 201704590 | Invoice received 29/8 Note: PO raised for £332 and invoice total £362
[5 empty] | Shop window stencil print and installation | John E Wright |  | 220 |  | 220 | } |  | 201704645 | Sep
[5 empty] | Interpretation board print and installation | John E Wright |  | 60 |  | 60 | } |  | 201704645 | Sep
[5 empty] | Interpretation board, leaflet and vinyl design | Process Black |  | 200 |  | 200 | } | 200 | 201704644 | Aug
[5 empty] | Leaflet print | Bluestorm |  | 224 |  | 224 |  | 224 | 201704642
[10 empty] | 103682.04 |  | 92556.11

## I006 - And Now
|  | LOGG I006 - Lone Twin |  |  |  |  | Allocated Budget |  | 107117.82 |  | Committed |  | Actuals | Purchase Order | Notes
[7 empty] | Working Budget | Sum of below | 107117.82
|  | Cost Centre | Sub code | Analysis code | Item | Notes | Calculation
[5 empty] | CREATIVE COMMISSION |  |  |  | 71600
ZK101.K207.I006 | . | ZK101 | K207 | I006 | Lone Twin Commission and Production Agt |  |  | 21500 |  |  | 21500 |  | 21500
ZK101.K208.I006 | . | ZK101 | K208 | I006 | And Now Commission and Production Agt |  |  | 19555 |  |  | 19555 | } | 50100 | 201703602 | Final invoice received and due for payment w/c 14 August
|  | ZK101 | K208 | I006 | And Now: Additional Commission and Production Agt |  |  | 30545 |  |  | 30545 | }
[5 empty] | PRODUCTION COSTS |  |  |  | 32513.82
ZK103.K161.I006 | . | ZK103 | K161 | I006 | Production Budget devolved to TG |  | Final | 25700.58 |  |  | 25700.58 |  | 25700.58 | 201704014 | August payment - second half. 2nd invoice received w/c 14/8
ZK106.K227.I006 | . | ZK106 | K227 | I006 | Production costs held by Hull 2017 |  | To be fully scoped | 0 |  |  |  | } | -1.0658e-13
|  | ZK106 | K227 | I006 | Public notice |  |  | 344 |  |  | 344 | } | 344 | 201703561
|  | ZK106 | K227 | I006 | Eastmount Playing Fields costs | Hire |  | 1826.25 |  |  | 1826.25 | } |  | 201704992
|  | ZK106 | K227 | I006 | Eastmount Recreation Centre | Hire cost | £20/day, 11 days plus donation | 500 |  |  | 500 | } | 500 | 201704299
|  | ZK106 | K227 | I006 | Water urn | Amazon purchase paid with cc |  | 44 |  |  | 44 | } | 44 | Credit Card | July
|  | ZK106 | K227 | I006 | Card for hopes | Amazon - MM expenses |  | 19.96 |  |  | 19.96 |  | 19.96 | 201704250 | July
|  | ZK106 | K227 | I006 | Posca Marker | Amazon - MM expenses |  | 27.96 |  |  | 27.96 |  | 27.96 | 201704250 | July
|  | ZK106 | K227 | I006 | Black spray paint for stencilling crate | Amazon - MM expenses |  | 7.93 |  |  | 7.93 |  | 7.93 | 201704250 | July
|  | ZK106 | K227 | I006 | Pencils for collecting hopes | Office Outlet - MM expenses |  | 14.99 |  |  | 14.99 |  | 14.99 | 201704250 | July
|  | ZK106 | K227 | I006 | Refreshments and SD Cards | Asda - MM expenses |  | 81.47 |  |  | 81.47 |  | 81.47 | 201704250 | July
|  | ZK106 | K227 | I006 | Refreshments for volunteers - Asda | Asda - MM expenses |  | 13.16 |  |  | 13.16 |  | 13.16 | 201704250 | July
|  | ZK106 | K227 | I006 | Milk | Premier - MM expenses |  | 0.99 |  |  | 0.99 |  | 0.99 | 201704250 | July
|  | ZK106 | K227 | I006 | Milk | McColl's - MM expenses |  | 1.49 |  |  | 1.49 |  | 1.49 | 201704250 | July
|  | ZK106 | K227 | I006 | Text update to participants | Textburst - MM expenses |  | 24 |  |  | 24 |  | 24 | 201704250 | July
|  | ZK106 | K227 | I006 | Hire of St Maggie's Hall | Volunteer briefing and rehearsals | £12 an hour - 5 hours | 54 |  |  | 54 | } | 54 | Petty Cash | July
|  | ZK106 | K227 | I006 | Artist Drinks | KF expenses |  | 79.58 |  |  | 79.58 | } | 79.58 | KF expenses | August
|  | ZK106 | K227 | I006 | Shoal snacks - Morrisons | petty cash |  | 32.6 |  |  | 32.6 |  | 32.6 | Petty Cash
|  | ZK106 | K227 | I006 | Shoal costumes - Primark | petty cash |  | 93 |  |  | 93 |  | 93 | Petty Cash
|  | ZK106 | K227 | I006 | Milk - Premier | petty cash |  | 1.19 |  |  | 1.19 |  | 1.19 | Petty Cash
|  | ZK106 | K227 | I006 | Meals for staff during delivery period | Morrisons - EB July expenses |  | 33.27 |  |  | 33.27 |  | 33.27 | EB expenses | August
ZK106.K115.I006 | . | ZK106 | K115 | I006 | Taxi for Siana Mae to help out | From our taxi account |  | 13.4 |  |  | 13.4 |  | 13.4 | Taxi account
ZK106.K244.I006 | . | ZK106 | K244 | I006 | Licence Application | for East Mount Playing Fields |  | 100 |  |  | 100 |  | 100 | Cheque | 2017-05-17
ZK106.K253.I006 | . | ZK106 | K253 | I006 | Lis Poulsom | Community Engagement Coordinator |  | 3500 |  |  | 3500 |  | 3500 | 201704226 | Should both be paid in July
[5 empty] | Heralding |  |  |  | 250
ZK109.K158.I006 | . | ZK109 | K158 | I006 | Margaret Photo Call | Sean Spencer |  | 250 |  | } | 250 |  | 0 | To be journaled from Digital.
}
[5 empty] | Event Marketing |  |  |  | 927
ZK109.K138.I006 | . | ZK109 | K138 | I006 | Design (Flyers, crate stencil, signage) | Process Black |  | 250 |  |  | 250 |  | 250 | 201705186 | Forecast Aug payment, actual paid July
|  | ZK109 | K138 | I006 | Print of A5 flyers and delivery | Bluestorm |  | 318 |  |  | 318 |  | 318 | 201704185 | Forecast Aug payment, actual paid July
|  | ZK109 | K138 | I006 | Distribution to households | Bluestorm |  | 215 |  |  | 215 |  | 215 | 201704184 | Forecast Aug payment, actual paid July
ZK109.K271.I006 | . | ZK109 | K271 | I006 | Distribution | Hull Box Office |  | 144 |  |  | 144 |  | 144 | 201704183 | Forecast Aug payment, actual paid July
[5 empty] | Wayfinding Signage |  |  |  | 729
ZK109.K159.I006 | . | ZK109 | K159 | I006 | Print and installation | John E Wright |  | 729 |  |  | 729 |  | 729 | 201704428 | Aug payment
[5 empty] | Resident Notifications |  |  |  | 246
ZK109.K335.I006 | . | ZK109 | K335 | I006 | Print and preparation of resident notification | Kalikwik |  | 146 |  |  | 146 | } | 146 | 201704182 | Forecast Aug payment, actual paid July
ZK109.K335.I006 | . | ZK109 | K335 | I006 | Distribution of resident notification letters | Bluestorm |  | 100 |  |  | 100 | } | 100 | 201704181 | Forecast Aug payment, actual paid July
[5 empty] | Eco Washes |  |  |  | 210
ZK109.K270.I006 | . | ZK109 | K270 | I006 | Eco washing around Longhill | Andy Pea |  | 210 |  |  | 210 |  | 0 | 201704627 | Invoice processed 13/09. Sept payment | I005
[5 empty] | Crates |  |  |  | 442
ZK109.K247.I006 | . | ZK109 | K247 | I006 | Longhill Burn stencil print | John E Wright |  | 65 |  |  | 65 |  | 65 | 201704330 | Aug payment
ZK106.K247.I006 | . | ZK106 | K247 | I006 | Miniature Crate make | Becky May |  | 77 |  | } | 77 |  | 77 | 201704256
|  | ZK106 | K247 | I006 | Walk the Plank cancellation | for crate movement |  | 300 |  | } | 300 |  | 300 | 201704596 | invoice received 21/8
[5 empty] | Facebook Advert |  |  |  | 200
ZK109.K272.I006 | . | ZK109 | K272 | I006 | Longhill Burn Facebook Advert | Tues - Sat |  | 200 |  |  | 200 |  | 0 | To be journaled from digital
[11 empty] | 107117.82 |  | 104631.57

## I007 - Aswarm
|  | LOGG I007 - Aswarm |  |  |  |  | Allocated Budget |  | 123403 | Committed |  | Actuals | Purchase Order | Notes
[7 empty] | Working Budget | Sum of below | 123403
|  | Cost Centre | Sub code | Analysis code | Item | Notes | Calculation
[5 empty] | CREATIVE COMMISSION |  |  |  | 80000
ZK101.K207.I007 | . | ZK101 | K207 | I007 | Aswarm Commission and Production Agt |  |  | 80000 |  | 80000 |  | 67781 | 201703143 | Added £2060 and £2628 for additional production costs to be paid with final payment - taken from production costs to be scoped)
[5 empty] | PRODUCTION COSTS |  |  |  | 35303
ZK103.K161.I007 | . | ZK103 | K161 | I007 | Production Budget devolved to TG or held by Hull 2017 |  | To be fully scoped | 27000 |  | 27000 |  | 13000 | 201704666 | Invoice for 50% received 17/8. £1000 taken from exec pot.
ZK111.K237.I007 | . | ZK111 | K237 | I007 | Room hire for volunteer training | Endeavour Training Centre |  | 32 |  | 32 |  | 32 | 201703564
ZK106.K227.I007 | . | ZK106 | K227 | I007 | Production Budget held by Hull 2017 |  | To be fully scoped | 1652.75 |  |  | } | -5.6843e-14 |  | Costs for additional production taken from here to commissioning fee
|  | ZK106 | K227 | I007 | Fee to KCOM for digging hole | Hole on Beverly Rd for Heralding |  | 700 |  | 700 | } | 700 | 201703733
|  | ZK106 | K227 | I007 | Room hire | Rehearsal and breakout space for voice collection | Mind | 420 |  | 420 | } | 420 | 201703882 | July payment
|  | ZK106 | K227 | I007 | Van Hire | To transport Voice Collectors | 2x July sessions | 675 |  | 675 | } | 372.83 | 201704005 | Likely to be paid out in July
|  | ZK106 | K227 | I007 | Milk for volunteer training session | EB July expenses | Mini Market | 1.25 |  | 1.25 | } | 1.25 | Expenses
|  | ZK106 | K227 | I007 | Refreshments for volunteer training session | EB July expenses | Poundworld | 7.25 |  | 7.25 | } | 7.25 | Expenses
ZK106.K245.I007 | . | ZK106 | K245 | I007 | Park costs | 5 days set up, 6 days live | £258 set-up, £515 live | 3564.75 |  | 3564.75 |  | 0 | 201704991 | October payment
|  | ZK106 | K245 | I007 | Bond for park hire |  |  | 1250 |  | 1250 |  |  | Cheque | Deposit
[5 empty] | Marketing |  |  | Marketing Total | 5779
.. | . |  |  |  | To be fully scoped (Marketing Campaigns, including design) |  |  | 3545 |  |  |  | 0
.. | . |  |  |  | To be fully scoped (Production Branding / Print Costs) |  |  | 2234 |  |  |  | 0
[5 empty] | Heralding |  |  |  | 55
ZK109.K158.I007 | . | ZK109 | K158 | I007 | Redifussion Stencil | John E Wright |  | 30 |  | 30 | } | 30
|  | ZK109 | K158 | I007 | Redifussion Stencil design | Process Black |  | 25 |  | 25 | } | 25 | 201704309 | Forecast Aug payment, actual paid July
|  | ZK109 |  | I007 | To be scoped |  |  | 0
[5 empty] | Flyers |  |  |  | 1500
|  | New code please |  |  | Design |  |  | 300
|  | New code please |  |  | Print |  |  | 700
|  | New code please |  |  | Distribution |  |  | 500
[5 empty] | Signage |  |  |  | 266
|  | New code please |  |  | Print and installation | John E Wright |  | 266
[5 empty] | Crate |  |  |  | 500
|  | New code please |  |  | Van hire |  |  | 150
|  | New code please |  |  | Fuel |  |  | 20
|  | New code please |  |  | Crew |  |  | 300
|  | New code please |  |  | Stencil | John E Wright |  | 30
[10 empty] | 113705.25 |  | 82369.33

## I008 - McGuires
|  | LOGG I008 - McGuires |  |  |  |  | Allocated Budget |  | 132100 | Committed | Actuals | Purchase Order | Notes
[7 empty] | Working Budget | Sum of below | 132100
|  | Cost Centre | Sub code | Analysis code | Item | Notes | Calculation
[5 empty] | CREATIVE COMMISSION |  |  |  | 90000
ZK101.K207.I008 | . | ZK101 | K207 | I008 | McGuires Commission and Production Agt |  |  | 90000 |  | 90000 | 80000 | 201702678
[5 empty] | PRODUCTION COSTS |  |  |  | 33000
ZK103.K161.I008 | . | ZK103 | K161 | I008 | Production Budget devolved to TG |  | To be fully scoped | 30000 |  |  | 15000 |  | First half out in August. Invoice received 16/8
ZK106.K227.I008 | . | ZK106 | K227 | I008 | Production Budget held by Hull 2017 |  | To be fully scoped | 2369.54 |  |  | 0
|  | ZK106 | K227 | I008 | Fire Signage |  |  | 262.58 |  | 262.58 |  | 201704754 | August
|  | ZK106 | K227 | I008 | First Aid Training | Davy and Rosie for build | TBC | 232 |  |  |  | 201705067
|  | ZK106 | K227 | I008 | Fridges for Pumping Station and Staples |  |  | 135.88 |  | 135.88 |  | GH expenses
[5 empty] | Marketing |  |  |  | 9100
.. | . |  |  |  | To be fully scoped (Marketing Campaigns, including design) |  |  | 6600 |  |  | 0
.. | . |  |  |  | To be fully scoped (Production Branding / Print Costs) |  |  | 2500 |  |  | 0
[10 empty] | 90398.46 | 95000

## I009 - Macnas
|  | LOGG I009 - Macnas |  |  |  |  | Allocated Budget |  | 168449.05 | Committed |  | Actuals | Purchase Order | Notes
[7 empty] | Working Budget | Sum of below | 168449.05
|  | Cost Centre | Sub code | Analysis code | Item | Notes | Calculation
[5 empty] | CREATIVE COMMISSION |  |  |  | 119657.22
ZK101.K207.I009 | . | ZK101 | K207 | I009 | Macnas Commission and Production Agt | Contract in euros |  | 119657.22 |  |  |  | 0 | Moneycorp - No PO required | €129,050 euros final rate
Cashflow??
[5 empty] | PRODUCTION COSTS |  |  |  | 36591.83
ZK103.K161.I009 | . | ZK103 | K161 | I009 | Production Budget devolved to TG |  | To be fully scoped | 30000 |  |  |  | 0
ZK106.K227.I009 | . | ZK106 | K227 | I009 | Budget held by Hull 2017 |  |  | 4466.13 |  |  |  | 0
ZK106.K115.I009 | . | ZK106 | K115 | I009 | Macnas Travel | Noeline and Peter - 11 Sept | Traveleads | 636.17 |  | 636.17 | } | 636.17 | 201704898 | September. Invoice for £120.36 signed off. Invoice of £515.81 signed off.
|  | ZK106 | K115 | I009 | Macnas Travel | Noeline and Alex - 15-17 Sept | Ryanair | 407.65 |  | 407.65 | } |  | Credit Card
|  | ZK106 | K115 | I009 | Macnas Travel | Noeline 2 Oct | Ryanair | 25.24 |  | 25.24 | } |  | Credit Card
|  | ZK106 | K115 | I009 | Macnas Travel | Noeline 4 Oct | Aer Lingus | 44.99 |  | 44.99 | } |  | Credit Card
|  | ZK106 | K115 | I009 | Macnas Travel | Noeline 16-19 Oct | Ryanair | 54.09 |  | 54.09 | } |  | Credit Card
|  | ZK106 | K115 | I009 | Macnas Travel | All trains visits 11 Sept - 19 Oct | Traveleads | 413.56 |  | 413.56 |  | 413.56 | 201704926 | September. Invoices signed off.
ZK106.K247.I009 | . | ZK106 | K247 | I009 | Staples clear out for rehearsals | 2017-09-12 |  | 300 |  | 300 | } | 0
|  | ZK106 | K247 | I009 | Staples roller shutter service | for structure storage and rehearsal |  | 75 |  | 75 | }
ZK106.K248.I009 | . | ZK106 | K248 | I009 | PA system for rehearsals |  |  | 169 |  | 169 |  | 0
[5 empty] | Marketing |  |  |  | 12200
.. | . |  |  |  | To be fully scoped (Marketing Campaigns, including print) |  |  | 7200 |  |  |  | 0
.. | . |  |  |  | To be fully scoped (Production Branding / Print Costs) |  |  | 5000 |  |  |  | 0
[10 empty] | 2125.7 |  | 1049.73

## I010 - Crates
|  | LOGG I010 - Crates |  |  |  |  | Allocated Budget |  | 61000 | Committed |  | Actuals | Purchase Order | Notes
[7 empty] | Working Budget | Sum of below | 61000
|  | Cost Centre | Sub code | Analysis code | Item | Notes | Calculation
[5 empty] | PHASE 1 |  |  |  | 35035
ZK101.K207.I010 | . | ZK101 | K207 | I010 | Commission to Walk the Plank |  |  | 34000 |  | 34000 |  | 34000 | 201702649
ZK106.K244.I010 | . | ZK106 | K244 | I010 | Overalls etc |  |  | 0 |  |  | } | 0
ZK106.K244.I010 | . | ZK106 | K244 | I010 | Security | Freedom Centre | 3 nights x 2 people | 875 |  | 875 | ] | 875 | 201703054
|  | ZK106 | K244 | I010 | Green Ginger Stencils (12) |  |  | 160 |  | 160 | } | 160
[5 empty] | PHASE 2 |  |  |  | 25965
ZK101.K208.I010 | . | ZK101 | K208 | I010 | Transport | All to be fully scoped |  | 5000 |  |  | } | 0
ZK101.K208.I010 | . | ZK101 | K208 | I010 | Commission + build |  |  | 15000 |  |  | }
ZK106.K245.I010 | . | ZK106 | K245 | I010 | Misc |  |  | 5965 |  |  |  | 0
[10 empty] | 35035 |  | 35035

## I011 - Time Capsule
|  | LOGG I011 - Time Capsule |  |  |  |  | Allocated Budget |  | 15000 | Committed | Actuals | Purchase Order | Notes
[7 empty] | Working Budget | Sum of below | 15000
|  | Cost Centre | Sub code | Analysis code | Item | Notes | Calculation
[5 empty] | COMMISSIONS |  |  |  | 7500
ZK101.K207.I011 | . | ZK101 | K207 | I011 | Nominal allowance until scoped further |  |  | 7500 |  |  | 0
[5 empty] | EVENT / PRODUCTION |  |  |  | 7500
ZK106.K227.I011 | . | ZK106 | K227 | I011 | Nominal allowance until scoped further |  |  | 7500 |  |  | 0
[10 empty] | 0 | 0

## I012 - Book
|  | LOGG I012 - Book |  |  |  |  | Allocated Budget |  | 120000 | Committed | Actuals | Purchase Order | Notes
[7 empty] | Working Budget | Sum of below | 120000
|  | Cost Centre | Sub code | Analysis code | Item | Notes | Calculation
[5 empty] | CREATIVE |  |  |  | 25000
ZK101.K207.I012 | . | ZK101 | K207 | I012 | Writer / illustrator |  |  | 15000 |  |  | 0
ZK101.K208.I012 | . | ZK101 | K208 | I012 | Designer |  |  | 10000 |  |  | 0
[5 empty] | PRINT |  |  |  | 55000
ZK109.K138.I012 | . | ZK109 | K138 | I012 | LS provided rough figure | full colour, pur bound,60pp | Based on c. 120,000 | 55000 |  |  | 0
[5 empty] | DISTRIBUTION |  |  |  | 40000
ZK109.K271.I012 | . | ZK109 | K271 | I012 | Royal Mail costs | LS provided rough quote |  | 40000 |  |  | 0
[10 empty] | 0 | 0

## I013 - Fellowship
|  | LOGG I013 - Fellowship |  |  |  |  | Allocated Budget |  | 19500 | Committed |  | Actuals | Purchase Order | Notes
[7 empty] | Working Budget | Sum of below | 19500
|  | Cost Centre | Sub code | Analysis code | Item | Notes | Calculation
[5 empty] | WEBSITE DEVELOPMENT |  |  |  | 5000
ZK109.K273.I013 | . | ZK109 | K273 | I013 | Technical build and design fees, domain name registering, hosting etc |  | figure from DW | 5000 |  | 5000 |  | 5000
[5 empty] | CONTENT DEVELOPMENT PHASE 1 |  |  |  | 5270.93
ZK101.K207.I013 | . | ZK101 | K207 | I013 | Director | Alex Mitchell |  | 750 |  | 750 |  | 750 | 201702973
ZK101.K208.I013 | . | ZK101 | K208 | I013 | Designer / Prop buyer | Emily Anderton |  | 300 |  | 300 |  | 300 | 201703014
ZK101.K208.I013 | . | ZK101 | K208 | I013 | Props maker | Beckie May | Materials and Labour | 244 |  | 244 |  | 244 | 201703091
ZK101.K209.I013 | . | ZK101 | K209 | I013 | Actors | Adam Bassett |  | 300 |  | 300 |  | 300 | 201702972
ZK101.K209.IO13 | . | ZK101 | K209 | IO13 | Actors | Cal Stockbridge |  | 364.56 |  | 364.56 |  | 364.56 | 201703079
ZK101.K210.I013 | . | ZK101 | K210 | I013 | Materials & tech | Amazon - credit card |  | 181.39 |  | 181.39 |  | 181.39 | Credit Card
ZK101.K210.IO13 | . | ZK101 | K210 | IO13 | materials and Tech | Petty cash |  | 90.8 |  | 90.8 |  | 90.8 | Petty Cash
ZK101.K211.I013 | . | ZK101 | K211 | I013 | Costume | Boilersuits and lab coats |  | 276.4 |  | 276.4 |  | 276.4 | 201702674
ZK101.K212.I013 | . | ZK101 | K212 | I013 | BSL Interpreter | AA Global |  | 260 |  | 260 |  | 260 | 201702979
ZK101.K212.I013 | . | ZK101 | K212 | I013 | BSL Interpreter | Amy Tomlinson |  | 193 |  | 193 |  | 193 | 201702971
ZK101.K213.I013 | . | ZK101 | K213 | I013 | Photographer | Sodium | Vault photoshoot | 750 |  | 750 |  | 0 | Reduced from £1000 to £750 - remainder moved to Marketing below. | To be journalled from digital
ZK101.K214.I013 | . | ZK101 | K214 | I013 | Videographer | Josh | GGF HQ filming | 1500 |  | 1500 |  | 0 |  | To be journalled from digital
ZK101.K215.I013 | . | ZK101 | K215 | I013 | Tech petty cash claim 6 | Lunch for filming |  | 60.78 |  | 60.78 |  | 60.78
[5 empty] | CONTENT DEVELOPMENT PHASE 2 |  |  |  | 6000 |  |  |  |  | Place holder code-to be amended later
ZK102.K201.I013 | . | ZK102 | K201 | I013 | To be scoped. | To include all costs assoc. with Fellowship |  | 1020.44 |  |  |  | 0
ZK102.K208.I013 | . | ZK102 | K208 | I013 | Possible Dominic Wilcox Commissions, including all costs |  |  | 0 |  |  |  | 0
ZK102.K217.I013 | . | ZK102 | K217 | I013 | Videographer | Story so Far Video | Josh Moore | 1000 |  |  |  | 0 |  | To be journalled from Digital
|  | ZK102 | K217 | I013 | Teaser trailer editing | Story so Far Video | Patrick Mateer | 1000 | [5 empty] | To be journalled from Digital
ZK102.K209.I013 | . | ZK102 | K209 | I013 | Actors - Story So Far Video | Adam Bassett |  | 164.56 |  | 164.56 |  | 0 | 201704782 | Invoice received 13/9/17 for
|  | ZK102 | K209 | I013 | Actors - Story So Far Video | Cal Stockbridge |  | 100 |  | 100 |  | 100 | 201704767 | invoice received 23/8
ZK102.K281.I013 | . | ZK102 | K281 | I013 | BSL Interpreter - Story so Far video | Jane Kelsall |  | 170 |  | 170 |  | 170 | 201704800 | invoice received 23/8
|  | ZK102 | K272 | I013 | Hull Mag - 5 September | Bluestorm |  | 350 |  | 350 |  |  | 201704891 | Sept payment
|  | ZK102 | K272 | I013 | HDM advert | 2017-09-11 |  | 400 |  | 400 |  |  |  | Sept payment
|  | ZK102 | K272 | I013 | HDM HPTO |  |  | 500 |  | 500 |  |  |  | Sept payment
|  | ZK102 | K272 | I013 | Billboard Ads | Primesight |  | 470 |  | 470 |  |  |  | Sept payment
|  | ZK102 | K272 | I013 | Design for GG Interim Marketing |  |  | 125 |  | 125 |  |  | 201704890 | Invoice sent 5/9, received 12/9
|  | ZK102 | K217 | I013 | Facebook Ads - Likes/Reach |  |  | 400 |  | 400 |  |  | To be jounaled from digital
|  | ZK102 | K217 | I013 | Teaser Trailer Facebook Boost |  |  | 300 |  | 300 |  |  | To be journaled from digital
[5 empty] | Marketing |  |  |  | 3229.07
ZK101.K274.I013 | . | ZK101 | K274 | I013 | Facebook Acts of Wanton Wonder ads |  |  | 219.54 |  | 219.54 |  | 219.54 | To be journaled from digi?
ZK101.K304.I013 | . | ZK101 | K304 | I013 | Facebook Acts of Wanton Wonder ads |  |  | 80.28 |  | 80.28 |  | 80.28 | To be journaled from digi?
ZK109.K272.I013 | . | ZK109 | K272 | I013 | HDM Ad Acts of Wanton Wonder |  |  | 750 |  | 750 |  | 0 | To be journaled from HDM
ZK109.K304.I013 | . | ZK109 | K304 | I013 | Fellowship Business Cards | Process Black Design |  | 50 |  | 50 | } | 50 | 201704309
|  | ZK109 | K304 | I013 | Fellowship Business Cards | Print - 5,000 |  | 142 |  | 142 | } | 142 | 201703726
|  | ZK109 | K304 | I013 | Facebook Advert | GNGG / Fellowship |  | 300 |  | 300 | } |  | To be journaled from digi
|  | ZK109 | K304 | I013 | To be fully scoped (Marketing Campaigns/Digital Ads) | AWW print/dist in I014 |  | 1687.25 |  |  | } |  |  | £691.68 from misc content devel reallocated.
[10 empty] | 14792.31 |  | 8782.75

## I014 - MarComms
|  | LOGG I014 - MarComms |  |  |  |  | Allocated Budget |  | 14200 | Committed |  | Actuals | Purchase Order | Notes
[7 empty] | Working Budget | Sum of below | 14200
|  | Cost Centre | Sub code | Analysis code | Item | Notes | Calculation
[5 empty] | BRANDING |  |  |  | 2100
[5 empty] | Land of Green Ginger brand | Design time | 1 day @ £350 | [6 empty] | 350 | Already posted as actuals in I001
[5 empty] | Green Ginger Fellowship brand | Design time | 1 day @£350 | [6 empty] | 350 | Already posted as actuals in I001
ZK109.K270.I014 | . | ZK109 | K270 | I014 | GGF and Periplum print design time | Process Black | 6 days @ £350 | 2100 |  | 2100 | } | 2100 | 201702958
|  | ZK109 | K270 | I014 | Misc design time | Across as all projects - to be allocated |  | 0 | [6 empty] | Split out across project budgets
[5 empty] | BROCHURE IMAGES |  |  |  | 2100
ZK109.K158.I014 | . | ZK109 | K158 | I014 | Season 1 | Image commissions for LOGG |  | 1200 |  | 1200 |  | 1200
ZK109.K158.I014 | . | ZK109 | K158 | I014 | Seasons 2&3 | LOGG image development for season 2 brochure |  | 900 |  | 900 |  | 900
[5 empty] | MARKETING CAMPAIGNS |  |  |  | 0
[5 empty] | Fellowship | Print, distribution, advertising | I013 | [6 empty] | 2500 | Moved to sit within project budget
[5 empty] | Periplum | As above | I004 | [6 empty] | 6000 | Moved to sit within project budget
[5 empty] | Joshua Sofaer | As above | I005 | [6 empty] | 3500 | Moved to sit within project budget
[5 empty] | Lone Twin | As above | I006 | [6 empty] | 4000 | Moved to sit within project budget
[5 empty] | Aswarm | As above | I007 | [6 empty] | 6000 | Moved to sit within project budget
[5 empty] | Davy and Kristin McGuire | As above | I008 | [6 empty] | 6000 | Moved to sit within project budget
[5 empty] | Macnas | As above | I009 | [6 empty] | 6000 | Moved to sit within project budget
[5 empty] | PRODUCTION BRANDING / PRINT COSTS |  |  |  | 0
[5 empty] | Periplum | Site dressing, wayfinding, signage, resident notification | I004 | [6 empty] | 2500 | Moved to sit within project budget
[5 empty] | Joshua Sofaer | As above | I005 | [6 empty] | 1500 | Moved to sit within project budget
[5 empty] | Lone Twin | As above | I006 | [6 empty] | 2500 | Moved to sit within project budget
[5 empty] | Aswarm | As above | I007 | [6 empty] | 2500 | Moved to sit within project budget
[5 empty] | Davy and Kristin McGuire | As above | I008 | [6 empty] | 2500 | Moved to sit within project budget
[5 empty] | Macnas | As above | I009 | [6 empty] | 5000 | Moved to sit within project budget
[5 empty] | PHOTOGRAPHY AND VIDEO |  |  |  | 9226
ZK109.K159.I014 | . | ZK109 | K159 | I014 | Photography and video | live projects and heralding activity -some crossover with Fellowship | To be fully scoped | 2976 |  |  |  | 0
ZK109.K159.I014 | . | ZK109 | K159 | I014 | Periplum Horse & Carriage Deliveries | Chris Pepper / Jemstar |  | 250 |  | 250 | } | 0 |  |  | To be journaled from Digital
|  | ZK109 | K159 | I014 | Periplum 7 Alleys Photography/GNGG | James Mulkeen |  | 500 |  | 500 | } |  |  |  | Increased from £250 to £500
|  | ZK109 | K159 | I014 | Periplum 7 Alleys Video | Feet First |  | 0 |  | 0 | } |  |  |  | £750 removed as will not be charged.
|  | ZK109 | K159 | I014 | Periplum 7 Alleys/Hull 2017 Claim Video | Feet First |  | 1250 |  | 1250 | } |  |  |  | To be journaled from Digital
|  | ZK109 | K159 | I014 | Gold Nose of Green Ginger Opening | Sean Spencer |  | 250 |  | 250 | } |  |  |  | To be journaled from Digital
|  | ZK109 | K159 | I014 | Re-Redifussion Heralding moments | Patrick Mateer |  | 250 |  | 250 | } |  | Reduced from £500 |  | To be journaled from Digital
|  | ZK109 | K159 | I014 | Longhill Burn pre-event/RRD Voice Collecting | Chris Pepper / Jemstar |  | 500 |  | 500 |  |  |  |  | To be journaled from Digital
|  | ZK109 | K159 | I014 | Re-Redifussion Live | TBC |  | 500 |  | 500 |  |  |  |  | To be journaled from Digital
|  | ZK109 | K159 | I014 | August activity | TBC |  | 1000 | [6 empty] | To be journaled from Digital
|  | ZK109 | K159 | I014 | McGuires Heralding | TBC |  | 500 | [6 empty] | To be journaled from Digital
|  | ZK109 | K159 | I014 | McGuires Live | TBC |  | 250 | [6 empty] | To be journaled from Digital
|  | ZK109 | K159 | I014 | Macnas Heralding, rehearsals, live | TBC |  | 1000 | [6 empty] | To be journaled from Digital
ZK109.K271.I014 | . |  |  |  | FELLOWSHIP CAMPAIGN - wrongly coded |  |  |  | 774
ZK109.K271.I014 | . | ZK109 | K271 | I014 | Acts of Wanton Wonder Print |  |  | 270 |  |  | } | 270
|  | ZK109 | K271 | I014 | Acts of Wanton Wonder distribution | Hull Box Office |  | 504 |  |  | }
[10 empty] | 7700 |  | 4470
Summary of marketing budget moved to sit within project budgets:
[14 empty] | 2500 | Fellowship
[14 empty] | 8500 | Periplum
[14 empty] | 5000 | Joshua Sofaer
[14 empty] | 6500 | Lone Twin
[14 empty] | 8500 | Aswarm
[14 empty] | 8500 | Davy and Kristin McGuire
[14 empty] | 11000 | Macnas

## Marketing info for Laura
Land Of Green Ginger Marketing Budget
Project name | Project code | Cost Centre | Marketing related Budget
Fellowship | I013 | ZK109 | 2500
Periplum | I004 | ZK109 | 8500
Joshua Sofaer | I005 | ZK109 | 5000
Lone Twin | I006 | ZK109 | 6500
Aswarm | I007 | ZK109 | 8500
Davy and Kristin McGuire | I008 | ZK109 | 8500
Macnas | I009 | ZK109 | 11000
Marketing budget to remain in I014 | I014 | ZK109 | 17700
68200
Sub Code | Sub code name | I014 current split
K270 | BRANDING & DESIGN | 900
K271 | DISTRIBUTION COSTS | 6800
K138 | PRINT COSTS
K158 | PHOTOGRPAHY
K159 | FILMING | 10000
K272 | DIGITAL CONTENT CREATION
K273 | WEB DEVELOPMENT
K274 | EVALUATION & RESEARCH
17700

## Summary for James Trowsdale
LAND OF GREEN GINGER SUMMARY AS AT 31.05.2017
TOTAL SHOULD BE | [7 empty] | CASHFLOW | [9 empty] | TOTAL
|  |  |  | BUDGET NAME | BUDGET CODE | BUDGET | ACTUAL SPEND TO DATE | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-02-01
Original |  | 1400000 |  | Umbrella | I001 | 117124.03 | 67818.46 |  | 6743 | 6104 | 16660 | 8327 | 16958 | 9123 | 11449.4 |  |  | 143182.86 | -26058.83
Moved to corporate for salaries | EB, GH, MM | 105000 |  | 2016 | I002 | 137650 | 137650 | [10 empty] | 137650 | 0
Contribution to storage |  | 7000 |  | House | I003 | 33046.37 | 22041.14 | 1228 | 2688 | 2210 | 2210 | 2210 | 2205 | 4565 | 1400 | 1415 | 35.5 | 42207.64 | -9161.27
|  |  |  | Periplum | I004 | 140389.5 | 140389.5 | 2017-05-01: 1903; 2017-06-01: 11302 | 153594.5 | -13205
Budget remaining |  | 1288000 |  | Joshua Sofaer | I005 | 104020.23 | 92556.11 | 3000 | 5781 | 1600 | 7500 | 4100 | 100 | 100 | 100 | 100 | 100 | 115037.11 | -11016.88
|  |  |  | Lone Twin | I006 | 107117.82 | 104631.57 | 2017-05-01: 47977.5; 2017-06-01: 47391; 2017-07-01: 9056; 2017-08-01: 12075.5 | 221131.57 | -114013.75
|  |  |  | Aswarm | I007 | 123403 | 82369.33 | 2017-06-01: 13282; 2017-07-01: 49906; 2017-08-01: 2000; 2017-09-01: 0; 2017-10-01: 5656 | 153213.33 | -29810.33
Current budget splits |  |  |  | Davy & Kristin McGuire | I008 | 132100 | 95000 | 27125 | 12125 | 34125 | 2125 | 0 | 8000 |  |  |  |  | 178500 | -46400
| was | currently |  | Macnas | I009 | 168449.05 | 1049.73 | 35000 | 50250 | 2750 | 2750 | 40750 | 0 | 9500 |  |  |  | 142049.73 | 26399.32
Umbrella | 363000 | 328000 |  | Crates | I010 | 61000 | 35035 | 965 | 0 | 6000 | 0 | 6500 | 0 | 13300 |  |  |  | 61800 | -800
2016 | 140000 | 135888 |  | Time Capsule | I011 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 |  |  |  | 15000 | 0
2017 | 827000 | 830742 |  | Book | I012 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 95000 |  |  | 120000 | 0
|  |  |  | Fellowship | I013 | 19500 | 8782.75 | 2017-05-01: 3880.68; 2017-06-01: 0; 2017-07-01: 27000; 2017-08-01: 1450 | 41113.43 | -21613.43
| 1330000 | 1294630 |  | MarComms | I014 | 14200 | 4470 | 1561 | 2150 | 3707 | 0 | 5007 | 0 | 2305 |  |  |  | 19200 | -5000
[5 empty] | TOTAL | 1293000 | 791793.59 | 122640.18 | 151712 | 142458 | 46770.5 | 66894 | 57919 | 53893 | 107949.4 | 1515 | 135.5 | 1543680.17