| ARTIST | CONTACT | OUTLINE | AREA | KEY DATES | TO DO |
| --- | --- | --- | --- | --- | --- |
| Joshua Sofaer | joshua@joshuasofaer.com http://www.joshuasofaer.com/ | Nose Emporium | Bransholme North Point Shopping Centre – Louise Smith | 27/28 July site visit 28 – 30 August get in 31-4 Sept – Live 5 Sept get out | Contract - Signed Shop Unit - Confirmed Actor x 2 – Hellen Urben & Delivery of set – Louise Smith Tool Box – centre providing Marketing steer – Nose to see you # or 2017? Safeguarding – DBS check to be sent in, policy/guide advice to be given Risk Ass & PL to be sent to centre Set design plan |
| Periplum Claire Raftery Damian Wright | periplumperformance@googlemail.com http://www.periplum.co.uk | Message in a Bottle | East / North | Early July –Site visit Mid July – 1st community workshop Late July 2nd community workshop Early August – 3rd community workshop Mid/late august 7 day residency | Site visit 12 July Awaiting date for first visit – 9th July Possibly Getting delivery options & contacts – Milk float ongoing List of east & north groups – Site visit to Preston Road & Greatfield |
| Davy & Kristin McGuire | davyandkristinmcguire@gmail.com http://www.davyandkristinmcguire.com | Little Film Scenes | North/West Bingo Hall & Anlaby Rd | 7 – 12th Sept Live | Hire car – extra info required by foxy – EB to get other care hire contact for LOGG artists Location advice – Anlaby Road, outside of bingo hall and doorway for 2016 possibly inside for 2017 Permissions for bingo hall Other site along Anlaby Rd to be identified Story board |