PRSF Meeting:

Agenda: 22.03.2017

Present: Gareth Hughes (GH), Clare Drury (CD), Carys Tavener (CT), Sam Hunt (SH), Martin Atkinson (MA).

First 30 mins: Digital Chris Marr (CM), Press Ben McKnight (BM)

- Quick digital and comms catch up.

  - Use of captured footage into short films about each performance. Will we edit of Richard. Just determines his fee?

- We edit from Richard’s footage. MA to communicate with Richard D about footage he has captured and have it edited from this side. Can ask Richard to cover other things within his fee.

- CM to write up brief with GC for artist for wayfinding, map, freesheet.

  - Quick catch up on comms around residencies.

- Eliza has created cup song. CD to share WeTransfer link.

- 25 April: capture Jason Singh for residency visit.

- If artists have their own channels to share things please let us know: CM

Sales:

- Errollyn would be worth direct marketing with places she is working.

- Mica Levi: CM to check if Mica Levi gig at the university can benefit from this data.

- MA: put something in the diary for a press concentrated catch up for PRS.

- Production:

  - Run through Production schedule for the weekend and any elements we think might get in the way.

  - Refer to working budget.

  - Next steps in terms of Production.

  - Volunteer Management: need to engage a volunteer manager for this project. MA: Invite Harriet to next meeting.

  - EMs: when should we engage these? Stage Managers dealing with front of house. CT to scope EMs and SMs

Run through Production requirements for Residencies.

Residency Day: 24 June 2017

- Clare: outlines 24 June performance day. GH runs down production demands.

- Duty of care must come from groups themselves for the day.

- Gareth flags access restrictions on City Hall.

- Band/Musicians rehearsal 29 June. TBC. Holy Apostle?

Roles and Responsibilities:

- EM company around safeguarding.

- FOH and Production scheduling needs to be done externally. We will need to find budget.

- GH to draw up a spec for this event and costs.

Where are we with artists:

Deadline for technical information: 21 April

Confirm audience capacities: 28 April

- MA to contact Eliza and Liz for final tech spec for performance.

- Anna Meredith: need to get a list from Rhodri of percussion. Need to determine floor space. Thinks we can get another 20 seats. GH continuing conversation.

- Simon Holt: Hoping the stage extension should be in the night before with Music Service and NAPA performance.

- Gavin Bryars: MA to confirm he’s happy with an hour’s rehearsal.

- MA to get Jeremy from BBC up to speed.

- Mica Levi: GH checking they are happy 8ft stage extension.

- Daniel Elms: MA to ask about site visit.

- Ray Lee: Need to get updated plans. Especially in terms of crew costs. GH to go back to Jo to get updates. MA to put something in schedule.

- Laurence Crane: Feels complete. GH to request stage plot.

- Errollyn Wallen: GH to request stage plot.

- Emily Hall: GH to request technical information. Which piano are we putting in Mortimor Suite? GH to determine.

- Hannah Peel: Complete. GH to confirm audience capacity.

- Peter Edwards: GH to ask question on piano. Can Peter take a Yamaha C7 instead of Steinway.

- GH to call Jason Singh about scheduling in rehearsal.

- Jocelyn Pook: GH to chase stage plot.

- Peter Edwards: GH to try and make work with Daniel Elms setup.

- Philip Venables/London Sinf: MA Ask Adam for a Deep clean early on. Offer to pay for this. 9am get in.

- Sam Lee: MA to get technical detail of performance.