PROJECT OVERVIEW – DEPART

| NAME OF PROJECT | Depart |
| --- | --- |
| PROJECT START - FINISH DATES | 04/07/2017 - 30/06/2017 |
| PROJECT LIVE DATES | 18/05/2017 - 21/05/2017 |
| COC PROJECT LEAD | Katy Fuller |
| PROJECT SUMMARY | First performed at LIFT 2016, the production will tour to Hull, Brighton and Blackpool in May 2017. Created by Australian circus company Circa working with a host of collaborating artists, the performance will take place over four nights in Hull's General Cemetery. The audience is taken on a journey through the cemetery with light, sound and video projection installations, punctuated with performances from professional circus artists, young aspiring professional dancers, a community choir and community participant performers. In the build-up to the event, there will be a schedule of workshops and rehearsals with the community volunteer performers and community choir which will be led by professional artists. |
| TARGET AUDIENCES | - Hull Residents - Visitors from elsewhere in Yorkshire - Young People (16-25) |
| CORE PROJECT TEAM | - Katy Fuller (Exec Producer) - Cian Smyth (Producer) - Lindsey Hammond (Assistant Producer) - Sally Cowling (LIFT – Producer) - Any others? |
| ARTISTS | - Em Whitfield Brooks - choir leader - Circa - Others? |
| HERITAGE PARTNERS | - Friends of Hull General Cemetery – Lisa Hewson |
| DELIVERY PARTNERS | - LIFT - NCCA - Spitalfields Music - Brighton Festival - LeftCoast - Events Company? |
| PROJECT SPECIFIC AIMS & OBJECTIVES TO MEASURE | Use the Depart production as a tool to develop circus engagement in the city - Create an opportunity to develop circus audiences in Hull by bringing a performance of this under-represented art form to the city - Create opportunities for local performers and members of the community to participate in a circus production Create an internationally significant and artistically exceptional new piece of work - Use a unique event site for performance for the first time - Work in partnership with creative partners to develop a new piece of work that is of high quality |
| HULL 2017 STRATEGIC AIMS & OBJECTIVES THAT THE PROJECT IS CONTRIBUTING TO | High quality programme of arts, culture and heritage - 365 days of cultural programme that is ‘of the city’ yet outward looking and includes 60 commissions - Improving understanding and appreciation of Hull’s heritage Develop audiences - Increase total audiences for Hull's arts, cultural and heritage offer - Increase engagement and participation in arts and heritage amongst Hull residents - Increase the diversity of audiences for Hull’s arts and heritage offer Strengthen Hull and East Riding economy - Increase visitor numbers to Hull Improve wellbeing through engagement and participation - Increase levels of happiness and enjoyment as a result of engaging with arts and culture - Increase levels of confidence and community cohesion among local audiences and participants Increase aspirations, abilities and knowledge of residents - Delivery of training and development opportunities to local residents through arts and culture initiatives |
| SUMMARY OF DATA COLLECTION METHODS | - Project Monitoring Workbook - Audience Survey - Participant Survey - Creative Partners Survey |

PROJECT MONITORING & EVALUATION PLAN – PROJECT SPECIFIC AIMS & OBJECTIVES

| AIMS | OBJECTIVES | OUTPUTS & OUTCOMES | WHO YOU'LL GATHER INFORMATION FROM | METHOD OF DATA COLLECTION | WHEN TO GATHER DATA | RESOURCES | PERSON(S) RESPONSIBLE |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Use Depart as a vehicle to develop circus engagement in the city | Create an opportunity to develop circus audiences in Hull by bringing a performance of this under-represented art form to the city | - % of audience introduced to contemporary circus for the first time - Postcode origins of attendees (% visitors to the city for purpose of attending performance; % Hull residents from areas less likely to engage with the arts) | Audience Members | Audience Survey | W/C 22nd May 2017 | Staff Time | Pippa Gardner |
|  | Create opportunities for local performers and members of the community to participate in a circus production | - # Freelance Contracts (5 in PID) - # local community choir participants (100) - # volunteer cast participants (15) - # circus champion performers (5) | Project Team | Project Monitoring Workbook | Ongoing | Staff Time | Pippa Gardner |
| Create an internationally significant and artistically exceptional new piece of work | Use a unique event site for performance for the first time | - % of audience visiting Hull General Cemetery for the first time - % of audience attending an outdoor performance for the first time - % of audience attending arts and cultural event in a cemetery for first time - % of audience attending contemporary circus for the first time - Audience responses to: "how do you feel about the use of the site within the performance?" | Audience Members | Audience Survey | W/C 22nd May 2017 | Staff Time | Pippa Gardner |
|  |  | - Use of Hull General Cemetery for a contemporary circus performance for the first time | Project Team | Project Monitoring Workbook | N/A | N/A | Pippa Gardner |
|  | Work in partnership with creative partners to develop a new piece of work that is of high quality | - Successful delivery of project in partnership with LIFT, NCCA and Spitalfields Music | Creative Partners | Creative Partner Survey | W/C 22nd May 2017 | Staff Time | Pippa Gardner |
|  |  | - Successful delivery of project in partnership with the friends of Hull General Cemetery | Friends of Hull General Cemetery Contact – Lisa Hewson | Telephone/Email Interview? | ? | Staff Time | Pippa Gardner |
|  |  | - Performance rated as high quality by Creative Partners and Audiences | Creative Partners Audience Members | Creative Partner Survey Audience Survey | W/C 22nd May 2017 | Staff Time | Pippa Gardner |

PROJECT MONITORING & EVALUATION PLAN – HULL 2017 AIMS & OBJECTIVES

| AIMS | OBJECTIVES | OUTPUTS & OUTCOMES | WHO YOU'LL GATHER INFORMATION FROM | METHOD OF DATA COLLECTION | WHEN TO GATHER DATA | RESOURCES | PERSON(S) RESPONSIBLE |
| --- | --- | --- | --- | --- | --- | --- | --- |
| High quality programme of arts, culture and heritage | 365 days of cultural programme that is ‘of the city’ yet outward looking and includes 60 commissions | - 1 new contemporary circus commission | Project Team | Project Monitoring Workbook | Ongoing | Staff time | Pippa Gardner |
| Develop audiences | Increase total audiences for Hull's arts, cultural and heritage offer | - # audience members | Project Team | Project Monitoring Workbook | W/C 22nd May | Staff time | Pippa Gardner |
|  | Increase engagement and participation in arts and heritage amongst Hull residents | Increase engagement and participation in arts and heritage amongst Hull residents | - % of audience attending an outdoor performance for the first time | Audience Members | Audience Surveynd May | W/C 22nd May | Staff time |
|  | Increase the diversity of audiences for Hull’s arts and heritage offer | - % Hull residents from areas less likely to engage with the arts | Audience Members | Audience Survey | W/C 22nd May | Staff time | Pippa Gardner |
| Strengthen Hull and East Riding economy | Increase visitor numbers to Hull | - % visitors to the city for purpose of attending performance | Audience Members | Audience Survey | W/C 22nd May | Staff time | Pippa Gardner |
| Improve wellbeing through engagement and participation | Increase levels of happiness and enjoyment as a result of engaging with arts and culture | - % agree or strongly agree that it was an enjoyable experience | Audience Members Community Choir and Other Performance Participants | Audience Survey Participant Survey | W/C 22nd May | Staff time | Pippa Gardner |
|  | Increase levels of confidence and community cohesion among local audiences and participants | - % report increase in confidence levels as a result of participating in performances - % agree or strongly agree that they have interacted with people they wouldn’t otherwise have | Community Choir and Other Performance Participants | Participant Survey | W/C 22nd May | Staff time | Pippa Gardner |
| Increase aspirations, abilities and knowledge of residents | Delivery of training and development opportunities to local residents through arts and culture initiatives | - # Freelance Contracts (5 in PID) - # local community choir participants (75 in PID) - # local young people participants (25 in PID) - # training and participation opportunities | Project Team | Project Monitoring Workbook | Ongoing | Staff time | Pippa Gardner |