## Detailed Critial Path
Event Name: Made in Hull
Client: Hull City of Culture
Event Date: 1st January - 15th January
Project Code:
Revision
Current week commencing
KEY
Milestones |  |  |  | No. of Months | 5 |  |  | 4 |  |  |  | 3 |  |  |  |  | 2 |  |  |  | 1 |  |  |  | 0
Completed |  |  |  | Month | August |  |  | September |  |  |  | October |  |  |  |  | November |  |  |  | December |  |  |  | January
Needs Immediate Action |  |  |  | Weeks before Parade
|  |  |  | Days | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m
Dates
Key Meetings | Start Date | End Date | Notes | Name / Responsibility
Internal Project Team Meetings | 2016-07-25 | 2016-01-31 | every 2 weeks, moving to every week in october
Creative Project Team Meetings (face to face) | 2016-07-25 | 2016-12-01 | every 2 weeks
Production agency Conference call (weekly) | 2016-08-01 | 2017-01-31
Artists Stakeholder Meetings | 2016-08-08
Internal Debrief | 2017-01-20 | 2018-01-20 | TBC in line with Board timelines
External Debrief | 2017-01-25 | 2017-01-25 | TBC in line with Board timelines
Wash up report meeting |  | 2017-01-31 | TBC in line with Board timelines
Fruit visit possible scenic suppliers discussion (GC dependant) | 2016-11-03
Interpretation meeting 9am-11am | 2016-11-04
Design and orientation meeting (AL/DM/DJ/CC/NH) | 2016-11-04
Full technical meeting (call 14.30-16.30) | 2016-11-09
All artists meeting with core creative team (12pm-2pm) | 2016-11-15
Technical meeting with GC and possible suppliers (2pm-4.30pm) | 2016-11-15
Art Commisioning
Creative kick off meeting with key internals. | 2016-07-25 | 2017-07-25
Identify artists for intrest to tender | 2016-08-01 | 2016-08-08
Create deck for briefing and brief | 2016-08-16 | 2016-08-17
Artist tender for intrest deadline | 2016-08-16 | 2016-08-17
contracted: Artists chosen. | 2016-08-16 | 2016-08-17
Individual brief writing | 2016-08-17 | 2016-08-20 |  | NH/RC
Meeting Phase 1 to answer queries with each artist chosen | 2016-08-08 | 2016-08-16 | urban productions will be on the 5th sept.
Phase 2 and engagement with senior team | 22./08/16 | 2016-09-27
sign off of concept | 2016-10-17 | 2017-10-17
design development | 2016-10-18 | 2016-10-31
production development | 2016-10-18 | 2016-10-31
tech development | 2016-10-21 | 2016-12-01
sign off R&D | 2016-11-03
Wash up report meeting
Stage 1 sign off artists | 2016-11-21
Sign off point 2 | 2016-12-06
Final agreed delivery date and sign off if not agreed from above | 2016-12-12
Cut off (creative) | 2016-12-19
Creative
Creative Kick off Project meeting | 2016-07-25
Core team meeting | 2016-08-08 | 2017-01-31
Continuous stakeholder client liaison | TBC | TBC
Present creative themes and core concepts to Board and stakeholders | TBC | TBC
Review of creative themes and core concepts with wider teams (fortnightly meeting) | 2016-09-01 | 2016-12-15
Approval of scope on creative themes and core concepts | 2016-08-16 | 2016-08-17
3D scope of works briefed and commenced. (design) | 2016-08-17 | 2016-08-31
Sound design scope developed. | 2016-08-17 | 2016-11-01
Present technical production for approval | TBC | TBC
H&S approve technical production and operational plans | TBC | TBC
Stakeholder meetings (inclusive of media partners) | 2016-10-01 | 2016-12-01
Inter-agency liaison with depatrtment leads: Design, Interptritation, Digital, Marketing, PR | 2016-08-25 | 2016-01-15
written word first draft (narartive) | 2016-07-25 | 2016-08-08
Development Phase 1 | 2016-08-08 | 2016-08-22
Decvelopment Phase 2 | 2016-08-22 | 2016-09-27
wriitten word narrative sign off. | 2016-09-30 | 2016-10-01
Post-event reconciliation with boards for stakeholders. | 2017-01-31 | 2017-01-31
Finance Stages & Reconciliation
Contracts of artists and core team agreed & finalised | 2016-08-01 | 2016-09-01
Budget approved | 2016-08-08 | 2016-09-01
Payment schedule agreed | 2016-09-01
Artists Contract signed | 2016-09-01 | 2016-09-12
T&Cs and payment schedules agreed with suppliers | 2016-10-01 | 2016-10-24
Purchase orders sent to suppliers | TBC | TBC
Budget reconciled | 2017-01-31 | 2017-01-31
General Project
Approval of operational project scope | 2016-08-15 | 2016-10-03
Stakeholder management: Internal and external | 2016-08-15 | 2017-01-31
Programming, interpritation and design Concept and strategy development | 2016-08-22 | 2016-10-10
Operations management draft complted. | 2016-08-22 | 2016-10-01
Onsite
Reccees for (external programming) | 2016-08-08 | 2016-09-12
Load in dates | 2016-12-20 | 2016-12-28
Tech and creative rehersal period | 2016-12-28 | 2016-12-31
Live dates: | 2017-01-01 | 2017-01-15
Site de-rig and official handover of space back to Holticulture / Operations. | 2017-01-15 | 2017-01-17
Sponsorship
Identify key partners/opportunities and VIK deals | TBC | TBC
Engagement with partners/sponsors | TBC | TBC
Agree reciprocal benefits for confirmed sponsors and contracts signed if applicable | TBC | TBC
Agree with Directorate any external branding agreements required. | 2016-08-08 | 2016-08-30
Collation of partnership deliverables (e.g. company logos, artwork, text for websites) | 2016-09-01 | 2016-09-19
Activation of sponsor activity | 2017-12-01 | 2017-01-15
Reconciliation report of worth to the sponsors/client | 2017-01-15 | 2017-01-31
Creative design and implimentation
Creative briefed (internal and external) with budget parameters | 2016-08-22 | 2016-09-01
3D Design development key stages outside of artists commisions (outline) deadline | TBC | TBC
Creation of technical drawings | TBC | TBC
Approval/sign-off of final design & 'look & feel' | 2016-08-08 | 2016-10-01
3D elements out for production | 2016-12-01 | 2016-12-12
scheme implimentation | 2016-12-12
scheme sign off and install on site sign off. | 2016-12-29 | 2016-12-31
Way finding
Outline concept and development | 2016-08-22 | 2016-09-25
Scheme sign off | 2016-09-26 | 2016-09-26
3D elements Out for Production | 2016-11-21
Scheme Sign off | 2016-10-22 | 2016-10-22
Artwork | 2016-10-22 | 2016-11-14
Production | 14//11/16 | 2016-12-08
Install on site | 2016-12-12 | 2016-12-29
Staging & Props
Tshirts, fleeces - numbers and sizes | TBC | TBC
Lanyards design | TBC | TBC
Copy for design | TBC | TBC
Artwork | TBC | TBC
Lanyards and clothing Production | TBC | TBC
build in situ | 2016-12-27 | 2016-12-29
| TBC | TBC
Assets & Products
Assets & Product for event identified | 2016-08-16 | 2016-09-16
Quantities and delivery details agreed | 2016-10-16 | 2016-11-16
Storage resourced and agreed (including additional costs if appropriate) | 2016-09-16
Rehersal scope identification f requirement. | 2016-09-16
Items delivered to site for distribution to required area | 2016-12-29 | 2016-12-31
Signage, Branding & Wayfinding design - within the footprint of the route.
Signage & branding requirements identified
Signage & branding spec developed | 2016-09-16
Signage & branding spec approved | 2016-10-16
Print companies identified | 2016-09-16
Design templates approved | 2016-09-16
Design/art working | 2016-10-22 | 2016-11-14
Print company confirmed | 2016-10-16
Stage 1: sign off process for all branding and signage | 2016-11-14 | 2016-11-14
All branding and signage sent to print | 14//11/16 | 2016-12-08
Print adjustments as required | 2016-12-16 | 2016-12-16
Branding & signage delivered to site for install | 2016-12-12 | 2016-12-29
Cross check signage is in correct location | 2016-12-30 | 2016-12-30
Technical Design - infustructure
Technical initial briefing and development
Assigned Production team
Key technical suppliers identified
Supplier briefings & recces
Key technical suppliers contracted
Develop technical production
On-going meetings & discussions with technical suppliers
Queuing CAD and numbers plan designed and submitted
Site plans developed
Structural licensing and planning if required
Site plans issued to key stakeholders
Site plans revised and reissued as required
Final site plans submitted to key stakeholders and departments.
Onsite schedule developed
Onsite schedule issued to key stakeholders
Onsite schedule revised and re-issued as appropriate
Final onsite schedule issued to key stakeholders
Reconciliation report - technical
Whitefriargate shops get in | 2016-12-20 | 2016-12-23
Full get in all locations | 2016-12-26 | 2016-12-28
Tech rehearsals | 2016-12-29 | 2016-12-30
Show | 2017-01-01 | 2017-01-07
Get out of QVS | 2017-01-07
Hand back sites | 2017-01-10
Technical Production services. - Ground Control
Radio Communications Plan produced
PA system - specification produced
Toilets - specification produced (if required)
Power - specification produced
Cable management
Trakway (if required)
Event Capture (Videographer & Photographer)
Engage and contract content capture team | 2016-10-16
Develop strategy & brief | 2016-11-16
Delivery of assets from capture team | 2016-12-16
Complete the post-event internal reporting documents, inclusive of upload of images etc. | 2016-01-17
Edit and upload to social media where applicable | 2016-01-17
Ticketing/Accreditation (Special events)
Tickets onsale for Fruit | 2016-12-05
Accreditation designed, agreed and created | 2016-12-05
Miscellaneous
Contingecy budgeting
IT requirements identified
IT requirements confirmed & ordered
Rehearsal schedules submitted and agreed
Onsite briefing plans submitted and agreed
Event operations management plan distributed
Marketing, Digital and PR
Invite out to all Hull residents | 2016-11-28 |  |  | LS
Digital map interactive | 2016-11-28 |  |  | DW
Posters & banners on local press area
Interpretation rollout | 2016-12-21
Phase 1 building awareness | Oct/Nov
Phase 2 core campaign period | Dec/Jan
Phase 3 follow up audience development | Jan
Direct mail go to print | 2016-10-26
Final print advertising concepts, visualed up and proofed | 2016-11-18
Final approval and radio advert | 2016-11-25
Residential letters drawn up and proofed | 2016-12-01
Foldout wayfinding map go to print | 2016-12-01
Direct mailout delivered to homes in Hull | 2016-12-01 | 2016-12-07
Interpretation boards go to print | 2016-12-01
Additional residential letter to go out to city centre based residents only | 2016-12-08
Interpretation boards printed and finished ahead of Xmas break | 2016-12-22
Foldout wayfinding map delivered to office | 2016-12-22
Installation of all interpreation boards | 2016-12-30 | 2016-12-31

## Operations Project Critical Pat
Event Name: Made in Hull
Client: Hull City of Culture
Event Date: 1st January - 15th January
Project Code:
Revision
Current week commencing
KEY
Milestones |  |  | No. of Months | 5 |  |  |  |  | 4 |  |  |  | 3 |  |  |  |  | 2 |  |  |  | 1 |  |  |  | 0
Completed |  |  | Month | August |  |  |  |  | September |  |  |  | October |  |  |  |  | November |  |  |  | December |  |  |  | January
Needs Immediate Action |  |  | Weeks before Parade
|  |  | Days | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m
|  |  | Dates | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23
|  | Notes | Name / Responsibility
Key Meetings | Internal Project Team Meetings
| Creative Project Team Meetings (face to face) | NEXT MEETING INFO: 3rd Nov (creative team) with the afternoon of the 3rd from 1.30pm - being Durham /Dan/Ala (/NH/ CC) with tech suppliers. 4th Nov Morning of the 4th being for Overall Production meeting with You guys. (not suppliers), Creative Core team. Afternoon of the 4th Creative team meeting only. | GC - KD, CD, TSB. DM | [13 empty] | 03 & 04/11/16
| SAG Meetings |  | GC - KD | [9 empty] | 2016-10-06 |  |  |  |  | 2016-11-10 |  |  |  | 2016-12-08
| Production agency Conference call (weekly) |  | GC - KD
| Tech Meeting - Blueman / PRS, Whitefriar Gate Shop meeting with artists 10:15-11:15, The Deep 12:30-14:00, production supplier meetings 15:30-17:30 |  | NH, KD | [11 empty] | 2016-10-17
| Tech Meeting - Whitefriar Gate 11:15 & VT tech company meetings PM |  | NH, KD | [11 empty] | 2016-10-18
| Supplier site visit & Internal supplier meeting with Chris Clay |  | GC - KD, CD, DM, JG, MD | [13 empty] | 2016-11-03
| Creative Meeting |  | KD, DM | [13 empty] | 2016-11-04
| Highways Meeting |  | KD | [13 empty] | 2016-11-04
| On site / live ELT | Scheduled daily | Emergency liaison team including Ras
| Hot debriefs - show | Scheduled daily | EM team - EM, site, production, venue, stage, security
Internal Debrief
| External Debrief | Post event, date TBC | GC - KD, CD, TSB. DM
Wash up report meeting
Licensing, Approval & Permissions | Licensing, Approval & Permissions processes commences
Premises License submitted
Newspaper advertising of licence application
Premises notice notice of application (28 consecutive days starting from the day after the day the application is made)
Licensing, Approval & Permissions Secured
No Objection from stakeholders
Temporary Traffic Order
Acoustic consultant - pre event background assessment
Acoustic consultant - on the day monitoring and reporting
Resident Mitigation plan developed
Financials /Contracting - Client | Phase 1 budget prepared
Phase 1 Budget approved
Phase 2 budget prepared
Phase 2 budget approved
Phase 3 budget prepared
Phase 3 budget approved
Budget revisions & updates (weekly)
Payment Schedule/ Cancellation Terms
Project Revenue Target met
Reconciliation & Final Invoicing
Audit File
Drawings/ Plans/ Designs | Phase 1 drawings - current site design | In progress, Zeb Yard compelte | JG
Phase 2 drawings - sites with content overlay - updates and amends
Plans issued
Traffic Management | Appoint traffic management company | SEP Traffic Management | KD
| Traffic Management Planning |  | KD
| Road signage plan produced | V1 complete
Traffic Management Stewarding plan produced
Contingency planning
Traffic management infrastructure installed - signage, coness
Traffic management infrastructure removed
Health & Safety | Event Safety Plan as part of ESMP | V1 complete
Contingency planning as part of ESMP
Risk assessments produced alongside the ESMP
Contractor risk assessment, method statements and insurance docs collated and audited
SAG and Table top exercises
First Aid planning produced
Risk & issue management / risk register development
Crowd Management | Pedestrian Signage Plan produced
Crowd Management Planning as part of ESMP process
Crowd Management Stewarding Plan produced as part of ESMP process
Command and Control panel meetings
Emergency procedures developed
Table Top exercises
Stewarding & Security | Agreement of crowd and traffic management steward resourcing and allocation plans
| Site Security planning |  | KD
Site Security plan produced
Contingency planning
Table top exercises
Steward and security logistical plan agreed
Media Management | Discuss media requirements
Develop accreditation plan
Venue Management | Investigate ELT position
Technical Production | Projection rate card spend to suppliers |  | TSB / DM | [7 empty] | 2016-09-21
| Projection rate card returned from suppliers |  | TSB / DM | [8 empty] | 2016-09-30
| Bluman Associates appointed as projection supplier |  | TSB / DM | [10 empty] | 2016-10-14
| Audio / lighting tender sent to suppliers |  | TSB / DM | [11 empty] | 2016-10-20
| Audio / lighting tender returned |  | TSB / DM | [12 empty] | 2016-10-28
| Appointment of audio / lighting supplier |  | TSB / DM | [13 empty] | 2016-10-31
| Quotes returned from audio / lighting suppliers |  | TSB / DM | [14 empty] | 2016-10-11
| PA System - Specification produced per location |  | TSB / DM
| Video / Projection Mapping - Specification produced per location |  | TSB / DM
| Production Schedule |  | TSB / DM
| Venue matrix | Master doc per venue - spec, briefs, operating times, facilities | TSB / DM
| 3d renders produced |  | TSB / DM
| Staffing plan |  | TSB / DM / KD / CD
| Resources management plan |  | TSB / DM
Site Management | Power supplier tender sent out |  | JG / MD | [12 empty] | 2016-10-25
| Power supplier tender returned |  | JG / MD | [13 empty] | 2016-10-31
| Power supplier confirmed |  | JG / MD | [15 empty] | 2016-11-14
| Power - Specification produced |  | JG / MD
| Site build and derig Schedule |  | JG / MD | [17 empty] | 2016-11-28
| Fencing (including CCB Barrier) quantities |  | JG / MD | [14 empty] | 2016-11-10
| Cable management |  | JG / MD
| Boneyard location confirmed |  | JG / MD / CC
| Back of house compounds - specification |  | JG / MD
Signage Planning | CM Signage Plans compiled
CM Signage Plan authorised/signed off
CM Art work to graphics company
Health & Safety / CMP Signage produced
CM Signage installed
TM Signage plans compiled
TM Signage plans authorised/sign-off
TM Signage produced
TM Signage Installed
Financials/Contracting - Suppliers | Supplier Terms & Conditions |  | KD / FINANCE
| Supplier Payment Schedule |  | KD / FINANCE
| POs |  | KD / FINANCE
Hull City of culture and Ground Control Operations | Insurance |  | KD / CD
| Noise Management |  | KD / CD
| ELT Specification |  | KD / CD
| Submit Production Plans to Local Authorities |  | KD / CD
| Radio Communications Plan produced |  | KD / CD
| Onsite IT Requirements/ Scoping Doc |  | KD / CD
| Onsite Financial Requirements |  | KD / CD
| Onsite Equipment Requirements |  | KD / CD
| Project Overview |  | KD / CD
| Onsite Schedule & Key Docs |  | KD / CD
| Job Close Processes |  | KD / CD
Crew and project team logistics | Accommodation
Travel
Refreshments
Accreditation - different levels and production agreed
Crew and performer Welfare
| Crew Handbook |  | CD / KD
Legal Requirements | Identify legal requirements e.g. planning permission/ licenses
Obtain appropriate permissions/ licenses
Data sharing agreement
Sustainability | Identify project team champion
Stakeholder Register
Communication Plan with stakeholders
Sustainability Management Tracker
Event Impact Assessment

## Stakeholder Meeting Dates
Event Name: Made in Hull
Client: Hull City of Culture | [8 empty] | Current week commencing
Event Date: 1st January - 15th January |  |  |  | Current week commencing |  |  |  |  | `
Project Code:
Revision |  |  | No. of Months | 5 |  |  | 4 |  |  |  | 3 |  |  |  |  | 2 |  |  |  | 1 |  |  |  | 0
|  |  | Month | August |  |  | September |  |  |  | October |  |  |  |  | November |  |  |  | December |  |  |  | January
Weeks before Happening
|  |  | Days | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m
Dates
Key Dates & Trigger Points |  | Notes | Name / Responsibility
Sean holiday and away times | 21st August to the 5th September
6th - 12th October
Chris Holiday | 25th Sept to the 3rd October
Ala holiday | 24th August to the 4th September
5th October 12th October (out of the country)
22nd October to the 30th October (can only work from London)
Niccy | 24th August
Bank Holidays | Christmas
Boxing Day
Bank Holidays
Other relevant dates | Local Authority elections
Possible Dates - Scenarios
Core Group Milestones
3rd Oct | Review artists R&D and agree into production and development stage | Complete | NH
4th Oct | Create master technical list with GC |  | CC/NH
28th Oct | Send draft contracts to all artists |  | WH
8th Nov | Leeds based artists in situ |  | SM/NH
10th & 11th Nov | London based artists in situ |  | SM/NH
15th Nov | Get all artists and technical together for production meeting 12pm-2pm
21st Nov | Stage 1 sign off artists
6th Dec | Sign off point 2
12th Dec | Final agreed delivery date and sign off if not agreed from above
19th Dec | Cut off (creative)
20th Dec | Fit up Whitefriargate
26th Dec | Get in across all locations bar Whitefriargate
29th Dec | Technical Rehearsals |  | CC & Technical
30th Dec | Rehearsals and sign off |  | NH/AL
1st Jan | First show (open till 10pm)
7th Jan | Last day of show and complete get out of QVS |  | CC/KD
10th Jan | Hand site back to full public access |  | KD

## Community Engagement Plan
Event Name: Made in Hull
Client: Hull City of Culture
Event Date: 1st January - 15th January
Project Code:
Revision
Current week commencing
|  |  | No. of Months | 5 |  |  | 4 |  |  |  | 3 |  |  |  |  | 2 |  |  |  | 1 |  |  |  | 0
|  |  | Month | August |  |  | September |  |  |  | October |  |  |  |  | November |  |  |  | December |  |  |  | January
|  |  | Weeks before Parade | 14
|  |  | Days | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m
|  |  | Dates | 3rd
Key Dates & Trigger Points |  | Notes | Name / Responsibility
Bank Holidays | Christmas
Boxing Day
Bank Holidays
Other relevant dates | Local Authority elections
Possible Parade Dates - Scenarios
Community Engagement Comms Plan | Agree Locations can take place
Detailed assesement and understanding of impacts
Agree advice and information / develop and finalise factsheet
Submit TMO / Premises Licence
Inform PR & Media?
Community & stakeholder engagement - ongoing comms
Community & stakeholder engagement - letter & map highlighting route / closures / estimated timings
Hull website live with copy & map highlighting route / closures / estimated timings
BHF website live copy & map highlighting route / closures / estimated timings
Day Activity.
Online comms messaging
Hotline for residents to call?