## OVERVIEW
21.02.17
TITLE OF EVENT | The 7 Alleys
PRODUCTION | Periplum | Artistic content and production
TECHNICAL | TG Events | Site and production management
EVENT | Hull2017 | Event management
VENUE | East Park | Gardens to the front of the Pavilion, behind the Pavilion, the road way leading to the Pavilion, the Arena to the left of the roadway
SPECIFICATION | Show is a promenade piece involving set action performance pieces around the Pavilion and Arena of East Park, the show will involve stage effects (lighting and sound) plus small scale pyrotechnics (stage material and hand held) | The show will involve a community cast working with professional performers
AUDIENCE PROFILE | Audiences will be invited from the Preston Road area and East Park area via a mail out. Audiences will be asked to claim up to 7 tickets for the show. The show is intended for a family audience.
TICKETED | No
Dates | Friday 28th April | IN
| Saturday 29th April | IN
| Sunday 30th April | BUILD / PM Rehearsals
| Monday 1st May | BUILD / PM Rehearsals
| Tuesday 2nd May | BUILD / PM Rehearsals
| Wednesday 3rd May | SHOW
| Thursday 4th May | SHOW
| Friday 5th May | SHOW
| Saturday 6th May | SHOW
| Sunday 7th May | OUT
| Monday 8th May | OUT
Capacity | 4000 per night
Times | DOORS - 20:45
SHOW - 21:15 - 22:15
CLEAR - 23:00
Duration | 1hr

## SECURITY
PERIPLUM | 7 ALLEYS | SECURITY ROSTA |  |  |  | based on Prestige rates
|  | ROLE | TIMES | NO | HRS | COST PER HR
IN | Friday 28th April | Daytime property protection | 08:00 - 18:00 | 2 | 10 | 12.5 | 250
|  | Overnight property protection | 18:00 - 08:00 | 2 | 14 | 12.5 | 350
IN | Saturday 29th April | Daytime property protection | 08:00 - 18:00 | 2 | 10 | 12.5 | 250
|  | Overnight property protection | 18:00 - 08:00 | 2 | 14 | 12.5 | 350
BUILD / PM Rehearsals | Sunday 30th April | Daytime property protection | 08:00 - 18:00 | 2 | 10 | 12.5 | 250
|  | Overnight property protection | 18:00 - 08:00 | 2 | 14 | 12.5 | 350
BUILD / PM Rehearsals | Monday 1st May | Daytime property protection | 08:00 - 18:00 | 2 | 10 | 12.5 | 250
|  | Overnight property protection | 18:00 - 08:00 | 2 | 14 | 12.5 | 350
BUILD / PM Rehearsals | Tuesday 2nd May | Daytime property protection | 08:00 - 18:00 | 2 | 10 | 12.5 | 250
|  | Overnight property protection | 18:00 - 08:00 | 2 | 14 | 12.5 | 350
SHOW | Wednesday 3rd May | Daytime property protection | 08:00:00 - 20:00 | 2 | 12 | 12.5 | 300
|  | Security Manager | 19:30 - 23:30 | 1 | 4 | 15 | 60
|  | Show stewarding - 3x main gate support 2x Stewards | 19:30 - 23:30 | 2 | 4 | 11.5 | 92
|  | Show security - 4x patrolling back of houses | 19:30 - 23:30 | 4 | 4 | 11.5 | 184
|  | Show security - 2x WEST GATE | 19:30 - 23:30 | 2 | 4 | 11.5 | 92
|  | Show security - 2x EAST GATE | 19:30 - 23:30 | 2 | 4 | 11.5 | 92
|  | Show Security - 2x NORTH GATE *(Blue badge entrance) | 19:30 - 23:30 | 2 | 4 | 11.5 | 92
|  | Overnight property protection | 23:00 - 08:00 | 2 | 9 | 12.5 | 225
SHOW | Thursday 4th May | Daytime property protection | 08:00:00 - 20:00 | 2 | 12 | 12.5 | 300
|  | Security Manager | 19:30 - 23:30 | 1 | 4 | 15 | 60
|  | Show stewarding - 3x main gate support 2x Stewards | 19:30 - 23:30 | 2 | 4 | 11.5 | 92
|  | Show security - 4x patrolling back of houses | 19:30 - 23:30 | 4 | 4 | 11.5 | 184
|  | Show security - 2x WEST GATE | 19:30 - 23:30 | 2 | 4 | 11.5 | 92
|  | Show security - 2x EAST GATE | 19:30 - 23:30 | 2 | 4 | 11.5 | 92
|  | Show Security - 2x NORTH GATE *(Blue badge entrance) | 19:30 - 23:30 | 2 | 4 | 11.5 | 92
|  | Overnight property protection | 23:00 - 08:00 | 2 | 9 | 12.5 | 225
SHOW | Friday 5th May | Daytime property protection | 08:00:00 - 20:00 | 2 | 12 | 12.5 | 300
|  | Security Manager | 19:30 - 23:30 | 1 | 4 | 15 | 60
|  | Show stewarding - 3x main gate support 2x Stewards | 19:30 - 23:30 | 2 | 4 | 11.5 | 92
|  | Show security - 4x patrolling back of houses | 19:30 - 23:30 | 4 | 4 | 11.5 | 184
|  | Show security - 2x WEST GATE | 19:30 - 23:30 | 2 | 4 | 11.5 | 92
|  | Show security - 2x EAST GATE | 19:30 - 23:30 | 2 | 4 | 11.5 | 92
|  | Show Security - 2x NORTH GATE *(Blue badge entrance) | 19:30 - 23:30 | 2 | 4 | 11.5 | 92
|  | Overnight property protection | 23:00 - 08:00 | 2 | 9 | 12.5 | 225
SHOW | Saturday 6th May | Daytime property protection | 08:00:00 - 20:00 | 2 | 12 | 12.5 | 300
|  | Security Manager | 19:30 - 23:30 | 1 | 4 | 15 | 60
|  | Show stewarding - 3x main gate support 2x Stewards | 19:30 - 23:30 | 2 | 4 | 11.5 | 92
|  | Show security - 4x patrolling back of houses | 19:30 - 23:30 | 4 | 4 | 11.5 | 184
|  | Show security - 2x WEST GATE | 19:30 - 23:30 | 2 | 4 | 11.5 | 92
|  | Show security - 2x EAST GATE | 19:30 - 23:30 | 2 | 4 | 11.5 | 92
|  | Show Security - 2x NORTH GATE *(Blue badge entrance) | 19:30 - 23:30 | 2 | 4 | 11.5 | 92
|  | Overnight property protection | 23:00 - 08:00 | 2 | 9 | 12.5 | 225
OUT | Sunday 7th May | Daytime property protection | 08:00:00 - 20:00 | 2 | 12 | 12.5 | 300
OUT | Monday 8th May | NA | NA
6998

## MEDICAL
PERIPLUM | 7 ALLEYS | MEDICAL
WHO
Dates | IN | Friday 28th April | 08:00 - 18:00 | On site staff first aider
| IN | Saturday 29th April | 08:00 - 18:00 | On site staff first aider | ???
| BUILD / PM Rehearsals | Sunday 30th April | 08:00 - 18:00 | On site staff first aider | Periplum
|  |  | 18:00 - 23:00 | 2x first aiders | TBC
| BUILD / PM Rehearsals | Monday 1st May | 08:00 - 18:00 | On site staff first aider | Periplum
|  |  | 18:00 - 23:00 | 2x first aiders | St John
| BUILD / PM Rehearsals | Tuesday 2nd May | 08:00 - 18:00 | On site staff first aider | Periplum
|  |  | 18:00 - 23:00 | 2x first aiders | St John
| SHOW | Wednesday 3rd May | 20:00 - 23:00 | 1x ambulance 2x paramedics | St John
|  |  | 20:00 - 23:00 | 6x First aiders | St John
| SHOW | Thursday 4th May | 20:00 - 23:00 | 1x ambulance 2x paramedics | St John
|  |  | 20:00 - 23:00 | 6x First aiders | St John
| SHOW | Friday 5th May | 20:00 - 23:00 | 1x ambulance 2x paramedics | St John
|  |  | 20:00 - 23:00 | 6x First aiders | St John
| SHOW | Saturday 6th May | 20:00 - 23:00 | 1x ambulance 2x paramedics | St John
|  |  | 20:00 - 23:00 | 6x First aiders | St John
| OUT | Sunday 7th May | 08:00 - 18:00 | On site staff first aider | Periplum
| OUT | Monday 8th May

## VOLUNTEERS (DRAFT)
Periplum
The 7 Alleys
VOLUNTEERS
Saturday 29th April | IN
Sunday 30th April | IN
Monday 1st May | BUILD / PM Rehearsals
Tuesday 2nd May | BUILD / PM Rehearsals
Wednesday 3rd May | SHOW | 4x box office support
4x show information and support
Thursday 4th May | SHOW | 4x box office support
4x show information and support
Friday 5th May | SHOW | 4x box office support
4x show information and support
Saturday 6th May | SHOW | 4x box office support
4x show information and support
Sunday 7th May | OUT
Monday 8th May | OUT

## SITE
6x bay - back stage
10x bay - public
2x - accessible