TITANIUM FIREWORKS

FEE: £50,000 to be paid on receipt of invoice, with future payments subject to final budget confirmation

TERMS: As agreed in the terms and conditions of the Event & Production Management & Delivery Framework

GOODS & SERVICES TO BE PROVIDED:

- Pre-Production

- Design, Programming and simulation

- Health and Safety

- Production and sequencing of fireworks

- Security (at George Dock)

- Equipment Transport

- Insurance

- Radios (comms)

- Dock Infrastructure

- Firing System

- Firing Equipments

- Fireworks

- Management Fee

- Crew (including wages, per diems, transport and accommodation)

TIMETABLE OF DELIVERY

| 31 October 2016 | Delivery of Design and Simulation to Hull 2017 Team |
| --- | --- |
| 7 November 2016 | Design sign off by Hull 2017 Team |
| 28 – 31 December 2016 | Load in, George Dock, Hull |
| 1 January 2017 | Show Day – Display commences 20:17 |
| 2 – 3 January 2017 | Load Out and dock site handover to ABP |
| January 2017 | Debrief |